## Sheet1
Row Labels | Count of HUC 8
20
2022-07-15 | 1
2022-07-18 | 4
2022-07-25 | 2
2022-08-01 | 2
2022-08-05 | 2
2022-08-08 | 2
2022-08-14 | 2
2022-08-15 | 4
2022-08-31 | 1
Approved | 19
N/R | 19
Pending- To be delivered 7/22 | 3
N/R | 3
(blank) | 1
(blank) | 1
Grand Total | 43

## TO1_Review_Tracker (hidden)
TWDB 2D - Base Level Engineering
Independent QA/QC Tracking |  |  | Priority Level | Supplemental Info | Type of QC | First Submittal |  |  |  | Backcheck |  |  |  | Type of QC | First Submittal |  |  |  | Backcheck |  |  |  | Type of QC | First Submittal |  |  |  | Backcheck
|  |  |  | Number of Models Anticipated |  | Planned Data Submission | Actual Submission | Planned Comment Delivery | Actual Comment Delivery | Planned Response Submission | Response Received | Planned Backcheck | Finalized Backcheck |  | Planned Date Submission | Actual Submission | Planned Comment Delivery | Actual Comment Delivery | Planned Response Submission | Response Received | Planned Backcheck | Finalized Backcheck |  | Planned Date Submission | Actual Submission | Planned Comment Delivery | Actual Comment Delivery | Planned Response Submission | Response Received | Planned Backcheck | Finalized Backcheck | Consultant List
Stantec
Watershed Name | Watershed Number | Consultant Responsible |  |  | QC Milestone 1 - Terrain & Modeling Review | [8 empty] | Detailed QC Milestone 2 - Mapping Review Audit Milestone 1 - Terrain, Modeling, Prelim Mapping Review | [8 empty] | QC Milestone 3 - Completeness Check | [8 empty] | Atkins
Double Mountain Fork Brazos | 12050004 | AECOM | 2 | 9 | Audit | [8 empty] | Audit | [8 empty] | Detailed | [8 empty] | Freese & Nichols
Paint | 12060103 | AECOM | 1 | 4 | Detailed | [8 empty] | Detailed | [8 empty] | Detailed | [8 empty] | AECOM
Lower Clear Fork Brazos | 12060104 | AECOM | 2 | 3 | Audit | [8 empty] | Audit | [8 empty] | Detailed | [8 empty] | TWDB
Hubbard | 12060105 | AECOM | 1 | 6 | Audit | [8 empty] | Audit | [8 empty] | Detailed
Middle Colorado | 12090106 | Atkins | 2 | 7 | Audit | [8 empty] | Audit | N/R | 2020-06-27 | [6 empty] | Detailed
Pecan Bayou | 12090107 | Atkins | 2 | 7 | Audit | [8 empty] | Audit | N/R | 2022-06-20 | [6 empty] | Detailed
Jim Ned | 12090108 | Atkins | 1 | 3 | Detailed | N/R | 2022-05-03 | 2022-07-01 | [5 empty] | Detailed | N/R | 2022-05-29 | [6 empty] | Detailed
San Saba | 12090109 | Atkins | 1 | 9 | Audit | [8 empty] | Audit | N/R | 2022-06-20 | [6 empty] | Detailed
Brady | 12090110 | Atkins | 1 | 3 | Audit | [8 empty] | Audit | N/R | 2022-05-29 | [6 empty] | Detailed
Buchanan - LBJ Lakes | 12090201 | Atkins | 2 | 5 | Audit | [8 empty] | Audit | N/R | 2022-06-27 | [6 empty] | Detailed
North Llano* JPM | 12090202 | Atkins |  | 8 | Detailed | 2022-02-03 | 2022-02-03 | 2022-04-25 | 2022-04-25 |  |  |  |  | Audit | [8 empty] | Detailed
North Llano | 12090202 | Atkins | 1 | 8 | Audit | [8 empty] | Audit | N/R | 2022-05-29 | [6 empty] | Detailed
South Llano | 12090203 | Atkins | 1 | 7 | Detailed | N/R | 2022-05-03 | 2022-06-30 | [5 empty] | Detailed | N/R | 2022-05-29 | [6 empty] | Detailed
Llano | 12090204 | Atkins | 2 | 18 | Audit | [8 empty] | Audit | N/R | 2022-06-20 | [6 empty] | Detailed
Austin - Travis Lakes | 12090205 | Atkins | 2 | 4 | Audit | [8 empty] | Audit | N/R | 2022-06-27 | [6 empty] | Detailed | [8 empty] | QC Type List
Upper Brazos - Running Water Draw | 12050005 | Freese & Nichols | 1 | 5 | Detailed | N/R | 2022-03-15 | N/R | 2022-04-11 | N/R | 2022-05-23 | 2022-06-30 |  | Detailed | [8 empty] | Detailed | [8 empty] | Detailed
Upper Brazos - White | 12050006 | Freese & Nichols | 1 | 5 | Audit | [8 empty] | Audit | N/R | 2022-05-23 | 2022-07-08 | [5 empty] | Detailed | [8 empty] | Audit
Upper Brazos - Salt Fork | 12050007 | Freese & Nichols | 1 | 7 | Audit | [8 empty] | Audit | N/R | 2022-05-23 | [6 empty] | Detailed
Upper Brazos - Middle Brazos - Millers | 12060101 | Freese & Nichols | 2 | 9 | Audit | [8 empty] | Audit | N/R | 2022-05-23 | [6 empty] | Detailed
Lower Brazos - San Gabriel | 12070205 | Freese & Nichols | 1 | 5 | Audit | [8 empty] | Audit | N/R | 2022-05-23 | [6 empty] | Detailed
Nueces Headwaters | 12110101 | Stantec | 1 | 4 | Detailed | N/R | 2022-03-17 | N/R | 2022-04-25 |  | 2022-05-10 | 2022-07-05 |  | Detailed | [8 empty] | Detailed
Upper Nueces | 12110103 | Stantec | 2 | 7 | Audit | [8 empty] | Audit | [8 empty] | Detailed
Turkey | 12110104 | Stantec | 1 | 6 | Detailed | N/R | 2022-04-19 | N/R | 2022-05-20 |  |  |  |  | Audit | [8 empty] | Detailed
Middle Nueces | 12110105 | Stantec | 2 | 12 | Audit | [8 empty] | Audit | [8 empty] | Detailed
Upper Frio | 12110106 | Stantec | 2 | 12 | Audit | [8 empty] | Audit | N/R | 2022-05-02 | 2022-07-08 | [5 empty] | Detailed
Hondo | 12110107 | Stantec | 1 | 4 | Detailed | N/R | 2022-04-12 | N/R | 2022-05-20 |  |  |  |  | Audit | [8 empty] | Detailed
West Nueces | 12110102 | TWDB | 1 | 1 | Detailed | N/R | 2021-08-06 | N/R | 2021-09-08 | N/R | 2021-11-17 | N/R | 2021-11-17 | Detailed | 2022-07-08 | [7 empty] | Detailed | 2022-07-15
South Wichita | 11130205 | TWDB | 1 | 1 | Detailed | N/R | 2021-08-06 | N/R | 2021-09-08 | N?R | 2021-11-17 | N/R | 2021-11-30 | Detailed | 2022-07-08 | [7 empty] | Detailed | 2022-07-22
Updated/Edited by HALFF
Edited by TWDB in consulation with BLE Teams
TWDB edits based on recent conversations/correspondence
Partial Deliverable submitted (no mapping)
Priority 1 | 08/31 delivery - 16 HUCs
Priority 2 | 09/30-10/15 delivery - 11 HUCs
Note on P30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: TWDB edit from 06/22/2022 stantec progress report.
Note on Q30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: TWDB edit from 06/22/2022 stantec progress report.

## Mapping Review
Technical Mapping Review | Reference | P/F | Reviewer Comments | Corrective Action | Reviewer Initials | Date Completed | Consultant Response | Response Date | Backcheck initials if sufficient
QC Review [<1 hr]
Review consultant QC process for Mapping & FDR. Documentation has been submitted and all internal QC comments have been addressed. [Addressed = comments have responses and check from backcheck] |  | P | None | None | LH | 2023-08-30
Report should provide all information identified in BLE Report Template | O:\WSC\FSCA\Mapping\CTP\Base Level Engineering\Guidance\202107_v6_BLE Submittal Guidance_R6___FINAL.pdf | P | None | None | LH | 2023-08-30
Report should include a CNMS/NVUE evaluation map (where does BLE support FIRMs, based on Zone A review criteria – similar floodplain width) |  | NA | CNMS not included in this submittal, will be validated at a later date | NA | LH | 2023-08-25 | Noted | 2023-08-30 | GM
S_Pol_AR - File should include all communities that intersect and include some community area within the HUC8 being addressed |  | P | None | None | LH | 2023-08-25
S_Pol_AR - Spatial Reference System should be consistent with guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | P | None | None | LH | 2023-08-25
S_Pol_AR - Null values should be consistent with guidance | O:\WSC\FSCA\Mapping\CTP\Base Level Engineering\Guidance\202107_v6_BLE Submittal Guidance_R6___FINAL.pdf | P | None | None | LH | 2023-08-25
S_Pol_AR - Topology rules should be consistent with guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | P | None | None | LH | 2023-08-30
S_Pol_AR - Spatial information should be submitted in agreement with the guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | F | All political entities should have titles included (e.g. "City of Amarillo") | Add titles to cities and towns in POL_NAME1 | LH | 2023-08-25 | Titles added to cities and towns. No title added to villages. | 2023-08-30 | GM
S_HUC_AR - Spatial Reference System should be consistent with guidance |  | P | None | None | LH | 2023-08-25
S_HUC_AR - Null values should be consistent with guidance | O:\WSC\FSCA\Mapping\CTP\Base Level Engineering\Guidance\202107_v6_BLE Submittal Guidance_R6___FINAL.pdf | P | None | None | LH | 2023-08-25
S_HUC_AR - Topology rules should be consistent with guidance |  | P | None | None | LH | 2023-08-30
S_HUC_AR - Spatial information should be submitted in agreement with the guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | F | Incorrect HUC boundary | Update HUC boundary | LH | 2023-08-25 | Updated | 2023-08-30 | GM
S_HUC_AR - HUC8 watershed boundary based on the USGS Watershed Boundary Dataset |  | F | Incorrect HUC boundary | Update HUC boundary | LH | 2023-08-25 | Updated | 2023-08-30 | GM
SUB-BASINS - For 1d only, Not required for delivery in 2-D BLE analysis watersheds. |  | NA | NA | NA | NA | NA
XS_1D - For 1d only, Not required for delivery in 2-D BLE analysis watersheds. |  | NA | NA | NA | NA | NA
BFE_2D - Null values should be consistent with guidance | O:\WSC\FSCA\Mapping\CTP\Base Level Engineering\Guidance\202107_v6_BLE Submittal Guidance_R6___FINAL.pdf | P | None | None | LH | 2023-08-25
BFE_2D - Topology rules should be consistent with guidance |  | NA | Could not get topology to finish running, pelase confirm that topology was run on this layer and that no errors were found. | NA | LH | 2023-08-30 | Topology unable to be ran due to time constraints. No errors expected | 2023-08-30 | GM
BFE_2D - Spatial Reference System should be consistent with guidance | O:\WSC\FSCA\Mapping\CTP\Base Level Engineering\Guidance\202107_v6_BLE Submittal Guidance_R6___FINAL.pdf | P | None | None | LH | 2023-08-25
BFE_2D - Spatial information should be submitted in agreement with the guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | F | Contours outside of DTL_STUD_AR polygons should be "MAPPED" (or domain 1010) and countours inside of DTL_STUD_AR polygons should be "NOT MAPPED" or (or domain 1020). LEN_UNIT should be USFT (U.S. Survey Ft) if state plane projection was used. | Mark contours inside of DTL_STUD_AR polygons as "NOT MAPPED". Change LEN_UNIT to USFT. | LH | 2023-08-25 | Updated | 2023-08-30 | GM
BFE_2D - Create contours using the 1% annual chance WSEL event grid, in low lying areas, create 1- or 2-foot contours. Where more elevation is included in the study dataset, prepare 5-foot contours. | O:\WSC\FSCA\Mapping\CTP\Base Level Engineering\Guidance\202107_v6_BLE Submittal Guidance_R6___FINAL.pdf | P | None | None | LH | 2023-08-30
WTR_LN - Spatial Reference System should be consistent with guidance | O:\WSC\FSCA\Mapping\CTP\Base Level Engineering\Guidance\202107_v6_BLE Submittal Guidance_R6___FINAL.pdf | P | None | None | LH | 2023-08-25
WTR_LN- Null values should be consistent with guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | P | None | None | LH | 2023-08-25
WTR_LN - Topology rules should be consistent with guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | F | Must not overlap and must be single part | Repair overlaps and multi-part features | LH | 2023-08-30 | Overlaps corrected, singlepart | 2023-08-30 | GM
WTR_LN- Spatial information should be submitted in agreement with the guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | F | WTR_LN_ID values have an extra leading zero and duplicate values. 2 WTR_LNs are missing SHOWN_FIRM and SHOWN_INDX values | Re-assign WTR_LN_ID values. Fill out missing SHOWN_FIRM and SHOWN_INDX values. | LH | 2023-08-25 | Corrected | 2023-08-30 | GM
WTR_LN - model delivery through the MIP uses the same naming convention in WTR_NM. | O:\WSC\FSCA\Mapping\CTP\Base Level Engineering\Guidance\202107_v6_BLE Submittal Guidance_R6___FINAL.pdf | NA | NA | NA | NA | NA
WTR_AR - Spatial Reference System should be consistent with guidance | O:\WSC\FSCA\Mapping\CTP\Base Level Engineering\Guidance\202107_v6_BLE Submittal Guidance_R6___FINAL.pdf | P | None | None | LH | 2023-08-25
WTR_AR - Null values should be consistent with guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | P | None | None | LH | 2023-08-25
WTR_AR - Topology rules should be consistent with guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | P | None | None | LH | 2023-08-30
WTR_AR - Spatial information should be submitted in agreement with the guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | F | WTR_AR_ID values have an extra leading zero. | Remove extra leading zero from WTR_AR_ID values. | LH | 2023-08-25 | Updated | 2023-08-30 | GM
WTR_AR - should include lake/pond/reservoir boundaries available in the NHD Waterbody coverage |  | F | Waterbodies >= 20 acres included, but some smaller waterbodies at NID dams with a 200 acre foot or greater capacity missed. | Inlcude waterbodies at NID dams with a 200 acre foot or greater capacity. | LH | 2023-08-25 | Noted dams included | 2023-08-30 | GM
DTL_STUD_LN - Spatial Reference System should be consistent with guidance | O:\WSC\FSCA\Mapping\CTP\Base Level Engineering\Guidance\202107_v6_BLE Submittal Guidance_R6___FINAL.pdf | P | None | None | LH | 2023-08-25
DTL_STUD_LN - Null values should be consistent with guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | F | Fields CD_POC, CD_ADD1, CD_ADD2, CD_CTY, CD_STATE, CD_ZIP, CD_PHONE, CD_EMAIL, and STATUS should have null values for required if applicable ("Null" or ""). | Change null values for CD_POC, CD_ADD1, CD_ADD2, CD_CTY, CD_STATE, CD_ZIP, CD_PHONE, CD_EMAIL, and STATUS. | LH | 2023-08-25 | Updated | 2023-08-30 | GM
DTL_STUD_LN - Topology rules should be consistent with guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | F | Must be single part | When layer is re-done per comments, ensure features are single part | LH | 2023-08-30 | Single part | 2023-08-30 | GM
DTL_STUD_LN - Spatial information should be submitted in agreement with the guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | F | LOMR_ID should be sequential numbers with leading zeros. | Change LOMR_ID to sequential numbers with leading zeros | LH | 2023-08-25 | Updated | 2023-08-30 | GM
DTL_STUD_AR - Spatial Reference System should be consistent with guidance | O:\WSC\FSCA\Mapping\CTP\Base Level Engineering\Guidance\202107_v6_BLE Submittal Guidance_R6___FINAL.pdf | P | None | None | LH | 2023-08-25
DTL_STUD_AR - Null values should be consistent with guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | F | Fields CD_POC, CD_ADD1, CD_ADD2, CD_CTY, CD_STATE, CD_ZIP, CD_PHONE, CD_EMAIL, and STATUS should have null values for required if applicable ("Null" or ""). | Change null values for CD_POC, CD_ADD1, CD_ADD2, CD_CTY, CD_STATE, CD_ZIP, CD_PHONE, CD_EMAIL, and STATUS. | LH | 2023-08-25 | Updated | 2023-08-30 | GM
DTL_STUD_AR - Topology rules should be consistent with guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | F | Must not have gaps | When layer is re-done er comments, ensure topology is run and gaps are repaired | LH | 2023-08-30 | Updated to singlepart feature to remove gaps | 2023-08-30 | GM
DTL_STUD_AR - Spatial information should be submitted in agreement with the guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | F | LOMR_ID should be sequential numbers with leading zeros. | Change LOMR_ID to sequential numbers with leading zeros | LH | 2023-08-25 | Updated | 2023-08-30 | GM
FLD_HAZ_AR - Spatial Reference System should be consistent with guidance | O:\WSC\FSCA\Mapping\CTP\Base Level Engineering\Guidance\202107_v6_BLE Submittal Guidance_R6___FINAL.pdf | P | None | None | LH | 2023-08-25
FLD_HAZ_AR - Null values should be consistent with guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | P | None | None | LH | 2023-08-25
FLD_HAZ_AR - Topology rules should be consistent with guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | F | Numerous topology issues | Run topology (must not have gaps, must not overlap, must be larger than cluser tolerance) and repair errors | LH | 2023-08-30 | Topology unable to be ran due to time constraints. Additional dissolve and clipping steps ran to ensure no errors | 2023-08-30 | GM
FLD_HAZ_AR - Spatial information should be submitted in agreement with the guidance | O:\WSC\FSCA\Mapping\CTP\Base Level Engineering\Guidance\202107_v6_BLE Submittal Guidance_R6___FINAL.pdf | F | STUDY_TYP should be "BLE". SFHA_TF should be "True" for A zones. | Mark STUDY_TYP as "BLE". Mark A zones as "True" under SFHA_TF. | LH | 2023-08-25 | Updated | 2023-08-30 | GM
FLD_HAZ_AR - 1% and 0.2% floodplains should NOT have overlapping polygon areas. A42 |  | F | Failed Must not overlap topology check | Remove overlaps | LH | 2023-08-30 | Updated | 2023-08-30 | GM
FLD_HAZ_AR - Floodplains and grids should be reviewed against one another. The floodplain coverage and grids must agree at the extents, this is needed to assure that the viewer and report function will be supported. Review EST_RISK = HIGH against 1% grids. Review EST_RISK = MODERATE against 0.2% grids. |  | P | None | None | LH | 2023-08-30
TENPCT_FP - Spatial Reference System should be consistent with guidance | O:\WSC\FSCA\Mapping\CTP\Base Level Engineering\Guidance\202107_v6_BLE Submittal Guidance_R6___FINAL.pdf | P | None | None | LH | 2023-08-25
TENPCT_FP - Null values should be consistent with guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | P | None | None | LH | 2023-08-25
TENPCT_FP - Topology rules should be consistent with guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | F | Must not overlap (also shows must not have gaps errors but these can be ignored as they are a result of the TENPCT not being smoothed) | Repair overlaps | LH | 2023-08-30 | Updated | 2023-08-30 | GM
TENPCT_FP - Spatial information should be submitted in agreement with the guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | F | EST_AR_ID has an extra leading zero. STUDY_TYP should be "BLE". SFHA_TF should be "True" for 10% since it is contained within the 1%. | Remove extra leading zero from EST_AR_ID values. Mark STUDY_TYP as "BLE". Mark SFHA_TF as "True" for all features. | LH | 2023-08-25 | Updated | 2023-08-30 | GM
TENPCT_FP - Floodplains should be reviewed against the TENPCT_FP. Review of the 1% and 10% floodplains against one another to assure that the TENPCT_FP floodplain coverage is similar and does not expand beyond the 1% extent. |  | P | 10% extends beyond 1% because it was not simplified or smoothed, which is correct per guidance. | None | LH | 2023-08-25 | Noted | 2023-08-30 | GM
S_AOMI_AR - Not required | O:\WSC\FSCA\Mapping\CTP\Base Level Engineering\Guidance\202107_v6_BLE Submittal Guidance_R6___FINAL.pdf | F | AOMI_ID has an extra leading zero and count is off by one. Titles (e.g. "county", "city of") missing from Pol_NAME1 values. | Remove extra leading zero from AOMI_ID and recalculate values. Add titles to Pol_NAME1 values. | LH | 2023-08-25 | Updated | 2023-08-30 | GM
S_FRAC_AR - Spatial Reference System should be consistent with guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | P | None | None | LH | 2023-08-25
S_FRAC_AR - Null values should be consistent with guidance | O:\WSC\FSCA\Mapping\CTP\Base Level Engineering\Guidance\202107_v6_BLE Submittal Guidance_R6___FINAL.pdf | P | None | None | LH | 2023-08-25
S_FRAC_AR - Topology rules should be consistent with guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | F | 3 small gaps | Repair gaps | LH | 2023-08-25 | Gaps repaired | 2023-08-30 | GM
S_FRAC_AR - Spatial information should be submitted in agreement with guidance | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | F | SCENAR_ID should be null. | Replace values in SCENAR_ID with "null" or "" (empty string). | LH | 2023-08-25 | Updated | 2023-08-30 | GM
S_FRAC_AR - Check values for accuracy | https://www.fema.gov/sites/default/files/documents/fema_firm-database-technical-reference.pdf | P | None | None | LH | 2023-08-25
S_FRAS_Pt - Not required | O:\WSC\FSCA\Mapping\CTP\Base Level Engineering\Guidance\202107_v6_BLE Submittal Guidance_R6___FINAL.pdf
S_Studies_Ln- do quick spot check of CNMS linework versus study area including current CNMS coverage (S_Studies_LN, S_UnMapped, and NHD coverage) look for blanks or gaps in coverage. Zone X should have status type unverified and Zone A should be assessed. | O:\WSC\FSCA\Mapping\CTP\CNMS\CNMS_Tools_and_Roll_Up (The most recent CNMS database can be located here). O:\WSC\FSCA\ArcGIS_FMP\Shapefiles\NHDM_TX_MedRes.gdb (Most recent NHD database) | NA | CNMS not included in this submittal, will be validated at a later date | NA | LH | 2023-08-25 | Noted | 2023-08-30 | GM
S_UnMapped_Ln- Stream segments from upstream of BLE study should be included in this database, all others should be wrapped up in the S_Studies_Ln feature class. |  | F | CNMS not included in this submittal, will be validated at a later date. Also, Name of S_UnMapped_Ln is incorrect (named “S_Unnapped_Ln”). | Correct name of S_UnMapped_Ln | LH | 2023-08-25 | Corrected | 2023-08-30 | GM
CNMS Static Maps- Report should include a CNMS/NVUE evaluation map (where does BLE suport FIRMs, based on Zone A review criteria- similar floodplain width) and validation map. | O:\WSC\FSCA\Mapping\CTP\Base Level Engineering\Guidance\202107_v6_BLE Submittal Guidance_R6___FINAL.pdf pg 82 | NA | CNMS not included in this submittal, will be validated at a later date | NA | LH | 2023-08-25 | Noted | 2023-08-30 | GM
(L_Source_CIT). Table includes references for all source information used and included in the submittal information. |  | P | If necessary, be sure to update L_Source_Cit after fixing DTL_STUD_LN and DTL_STUD_AR. | NA | LH | 2023-08-30 | Noted | 2023-08-30 | GM