## Instructions
Engineering Files QC Checklists
1 | Please insert Study Name on Sign Off tab. This will automatically populate the remainder of the spreadsheets. Please insert the Feme Case No in front of the document name, and save the file with that name on your network.
2 | Please enter name (and initials) on Sign Off tab. If additional lines are required, copy the last line and insert below. As you complete the spreadsheets, you will need only to insert your initials.
3 | Please enter the name of the basin, stream reach, or coastal beach that you are reviewing in the appropriate space at the top of the sheet. The first of each set of forms requires names and dates to be added at the top of each column.
4 | Technical Review refers to the final review of work. This will be accomplished by an independent team of subject matter experts. Work should be considered as complete and ready to submit when submitted to this team. Be certain to add initials to the form. | Have the flow files for the Pluvial events been assigned correctly?
Are the flow files based on proper naming convention for the event, precipitation source?
5 | QA Verification refers to the determination that the work is ready to deliver. It is accomplished by a representative of the QA Manager. This review is cursory and involves review of records and spot checks of errors that appear to be systemic. The purpose of this review is to first ensure that all errors have been corrected, files are ready to be submitted and all records are ready for archival. Secondly, the review will focus on whether errors are systemic (requiring adjustment to procedure, or perhaps further training) or random (requiring review of schedules, budgets, etc.) Be certain to add initials to the form. | Has the SA/2D flow area been assigned the correct DSS precipitation file from the hydrology folder? Has the appropriate event in the DSS file been selected?
Does the model include all required and scoped events / frequencies?
6 | Should there be a requirement to review data a second (or more) time, simply copy the appropriate columns and insert them to the right of the original review columns.
7 | A separate worksheet may be required for each basin, stream reach or model, and coastal beach. In this case copy the worksheet and insert into the workbook in the proper sequential order. Please label the tab with the basin name, stream reach or model number(s), or beach to make use of the workbook easier.
8 | Please indicate status of each item by responding P (Pass), F (Fail), NA (Not applicable).
9 | When your review is complete and you are satisfied with the quality of the work, please sign a hard copy of the sign off sheet. Please be certain to retain the signed sheet with other project documents and be sure the next reviewer knows where to locate it. QA Verification reviewer, please scan the sign off sheet and add to the document files for the project.

## Sign off-QC Stamp
ATKINS QUALITY REVIEW CHECKLIST SIGN OFF FORM
Study / Stream Name
Deliverable
MIP Case #:
PM:
QC REVIEW ACTIVITY
Ready for QC | *Originator / Date :
2021-10-28
*By signing this you are certifying that you have performed a self check on each FIRM Panel using the checks within this checklist
QC Review | Are the flow files based on proper naming convention for the event, precipitation source?
| Has the SA/2D flow area been assigned the correct DSS precipitation file from the hydrology folder? Has the appropriate event in the DSS file been selected? | 2021-11-01
*By signing this you are certifying that you have performed a QC check on each FIRM Panel using the checks within this checklist
Changes Made | *Originator/ Date : | No changes requested
*By signing this you are certifying that you have corrected each QC citation and not introduced additional errors
QC Verification | *QC Reviewer: | No changes requested.
Date:
*By signing this you are certifying that each QC citation has been resolved
PQM Approval | *QA:
Date:
*By signing this you are certifying that, to the best of your ability, all project requirements have been met and all QC citations were properly resolved.

## Terrain Processing_FT
Terrain Processing
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
TWDB - Southern Beaver |  |  |  |  | Kurt Baron |  | 2023-01-23
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
Hydraulics Terrain Processing
1 | Is the correct unit system being used (i.e. SI vs. U.S. Customary)? Options -> "Unit System (US Customary/SI)…" |  | Pass | Yes. US Customary.
2 | Are the source data documented? |  | Fail | No.
3 | Are the process tiles projection, units, and datum documented? |  | Fail | No.
4 | Are the processed tiles in an appropriate projection? |  | Pass | Yes.
5 | Are the processed tiles in the correction vertical units? Confirm at locations where each data source is used. |  | Pass | Yes.
6 | Are the elevations consistent with known elevation sources such as the World Topographic Base Map? |  | Pass | Yes.
7 | Are the vertical and horizontal distances in the same unit (ft/m)? |  | Pass | Yes.
8 | Do the seamless DEMs use a cell size of 5 feet? |  | Pass | Yes.
9 | Are there significant seams at locations transitions from one data source to another? If so, are they justified? |  | Pass | No.
10 | Are there any discontinuities or gaps observed in the contours? If so, are they justified. |  | Pass | No.
11 | Are there any other comments regarding the terrain? |  | Pass | Any documentation?
Hydroconditioning for Watershed and Streamlines
12 | Were burn lines applied appropriately to simulate the natural flow path through ponds and reservoirs?
13 | Were the burn lines applied appropriately where the top of road is part of the topography?
14 | Is the stream network reasonable compared to the NHD flowlines? Are significant deviations documented and justified?
15 | Are the basin boundaries reasonable compared to the published HUC-8, HUC-10 and/or HUC-12 watershed boundaries? Are significant deviations documented and justified?
16 | Do the computed drainage areas reasonably match published values from gages, FIS reports or other studies?
17 | Are there any other comments regarding the basins or hydrologic network?
Total QC citations for this review |  |  | 2
Percent Passing |  |  | 88.24%
Other Comments

## Terrain Processing_M
Terrain Processing
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
TWDB - Southern Beaver |  |  |  |  | Kurt Baron |  | 2023-01-23
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
Hydraulics Terrain Processing
1 | Is the correct unit system being used (i.e. SI vs. U.S. Customary)? Options -> "Unit System (US Customary/SI)…" |  | Pass | Yes. SI units.
2 | Are the source data documented? |  | Fail | No.
3 | Are the process tiles projection, units, and datum documented? |  | Fail | No.
4 | Are the processed tiles in an appropriate projection? |  | Pass | Yes.
5 | Are the processed tiles in the correction vertical units? Confirm at locations where each data source is used. |  | Pass | Yes.
6 | Are the elevations consistent with known elevation sources such as the World Topographic Base Map? |  | Pass | Yes.
7 | Are the vertical and horizontal distances in the same unit (ft/m)? |  | Pass | Yes.
8 | Do the seamless DEMs use a cell size of 5 feet? |  | Pass | No. 5 meters.
9 | Are there significant seams at locations transitions from one data source to another? If so, are they justified? |  | Pass | No.
10 | Are there any discontinuities or gaps observed in the contours? If so, are they justified. |  | Pass | No.
11 | Are there any other comments regarding the terrain? |  | Pass | Any documentation?
Hydroconditioning for Watershed and Streamlines
12 | Were burn lines applied appropriately to simulate the natural flow path through ponds and reservoirs?
13 | Were the burn lines applied appropriately where the top of road is part of the topography?
14 | Is the stream network reasonable compared to the NHD flowlines? Are significant deviations documented and justified?
15 | Are the basin boundaries reasonable compared to the published HUC-8, HUC-10 and/or HUC-12 watershed boundaries? Are significant deviations documented and justified?
16 | Do the computed drainage areas reasonably match published values from gages, FIS reports or other studies?
17 | Are there any other comments regarding the basins or hydrologic network?
Total QC citations for this review |  |  | 2
Percent Passing |  |  | 88.24%
Other Comments

## Model Geometry
Hydraulics
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
RAS Mapper Setup
1 | Is the model projection correct?
2 | Does the terrain and model projections match
3 | Is the model geometry linked to Terrain, Land Cover, and Infiltration layers
4 | Do the model results show Terrain, Landcover and Infiltration layers linked
2D Mesh
1 | Does the digital terrain model input for the 2D model cover the entire 2D study area?
2 | Is the 2D mesh reasonably sized to limit cell count and obtain reasonable velocities? (Generally 200 ft and refined where needed)
3 | Is the model domain delineated properly to capture all contributing flows through rain-on-grid or external hydrograph?
4 | Are there any 2D mesh errors?
Breaklines
5 | Are breaklines sufficiently detailed to capture features (thalweg, roads, banks, berms, etc.)?
6 | Are breaklines consistent with the terrain data?
7 | Have sufficient offset breaklines been added to assure flow is not being restricted upstream?
8 | Are breaklines added such that the grid is not leaking.
Manning's n
9 | Is the source of the roughness coefficients or criteria for selecting default roughness coefficients documented?
10 | Are channel Manning's n values reasonable? Has 50pct plan been ran to delineated the channel region Polygon override for manning's n Values?
11 | Is the Manning's n dataset associated with the geometry file?
Infiltration Layer
12 | Are Curve Numbers (CN) values reasonable, and sufficiently documented?
13 | Are the Curve Numbers reasonable?
14 | Has the Infiltration Layer been correctly assigned to the geometry
Hydraulics Structures (including dams)
15 | Has a copy of the Terrain layer (Terrain.HydroEnforced) been created ?
16 | Have hydro forcing burn lines been applied at all crossing using the Terrain Channel Modification Tool? Are the bottom width, and max extent widths of each line appropriately estimated to match the current structure size? Changing the side slopes can cause some issues with stability if it is too steep or vertical.
17 | Has the Terrain.HydroEnforced.hdf file been correctly assigned to the geometry?
18 | Does the model account for any significant flow-regulating dams?
19 | Were 2D connections appropriately set-up to model the regulated outflow from the dams?
20 | Are the sources for the dam operations documented?
Other
21 | Are comparison points/lines (i.e., internal 2-D connections) captured and compared against applicable benchmarks? (gage, high water mark, effective BFE, etc.)
22 | If applicable, is the transfer line between this model and a downstream model well away from any boundary condition effects?
23 | Are perimieter boundary conditions applied where flow is leaving the 2D area?
24 | Are boundary coniditions applied such the flow does not build up at the boundary of the 2D mesh?
25 | Are there any other comments related to the model geometry?
Total QC citations for this review |  |  | 0
Percent Passing |  |  | 100%
Other Comments

## Unsteady Flow Data
Hydrology
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
1 | Are the precipitation depths reasonable, and sufficiently documented? Was a reasonable temporal storm distribution used?
2 | Have the flow files for the Pluvial events been assigned correctly ?
3 | Are the flow files based on proper naming convention for the event, precip source ?
4 | Has the SA/2D flow area been assigned the correct DSS precipitation file from the hydrology folder? Has the appropriate event in the DSS file been selected?
5 | Does the model include all required and scoped events / frequencies?
6 | Does model plan and precip have same AEP event. For example, 10% AEP plan use 10% AEP rainfall.
7 | Was the appropriate areal reduction factor used for the 2D mesh?
8 | Are the incoming hydrographs being applied properly? (location, shapes, timing, etc.). Confirm that any incoming hydrographs have the same time and magnitude of peak flow by opening up the upstream RAS models
9 | For hydrographs transferred from one RAS model to a downstream RAS model, are the incoming and outgoing hydrographs being applied at a coincident location?
10 | If using a direct flow transfer from an upstream model, does the time interval for the inflowing hydrograph match the time interval of the extracted hydrograph from the upstream model?
11 | Do all boundary conditions have a hydrograph or elevation/slope data assigned?
12 | Is the downstream boundary condition consistent with ground slope or know downstream WSEL?
13 | Are there any other comments related to the unsteady flow data?
Joint Probability Checks (Receiving Watersheds Only)
14 | Is the joint probability approach being applied to this watershed? If no, no additional checks are needed.
15 | Is this model for a headwater watershed? If so, no additional JP checks are needed.
16 | Are the Inflow Drainage Area and the Total Drainage Area upstream of each confluence correct? Are all areas computed in square miles? | [7 empty] | Screenshot 1 | Screenshot 2
17 | According to the Total Drainage Area (Atot) and the Drainage Area Ratio (RA), has the correct Watershed Category been assigned to each inflow watershed? (e.g., SS, SL, LS, LL - Refer to Screenshot 1) | [8 empty] | FEMA - 2D Watershed Modeling in HEC-RAS Recommended Practices - Appendix B JP Combinations
18 | For each event in the model, has the correct representative JP event been identified for each inflow watershed?
19 | Have the inflow hydrographs from all inflow watersheds been included in the model? Are the hydrographs for the correct representative JP events? (refer to Screenshot 2 )
20 | Has each inflow watershed been assigned its own JP flow and plan file?
21 | Has the JP flow file in RAS for each inflow watershed been created with the proper naming convention? (e.g., NRCS_1.0_PCT_0202_A6_JP)
22 | At each confluence, has each fluvial JP inflow hydrograph been shifted so that the peak of the JP inflow hydrograph is aligned with the peak of the pluvial hydrograph? As part of this check, temporarily disable other inflows so they do not interfere.
23 | Has the upstream watershed(s) offset .DSS file been copied to the hydrology folder for the watershed being modeled?
24 | Has a model/plan matrix been included with the model?
25 | Are there any other comments related to the Joint Probability hydrology?
Total QC citations for this review |  |  | 0
Percent Passing |  |  | 100%
Other Comments

## Model Execution and Results
Hydraulics
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
Model Execution
1 | Is the Diffusion Wave Equation being used?
2 | Is the timestep appropriate for the mesh size and calculated velocities?
3 | Are the Computation Options and Tolerances set to the default values? If no, is it documented and justified?
4 | Are the advanced time step control tab settings selected properly ? Are Variable time step parameters reasonable / Meet project needs ?
5 | Are both the "hydrograph output interval" and "mapping output interval" set at a reasonable interval to capture peak flows within the model?
6 | Are there any other comments related to the HEC-RAS Unsteady Plan settings?
Model Results
7 | Does the model run with no cell errors?
8 | Does the model have acceptable volume conservation (less than 3%)
9 | Is the Courant number generally less than 2 but no greater than 5?
10 | Was the model simulation long enough to pass the entire hydrograph(s) through the model?
11 | Is any flow trapped at the 2D boundary?
12 | Are all water-surface elevation convergence warning messages acceptable per computation tolerances?
13 | Are contributing areas contained within the 2D mesh or accounted for with inflow hydrographs?
14 | Are hydrographs at the internal and external boundary conditions smooth?
15 | Check to make sure the computed maximum depth, WSEL, and velocity values are not from numerical surge (i.e. Beginning of model).
16 | Are the water surface and depth grids reasonable with no artificial dips or spikes?
17 | Is there any ponding behind road embankments? If so, is it reasonable or should the model be modified to allow flow through the embankment?
18 | Do the velocity grids appear reasonable with no unusually high velocity areas?
19 | Have instances of model instabilities at the beginning of the simulation due to initial wetting of a dry grid been addressed? Should a initial condition (wet start) be used?
20 | Are there other comments related to the model results?
Total QC citations for this review |  |  | 0
Percent Passing |  |  | 100%
Other Comments

## Model Validation
Calibration and Validation
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
Validation is Performed for the 100-yr Only
1 | Is the method and parameters adjusted for model validation documented?
2 | Are the modifications to the Curve Number's and/or Manning's n reasonable?
3 | Have representative points in the watershed been used to check pluvial flows to confirm they are within the 1% regression bounds?
4 | Do the peak discharges compare favorably to gages, effective studies, INFRM flows, or other approved benchmarks? If not, have attempts been made to calibrate?
5 | Are there other comments related to model validation?
Joint Probability Checks
6 | Was the JP rainfall adjusted for calibration? If so, is it within the acceptable limits outlined in Appendix B of FEMA's best practices document?
Total QC citations for this review |  |  | 0
Percent Passing |  |  | 100%
Other Comments

## Model Clean-up
Model Clean-up
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
For Submission to Water Board
1 | HEC-RAS Project files: Have all temporary and interim project files been deleted from the model? (*.p##, *.g##, *.u##)
2 | HEC-RAS Output files: Have all unused output files been deleted from the project directory? (*.O##,*.hyd##, *.c##,*.b##, *.bco##, *.g##.hdf, *.p##.hdf, *.p##.blf, *.IC.O##, *.x##)
3 | HEC-RAS DSS Output file: Have any unused model outputs associated with plans no longer in use been deleted from the HEC-DSS Output file?
4 | HEC-RAS DSS Output file: Do hydrographs for all 7 recurrence interval events (10%, 4%, 2%, 1%, 0.2%, and 1% (+/-)) show up under the "Plot Stage and Flow Hydrographs" option within HEC-RAS?
5 | Have all old versions of geometries and plans been removed from the tree list within RAS Mapper?
6 | Have all non-essential shapefiles been removed from RAS Mapper?
7 | Is there a projection defined within RAS Mapper and is it correct?
8 | Are the terrain and land cover files correctly associated with the geometry and results layers?
9 | Have all folders and/or files that are not necessary for viewing results been deleted from the project folder (i.e. shapefiles, Excel documents, etc.)?
10 | Have all old and non-relevant comments within each unsteady flow plan been removed?
11 | Can the "computation log file" and "runtime messages" be seen for each plan?
Total QC citations for this review |  |  | 0
Percent Passing |  |  | 100%
Other Comments

## Sheet1
General
Hydraulics
Mapping Outputs
Do the boundaries look reasonable?
Are the WSELs for each return period in the correct order?
i.e. 0.2% > 1% > 2% > 4% > 10%
-If there are inflow hydrographs, check at least one cell in each main channel and check at least one location with flooding that is driven purely by precipitation
-Use the automated tool to check 500+ points within the fluvial- and pluvial-controlled flooding areas to confirm that WSELs increase for higher return period events.
Model Clean-up / File Management
HEC-RAS Project files: Have all temporary and interim project files been deleted from the model? (*.p##, *.g##, *.u##)
HEC-RAS Output files: Have all unused output files been deleted from the project directory? (*.O##,*.hyd##, *.c##,*.b##, *.bco##, *.g##.hdf, *.p##.hdf, *.p##.blf, *.IC.O##, *.x##)
HEC-RAS DSS Output file: Have any unused model outputs associated with plans no longer in use been deleted from the HEC-DSS Output file?
HEC-RAS DSS Output file: Do hydrographs for all 7 recurrence interval events (10%, 4%, 2%, 1%, 0.2%, and 1% (+/-)) show up under the "Plot Stage and Flow Hydrographs" option within HEC-RAS?
Have all old versions of geometries and plans been removed from the tree list within RAS Mapper?
Have all non-essential shapefiles been removed from RAS Mapper?
Is there a projection defined within RAS Mapper and is it correct?
Are the terrain and land cover files correctly associated with the geometry and results layers?
Have all folders and/or files that are not necessary for viewing results been deleted from the project folder (i.e. shapefiles, Excel documents, etc.)?
Have all old and non-relevant comments within each unsteady flow plan been removed?
Can the "computation log file" and "runtime messages" be seen for each plan?
Calibration and Validation
Is Rainfall Calibarion within -1% and +1% error? The error range is based on a second order polynomial relationship between CN and outflow.We want to keep the main DS outflow between the 1% and 1%+ range as typically this will result in the upstream most portions of the watershed being between the 1%- and 1%
Does the peak discharge compare favorably to gages, effective studies, regional regression studies, or other approved benchmark? If not, have attempts been made to calibrate? (This applies to both the study area and incoming hydrograph models.)
Where applicable, have USGS gage rating curve(s) been used to verify model results?
Have representative points in the watershed been used to check pluvia flows and stages to confirm they are within the 1pct regression bounds?
Have JP events been checked if they are within 1pct regression bounds as well ?
Additional Comments
Engineering analyses are documented and easily reproducible and include study methods, reasoning for method selection, input data and parameters, sources of data results, and justifications for major changes in computed flood hazard parameters.
Model, plans, flows, geometry, etc. names are correct
- 1PAC, 1PACPlus, etc.