## Sign off-QC Stamp
ATKINS QUALITY REVIEW CHECKLIST SIGN OFF FORM
Study / Stream Name | 11130209 Little Wichita Watershed
Deliverable | Base Level Engineering Dataset
MIP Case #: | 22-06-0047S
PM: | Seth Ahrens
QC REVIEW ACTIVITY
Ready for QC | *Originator / Date : | Iqra Shafi
2024-June-28
QC Review | *Reviewer / Date : | Michael R. Wilson, MS, CFM
2024-July-02; 2024-July-10
Changes Made | *Originator/ Date :
QC Verification | *QC Reviewer:
Date:
PQM Approval | *QA:
Date:

## Attribute Checks v1
Study |  |  | 11130209 Little Wichita Watershed
Reviewer |  |  | Michael R. Wilson, MS, CFM
Review Date |  |  | 2024-July-02
Spatial Analyst |  |  | Iqra Shafi
Response Date |  |  | 05 July 2024
Line No. | Feature Dataset | Feature Class | Field | Field Type¹ | Pass/ Fail | Reviewer Comment | Response Comment
1 | BASE_DATASET | S_POL_AR | DFIRM_ID |  | Pass
2 |  |  | VERSION_ID |  | Pass
3 |  |  | POL_AR_ID |  | Pass
4 |  |  | POL_NAME1 |  | Pass
5 |  |  | POL_NAME2 |  | Pass
6 |  |  | POL_NAME3 |  | Pass
7 |  |  | CO_FIPS |  | Pass
8 |  |  | ST_FIPS |  | Pass
9 |  |  | COMM_NO |  | Pass
10 |  |  | CID |  | Pass
11 |  |  | ANI_TF |  | Fail | This field should be "False (No)" for all records. | Changed to "False"
12 |  |  | ANI_FIRM |  | Pass
13 |  |  | COM_NFO_ID |  | Pass
14 |  |  | SOURCE_CIT |  | Pass
15 |  | S_HUC_AR | HUC_CODE |  | Pass
16 |  |  | HUC_NAME |  | Pass
17 |  |  | DIGITS |  | Pass
18 |  |  | CASE_NO |  | Pass
19 |  |  | VERSION_ID |  | Pass
20 |  |  | SOURCE_CIT |  | Pass
21 | EBFE_DATASET | SUBBASINS | EST_ID |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
22 |  |  | VERSION_ID |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
23 |  |  | E_SUBAS_ID |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
24 |  |  | E_SUBAS_NM |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
25 |  |  | HUC8_CODE |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
26 |  |  | WTR_NM | Hidden | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
27 |  |  | BASIN_DESC | Hidden | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
28 |  |  | EST_AREA |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
29 |  |  | AREA_UNIT |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
30 |  |  | NODE_ID | Hidden | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
31 |  |  | BASIN_TYP | Hidden | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
32 |  |  | SOURCE_CIT |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
33 |  |  | US_1 | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
34 |  |  | US_2 | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
35 |  |  | US_3 | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
36 |  |  | US_4 | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
37 |  |  | DS_1 | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
38 |  |  | PRECIP_IN | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
39 |  |  | MAINCHSLP | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
40 |  |  | E_Q_10PCT | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
41 |  |  | E_Q_04PCT | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
42 |  |  | E_Q_02PCT | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
43 |  |  | E_Q_01PCT | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
44 |  |  | E_Q_01PLUS | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
45 |  |  | E_Q_01MIN | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
46 |  |  | E_Q_0_2PCT | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
47 |  | XS_1D | EST_ID |  | N/A | Not submitted - XS are not required for 2D modeling areas.
48 |  |  | VERSION_ID |  | N/A | Not submitted - XS are not required for 2D modeling areas.
49 |  |  | XS_LN_ID |  | N/A | Not submitted - XS are not required for 2D modeling areas.
50 |  |  | WTR_NM |  | N/A | Not submitted - XS are not required for 2D modeling areas.
51 |  |  | STREAM_STN |  | N/A | Not submitted - XS are not required for 2D modeling areas.
52 |  |  | START_ID |  | N/A | Not submitted - XS are not required for 2D modeling areas.
53 |  |  | XS_LTR | Hidden | N/A | Not submitted - XS are not required for 2D modeling areas.
54 |  |  | XS_LN_TYP |  | N/A | Not submitted - XS are not required for 2D modeling areas.
55 |  |  | E_WSE_1PCT |  | N/A | Not submitted - XS are not required for 2D modeling areas.
56 |  |  | STRMBED_EL | Hidden | N/A | Not submitted - XS are not required for 2D modeling areas.
57 |  |  | LEN_UNIT | Hidden | N/A | Not submitted - XS are not required for 2D modeling areas.
58 |  |  | V_DATUM |  | N/A | Not submitted - XS are not required for 2D modeling areas.
59 |  |  | PROFXS_TXT |  | N/A | Not submitted - XS are not required for 2D modeling areas.
60 |  |  | MODEL_ID |  | N/A | Not submitted - XS are not required for 2D modeling areas.
61 |  |  | SEQ |  | N/A | Not submitted - XS are not required for 2D modeling areas.
62 |  |  | SOURCE_CIT |  | N/A | Not submitted - XS are not required for 2D modeling areas.
63 |  |  | E_WSE_10PC | New | N/A | Not submitted - XS are not required for 2D modeling areas.
64 |  |  | E_WSE_4PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
65 |  |  | E_WSE_2PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
66 |  |  | E_WSE_1PLU | New | N/A | Not submitted - XS are not required for 2D modeling areas.
67 |  |  | E_WSE_1MIN | New | N/A | Not submitted - XS are not required for 2D modeling areas.
68 |  |  | E_WSE_0_2P | New | N/A | Not submitted - XS are not required for 2D modeling areas.
69 |  |  | E_Q_10PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
70 |  |  | E_Q_04PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
71 |  |  | E_Q_02PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
72 |  |  | E_1_02PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
73 |  |  | E_Q_01PLUS | New | N/A | Not submitted - XS are not required for 2D modeling areas.
74 |  |  | E_Q_01MIN | New | N/A | Not submitted - XS are not required for 2D modeling areas.
75 |  |  | E_Q_0_2PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
76 |  | BFE_2D | EST_ID |  |  | Data not provided, please include these features in the next submittal. | Done
77 |  |  | VERSION_ID |  |  | Data not provided, please include these features in the next submittal. | Done
78 |  |  | EBFE_LN_ID |  |  | Data not provided, please include these features in the next submittal. | Done
79 |  |  | BLELEV1PCT |  |  | Data not provided, please include these features in the next submittal.
80 |  |  | LEN_UNIT |  |  | Data not provided, please include these features in the next submittal. | Done
81 |  |  | V_DATUM |  |  | Data not provided, please include these features in the next submittal. | Done
82 |  |  | SOURCE_CIT |  |  | Data not provided, please include these features in the next submittal. | Done
83 |  |  | BFE_LN_TYP | New |  | Data not provided, please include these features in the next submittal. | Done
84 |  | WTR_LN | EST_ID |  | Pass
85 |  |  | VERSION_ID |  | Pass
86 |  |  | WTR_LN_ID |  | Pass
87 |  |  | WTR_NM |  | Fail | Data is not populated; refer to replacement database and supplemental information to resolve the problem you encountered. | Done
88 |  |  | SHOWN_FIRM | Hidden | Pass
89 |  |  | SHOWN_INDX | Hidden | Pass
90 |  |  | SOURCE_CIT |  | Pass
91 |  | WTR_AR | EST_ID |  | Pass
92 |  |  | VERSION_ID |  | Pass
93 |  |  | WTR_AR_ID |  | Pass
94 |  |  | WTR_NM |  | Pass
95 |  |  | SHOWN_FIRM | Hidden | Fail | This field should be "Unknown" for all records. | Changed to "Unknown"
96 |  |  | SHOWN_INDX | Hidden | Fail | This field should be "Unknown" for all records. | Changed to "Unknown"
97 |  |  | SOURCE_CIT |  | Pass
98 |  | DTL_STUD_LN | DTL_LN_ID |  | Pass
99 |  |  | VERSION_ID |  | Pass
100 |  |  | LOMR_ID | Hidden | Pass
101 |  |  | EFF_DATE |  | Pass
102 |  |  | CASE_NO | Hidden | Pass
103 |  |  | SCALE | Hidden | Fail | Please populate this field; see the supplemental information for instructions on how to determine the value.
104 |  |  | SOURCE_CIT |  | Pass
105 |  |  | STATUS | Hidden | Pass
106 |  |  | FIRM_PAN | New | Pass
107 |  |  | TYPE | New | Pass
108 |  |  | CD_YN | New | Pass
109 |  |  | CD_POC | New | Pass
110 |  |  | CD_ADD1 | New | Pass
111 |  |  | CD_ADD2 | New | Pass
112 |  |  | CD_CTY | New | Pass
113 |  |  | CD_STATE | New | Pass
114 |  |  | CD_ZIP | New | Pass
115 |  |  | CD_PHONE | New | Pass
116 |  |  | CD_EMAIL | New | Pass
117 |  | DTL_STUD_AR | DTL_AR_ID |  |  | Data not provided, please include these features in the next submittal. | Done
118 |  |  | VERSION_ID |  |  | Data not provided, please include these features in the next submittal. | Done
119 |  |  | LOMR_ID | Hidden |  | Data not provided, please include these features in the next submittal. | Done
120 |  |  | EFF_DATE |  |  | Data not provided, please include these features in the next submittal. | Done
121 |  |  | CASE_NO | Hidden |  | Data not provided, please include these features in the next submittal. | Done
122 |  |  | SCALE | Hidden |  | Data not provided, please include these features in the next submittal.
123 |  |  | SOURCE_CIT |  |  | Data not provided, please include these features in the next submittal. | Done
124 |  |  | STATUS | Hidden |  | Data not provided, please include these features in the next submittal. | Done
125 |  |  | FIRM_PAN | New |  | Data not provided, please include these features in the next submittal. | Done
126 |  |  | TYPE | New |  | Data not provided, please include these features in the next submittal. | Done
127 |  |  | CD_YN | New |  | Data not provided, please include these features in the next submittal. | Done
128 |  |  | CD_POC | New |  | Data not provided, please include these features in the next submittal. | Done
129 |  |  | CD_ADD1 | New |  | Data not provided, please include these features in the next submittal. | Done
130 |  |  | CD_ADD2 | New |  | Data not provided, please include these features in the next submittal. | Done
131 |  |  | CD_CTY | New |  | Data not provided, please include these features in the next submittal. | Done
132 |  |  | CD_STATE | New |  | Data not provided, please include these features in the next submittal. | Done
133 |  |  | CD_ZIP | New |  | Data not provided, please include these features in the next submittal. | Done
134 |  |  | CD_PHONE | New |  | Data not provided, please include these features in the next submittal. | Done
135 |  |  | CD_EMAIL | New |  | Data not provided, please include these features in the next submittal. | Done
136 |  | FLD_HAZ_AR | EST_ID |  | Pass
137 |  |  | VERSION_ID |  | Pass
138 |  |  | EST_AR_ID |  | Pass
139 |  |  | STUDY_TYP | Hidden | Pass
140 |  |  | FLD_ZONE | Hidden | Pass
141 |  |  | ZONE_SUBTY |  | Pass
142 |  |  | SFHA_TF | Hidden | Pass
143 |  |  | STATIC_BFE | Hidden | Pass
144 |  |  | V_DATUM |  | Pass
145 |  |  | DEPTH | Hidden | Pass
146 |  |  | LEN_UNIT |  | Pass
147 |  |  | VELOCITY | Hidden | Pass
148 |  |  | VEL_UNIT | Hidden | Pass
149 |  |  | AR_REVERT | Hidden | Pass
150 |  |  | AR_SUBTRV | Hidden | Pass
151 |  |  | BFE_REVERT | Hidden | Pass
152 |  |  | DEP_REVERT | Hidden | Pass
153 |  |  | DUAL_ZONE | Hidden | Pass
154 |  |  | SOURCE_CIT |  | Pass
155 |  |  | EST_RISK | New | Pass
156 |  | TENPCT_FP | EST_ID |  | Pass
157 |  |  | VERSION_ID |  | Pass
158 |  |  | EST_AR_ID |  | Pass
159 |  |  | STUDY_TYP | Hidden | Pass
160 |  |  | FLD_ZONE | Hidden | Pass
161 |  |  | ZONE_SUBTY |  | Pass
162 |  |  | SFHA_TF | Hidden | Pass
163 |  |  | STATIC_BFE | Hidden | Pass
164 |  |  | V_DATUM |  | Pass
165 |  |  | DEPTH | Hidden | Pass
166 |  |  | LEN_UNIT |  | Pass
167 |  |  | VELOCITY | Hidden | Pass
168 |  |  | VEL_UNIT | Hidden | Pass
169 |  |  | AR_REVERT | Hidden | Pass
170 |  |  | AR_SUBTRV | Hidden | Pass
171 |  |  | BFE_REVERT | Hidden | Pass
172 |  |  | DEP_REVERT | Hidden | Pass
173 |  |  | DUAL_ZONE | Hidden | Pass
174 |  |  | SOURCE_CIT |  | Pass
175 |  |  | EST_RISK | New | Pass
176 | MIT-HAZ_DATASETS | S_AOMI_AR | AOMI_ID |  | Fail | Not all records are populated; values are not consecutive from 001 through 624. | Populated according to comment
177 |  |  | CID |  | Fail | Not all records are populated. | Populated according to comment
178 |  |  | POL_NAME1 |  | Fail | Not all records are populated. | Populated according to comment
179 |  |  | AOMI_CLASS |  | Fail | Not all records are populated. | Populated according to comment
180 |  |  | AOMI_TYP |  | Fail | Not all records are populated. | Populated according to comment
181 |  |  | AOMI_INFO |  | Pass
182 |  |  | HUC8_CODE |  | Fail | Not all records are populated. | Populated according to comment
183 |  |  | CASE_NO |  | Pass
184 |  |  | VERSION_ID |  | Pass
185 |  |  | SOURCE_CIT |  | Pass
186 |  | S_FRAC_AR | CEN_BLK_ID |  | Pass
187 |  |  | ARV_BG_TOT |  | Pass
188 |  |  | ARV_CN_TOT |  | Pass
189 |  |  | HAZARD_TYP | Hidden | Pass
190 |  |  | SCENAR_ID | Hidden | Pass
191 |  |  | TOT_LOSS10 | Hidden | Pass
192 |  |  | BL_TOT10 | Hidden | Pass
193 |  |  | CL_TOT10 | Hidden | Pass
194 |  |  | TOT_LOSS04 | Hidden | Pass
195 |  |  | BL_TOT04 | Hidden | Pass
196 |  |  | CL_TOT04 | Hidden | Pass
197 |  |  | TOT_LOSS02 | Hidden | Pass
198 |  |  | BL_TOT02 | Hidden | Pass
199 |  |  | CL_TOT02 | Hidden | Pass
200 |  |  | TOT_LOSS01 |  | Pass
201 |  |  | BL_TOT01 |  | Pass
202 |  |  | CL_TOT01 |  | Pass
203 |  |  | TOT_LSS0_2 | Hidden | Pass
204 |  |  | BL_TOT0_2 | Hidden | Pass
205 |  |  | CL_TOT0_2 | Hidden | Pass
206 |  |  | TOT_LSSAAL | Hidden | Pass
207 |  |  | BL_TOTAAL | Hidden | Pass
208 |  |  | CL_TOTAAL | Hidden | Pass
209 |  |  | HUC8_CODE |  | Pass
210 |  |  | CASE_NO |  | Pass
211 |  |  | VERSION_ID |  | Pass
212 |  |  | SOURCE_CIT |  | Pass
213 |  | S_FRAS_PT | FRAS_ID |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
214 |  |  | CEN_BLK_ID |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
215 |  |  | HAZARD_TYP |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
216 |  |  | OCCUP_TYP |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
217 |  |  | ARV_BG |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
218 |  |  | SCENAR_ID |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
219 |  |  | ARV_CN |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
220 |  |  | BLD_LOSS10 |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
221 |  |  | CNT_LOSS10 |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
222 |  |  | INV_LOSS10 |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
223 |  |  | BLD_LOSS04 |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
224 |  |  | CNT_LOSS04 |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
225 |  |  | INV_LOSS04 |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
226 |  |  | BLD_LOSS02 |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
227 |  |  | CN_LOSS02 |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
228 |  |  | INV_LOSS02 |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
229 |  |  | BLD_LOSS01 |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
230 |  |  | CNT_LOSS01 |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
231 |  |  | INV_LOSS01 |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
232 |  |  | BLD_LOSS0_2 |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
233 |  |  | CNT_LOSS0_2 |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
234 |  |  | INV_LOSS0_2 |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
235 |  |  | BLD_LSSAAL |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
236 |  |  | INV_LSSAAL |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
237 |  |  | CNT_LSSAAL |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
238 |  |  | HUC8_CODE |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
239 |  |  | CASE_NO |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
240 |  |  | VERSION_ID |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
241 |  |  | SOURCE_CIT |  |  | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No Data in old gdb
242 | CNMS_ DATASET | S_STUDIES_LN |  |  | N/A | Not included in project scope.
243 |  | S_UNMAPPED_LN |  |  | N/A | Not included in project scope.
244 | GRIDS | BLE_WSE01PCT |  |  |  | Data not provided, please include these features in the next submittal. | Provided
245 |  | BLE_WSE0_2PCT |  |  |  | Data not provided, please include these features in the next submittal. | Provided
246 |  | BLE_DEP01PCT |  |  |  | Data not provided, please include these features in the next submittal. | Provided
247 |  | BLE_DEP0_2PCT |  |  |  | Data not provided, please include these features in the next submittal. | Provided
248 | L_SOURCE_CIT | SOURCE_CIT |  |  | Pass
249 |  | DFIRM_ID |  |  | Pass
250 |  | CITATION |  |  | Pass
251 |  | PUBLISHER |  |  | Pass
252 |  | TITLE |  |  | Pass
253 |  | AUTHOR |  |  | Pass
254 |  | PUB_PLACE |  |  | Pass
255 |  | PUB_DATE |  |  | Pass
256 |  | WEBLINK |  |  | Pass
257 |  | SRC_SCALE |  |  | Pass
258 |  | MEDIA |  |  | Pass
259 |  | CASE_NO |  |  | Pass
260 |  | VERSION_ID |  |  | Pass
¹ | "Hidden" fields are those not visible to the public in the Region 6 viewer at https://webapps.usgs.gov/infrm/estbfe/.
"New" fields are created for the BLE database and are not described in the Technical References. Refer to the Base Level Engineering, Region 6 Submittal Guidance instead.

## Attribute Checks v2
Study |  |  | 11130209 Little Wichita Watershed
Reviewer |  |  | Michael R. Wilson, MS, CFM
Review Date |  |  | 2024-July-10
Spatial Analyst |  |  | Iqra Shafi
Response Date
Line No. | Feature Dataset | Feature Class | Field | Field Type¹ | Pass/ Fail | Reviewer Comment | Response Comment
1 | BASE_DATASET | S_POL_AR | DFIRM_ID |  | Pass
2 |  |  | VERSION_ID |  | Pass
3 |  |  | POL_AR_ID |  | Pass
4 |  |  | POL_NAME1 |  | Pass
5 |  |  | POL_NAME2 |  | Pass
6 |  |  | POL_NAME3 |  | Pass
7 |  |  | CO_FIPS |  | Pass
8 |  |  | ST_FIPS |  | Pass
9 |  |  | COMM_NO |  | Pass
10 |  |  | CID |  | Pass
11 |  |  | ANI_TF |  | Pass
12 |  |  | ANI_FIRM |  | Pass
13 |  |  | COM_NFO_ID |  | Pass
14 |  |  | SOURCE_CIT |  | Pass
15 |  | S_HUC_AR | HUC_CODE |  | Pass
16 |  |  | HUC_NAME |  | Pass
17 |  |  | DIGITS |  | Pass
18 |  |  | CASE_NO |  | Pass
19 |  |  | VERSION_ID |  | Pass
20 |  |  | SOURCE_CIT |  | Pass
21 | EBFE_DATASET | SUBBASINS | EST_ID |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
22 |  |  | VERSION_ID |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
23 |  |  | E_SUBAS_ID |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
24 |  |  | E_SUBAS_NM |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
25 |  |  | HUC8_CODE |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
26 |  |  | WTR_NM | Hidden | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
27 |  |  | BASIN_DESC | Hidden | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
28 |  |  | EST_AREA |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
29 |  |  | AREA_UNIT |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
30 |  |  | NODE_ID | Hidden | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
31 |  |  | BASIN_TYP | Hidden | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
32 |  |  | SOURCE_CIT |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
33 |  |  | US_1 | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
34 |  |  | US_2 | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
35 |  |  | US_3 | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
36 |  |  | US_4 | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
37 |  |  | DS_1 | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
38 |  |  | PRECIP_IN | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
39 |  |  | MAINCHSLP | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
40 |  |  | E_Q_10PCT | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
41 |  |  | E_Q_04PCT | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
42 |  |  | E_Q_02PCT | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
43 |  |  | E_Q_01PCT | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
44 |  |  | E_Q_01PLUS | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
45 |  |  | E_Q_01MIN | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
46 |  |  | E_Q_0_2PCT | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
47 |  | XS_1D | EST_ID |  | N/A | Not submitted - XS are not required for 2D modeling areas.
48 |  |  | VERSION_ID |  | N/A | Not submitted - XS are not required for 2D modeling areas.
49 |  |  | XS_LN_ID |  | N/A | Not submitted - XS are not required for 2D modeling areas.
50 |  |  | WTR_NM |  | N/A | Not submitted - XS are not required for 2D modeling areas.
51 |  |  | STREAM_STN |  | N/A | Not submitted - XS are not required for 2D modeling areas.
52 |  |  | START_ID |  | N/A | Not submitted - XS are not required for 2D modeling areas.
53 |  |  | XS_LTR | Hidden | N/A | Not submitted - XS are not required for 2D modeling areas.
54 |  |  | XS_LN_TYP |  | N/A | Not submitted - XS are not required for 2D modeling areas.
55 |  |  | E_WSE_1PCT |  | N/A | Not submitted - XS are not required for 2D modeling areas.
56 |  |  | STRMBED_EL | Hidden | N/A | Not submitted - XS are not required for 2D modeling areas.
57 |  |  | LEN_UNIT | Hidden | N/A | Not submitted - XS are not required for 2D modeling areas.
58 |  |  | V_DATUM |  | N/A | Not submitted - XS are not required for 2D modeling areas.
59 |  |  | PROFXS_TXT |  | N/A | Not submitted - XS are not required for 2D modeling areas.
60 |  |  | MODEL_ID |  | N/A | Not submitted - XS are not required for 2D modeling areas.
61 |  |  | SEQ |  | N/A | Not submitted - XS are not required for 2D modeling areas.
62 |  |  | SOURCE_CIT |  | N/A | Not submitted - XS are not required for 2D modeling areas.
63 |  |  | E_WSE_10PC | New | N/A | Not submitted - XS are not required for 2D modeling areas.
64 |  |  | E_WSE_4PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
65 |  |  | E_WSE_2PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
66 |  |  | E_WSE_1PLU | New | N/A | Not submitted - XS are not required for 2D modeling areas.
67 |  |  | E_WSE_1MIN | New | N/A | Not submitted - XS are not required for 2D modeling areas.
68 |  |  | E_WSE_0_2P | New | N/A | Not submitted - XS are not required for 2D modeling areas.
69 |  |  | E_Q_10PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
70 |  |  | E_Q_04PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
71 |  |  | E_Q_02PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
72 |  |  | E_1_02PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
73 |  |  | E_Q_01PLUS | New | N/A | Not submitted - XS are not required for 2D modeling areas.
74 |  |  | E_Q_01MIN | New | N/A | Not submitted - XS are not required for 2D modeling areas.
75 |  |  | E_Q_0_2PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
76 |  | BFE_2D | EST_ID |  | Pass
77 |  |  | VERSION_ID |  | Pass
78 |  |  | EBFE_LN_ID |  | Pass
79 |  |  | BLELEV1PCT |  | Pass
80 |  |  | LEN_UNIT |  | Pass
81 |  |  | V_DATUM |  | Pass
82 |  |  | SOURCE_CIT |  | Pass
83 |  |  | BFE_LN_TYP | New | Pass
84 |  | WTR_LN | EST_ID |  | Fail | This should be "11130209_BLE". | Corrected
85 |  |  | VERSION_ID |  | Pass
86 |  |  | WTR_LN_ID |  | Pass
87 |  |  | WTR_NM |  | Fail | Please re-check water names. There are no names present that come alphabetically later than "NP".
88 |  |  | SHOWN_FIRM | Hidden | Pass
89 |  |  | SHOWN_INDX | Hidden | Pass
90 |  |  | SOURCE_CIT |  | Pass
91 |  | WTR_AR | EST_ID |  | Pass
92 |  |  | VERSION_ID |  | Pass
93 |  |  | WTR_AR_ID |  | Pass
94 |  |  | WTR_NM |  | Pass
95 |  |  | SHOWN_FIRM | Hidden | Pass
96 |  |  | SHOWN_INDX | Hidden | Pass
97 |  |  | SOURCE_CIT |  | Pass
98 |  | DTL_STUD_LN | DTL_LN_ID |  | Fail | This should be "11130209_BLE". | Corrected
99 |  |  | VERSION_ID |  | Pass
100 |  |  | LOMR_ID | Hidden | Pass
101 |  |  | EFF_DATE |  | Pass
102 |  |  | CASE_NO | Hidden | Pass
103 |  |  | SCALE | Hidden | Fail | Panels 48077C0150D and 48077C0225D should be "24000". | Corrected
104 |  |  | SOURCE_CIT |  | Pass
105 |  |  | STATUS | Hidden | Pass
106 |  |  | FIRM_PAN | New | Pass
107 |  |  | TYPE | New | Pass
108 |  |  | CD_YN | New | Pass
109 |  |  | CD_POC | New | Pass
110 |  |  | CD_ADD1 | New | Pass
111 |  |  | CD_ADD2 | New | Pass
112 |  |  | CD_CTY | New | Pass
113 |  |  | CD_STATE | New | Pass
114 |  |  | CD_ZIP | New | Pass
115 |  |  | CD_PHONE | New | Pass
116 |  |  | CD_EMAIL | New | Pass
117 |  | DTL_STUD_AR | DTL_AR_ID |  |  | Not fully reviewed. There are 39 records in the attribute table that appear to belong to another feature class, perhaps | Corrected
118 |  |  | VERSION_ID |  |  | S_AOMI_Ar. Detailed study on panel 48077C0154D does not appear to have been captured. Please review SCALE values; these
119 |  |  | LOMR_ID | Hidden |  | can be determined from the panel numbers if you don't have access to the actual FIRM panels.
120 |  |  | EFF_DATE |  |  | ¦
121 |  |  | CASE_NO | Hidden |  | ¦
122 |  |  | SCALE | Hidden |  | ¦
123 |  |  | SOURCE_CIT |  |  | ¦
124 |  |  | STATUS | Hidden |  | ¦
125 |  |  | FIRM_PAN | New |  | ¦
126 |  |  | TYPE | New |  | ¦
127 |  |  | CD_YN | New |  | ¦
128 |  |  | CD_POC | New |  | ¦
129 |  |  | CD_ADD1 | New |  | ¦
130 |  |  | CD_ADD2 | New |  | ¦
131 |  |  | CD_CTY | New |  | ¦
132 |  |  | CD_STATE | New |  | ¦
133 |  |  | CD_ZIP | New |  | ¦
134 |  |  | CD_PHONE | New |  | ¦
135 |  |  | CD_EMAIL | New |  | V
136 |  | FLD_HAZ_AR | EST_ID |  | Fail | This should be "11130209_BLE". | Corrected
137 |  |  | VERSION_ID |  | Pass
138 |  |  | EST_AR_ID |  | Pass
139 |  |  | STUDY_TYP | Hidden | Pass
140 |  |  | FLD_ZONE | Hidden | Pass
141 |  |  | ZONE_SUBTY |  | Pass
142 |  |  | SFHA_TF | Hidden | Pass
143 |  |  | STATIC_BFE | Hidden | Pass
144 |  |  | V_DATUM |  | Pass
145 |  |  | DEPTH | Hidden | Pass
146 |  |  | LEN_UNIT |  | Pass
147 |  |  | VELOCITY | Hidden | Pass
148 |  |  | VEL_UNIT | Hidden | Pass
149 |  |  | AR_REVERT | Hidden | Pass
150 |  |  | AR_SUBTRV | Hidden | Pass
151 |  |  | BFE_REVERT | Hidden | Pass
152 |  |  | DEP_REVERT | Hidden | Pass
153 |  |  | DUAL_ZONE | Hidden | Pass
154 |  |  | SOURCE_CIT |  | Pass
155 |  |  | EST_RISK | New | Pass
156 |  | TENPCT_FP | EST_ID |  | Fail | This should be "11130209_BLE". | Corrected
157 |  |  | VERSION_ID |  | Pass
158 |  |  | EST_AR_ID |  | Pass
159 |  |  | STUDY_TYP | Hidden | Pass
160 |  |  | FLD_ZONE | Hidden | Pass
161 |  |  | ZONE_SUBTY |  | Pass
162 |  |  | SFHA_TF | Hidden | Pass
163 |  |  | STATIC_BFE | Hidden | Pass
164 |  |  | V_DATUM |  | Pass
165 |  |  | DEPTH | Hidden | Pass
166 |  |  | LEN_UNIT |  | Pass
167 |  |  | VELOCITY | Hidden | Pass
168 |  |  | VEL_UNIT | Hidden | Pass
169 |  |  | AR_REVERT | Hidden | Pass
170 |  |  | AR_SUBTRV | Hidden | Pass
171 |  |  | BFE_REVERT | Hidden | Pass
172 |  |  | DEP_REVERT | Hidden | Pass
173 |  |  | DUAL_ZONE | Hidden | Pass
174 |  |  | SOURCE_CIT |  | Pass
175 |  |  | EST_RISK | New | Pass
176 | MIT-HAZ_DATASETS | S_AOMI_AR | AOMI_ID |  | Pass
177 |  |  | CID |  | Pass
178 |  |  | POL_NAME1 |  | Fail | For areas outside cities (county areas) these need to include "Unincorporated Areas" (example: "Clay County" should be "Clay County Unincorporated Areas.") | Corrected
179 |  |  | AOMI_CLASS |  | Pass
180 |  |  | AOMI_TYP |  | Pass
181 |  |  | AOMI_INFO |  | Pass
182 |  |  | HUC8_CODE |  | Pass
183 |  |  | CASE_NO |  | Pass
184 |  |  | VERSION_ID |  | Pass
185 |  |  | SOURCE_CIT |  | Pass
186 |  | S_FRAC_AR | CEN_BLK_ID |  | Pass
187 |  |  | ARV_BG_TOT |  | Pass
188 |  |  | ARV_CN_TOT |  | Pass
189 |  |  | HAZARD_TYP | Hidden | Pass
190 |  |  | SCENAR_ID | Hidden | Pass
191 |  |  | TOT_LOSS10 | Hidden | Pass
192 |  |  | BL_TOT10 | Hidden | Pass
193 |  |  | CL_TOT10 | Hidden | Pass
194 |  |  | TOT_LOSS04 | Hidden | Pass
195 |  |  | BL_TOT04 | Hidden | Pass
196 |  |  | CL_TOT04 | Hidden | Pass
197 |  |  | TOT_LOSS02 | Hidden | Pass
198 |  |  | BL_TOT02 | Hidden | Pass
199 |  |  | CL_TOT02 | Hidden | Pass
200 |  |  | TOT_LOSS01 |  | Pass
201 |  |  | BL_TOT01 |  | Pass
202 |  |  | CL_TOT01 |  | Pass
203 |  |  | TOT_LSS0_2 | Hidden | Pass
204 |  |  | BL_TOT0_2 | Hidden | Pass
205 |  |  | CL_TOT0_2 | Hidden | Pass
206 |  |  | TOT_LSSAAL | Hidden | Pass
207 |  |  | BL_TOTAAL | Hidden | Pass
208 |  |  | CL_TOTAAL | Hidden | Pass
209 |  |  | HUC8_CODE |  | Pass
210 |  |  | CASE_NO |  | Pass
211 |  |  | VERSION_ID |  | Pass
212 |  |  | SOURCE_CIT |  | Pass
213 |  | S_FRAS_PT | FRAS_ID |  | N/A | Not included in project scope.
214 |  |  | CEN_BLK_ID |  | N/A | Not included in project scope.
215 |  |  | HAZARD_TYP |  | N/A | Not included in project scope.
216 |  |  | OCCUP_TYP |  | N/A | Not included in project scope.
217 |  |  | ARV_BG |  | N/A | Not included in project scope.
218 |  |  | SCENAR_ID |  | N/A | Not included in project scope.
219 |  |  | ARV_CN |  | N/A | Not included in project scope.
220 |  |  | BLD_LOSS10 |  | N/A | Not included in project scope.
221 |  |  | CNT_LOSS10 |  | N/A | Not included in project scope.
222 |  |  | INV_LOSS10 |  | N/A | Not included in project scope.
223 |  |  | BLD_LOSS04 |  | N/A | Not included in project scope.
224 |  |  | CNT_LOSS04 |  | N/A | Not included in project scope.
225 |  |  | INV_LOSS04 |  | N/A | Not included in project scope.
226 |  |  | BLD_LOSS02 |  | N/A | Not included in project scope.
227 |  |  | CN_LOSS02 |  | N/A | Not included in project scope.
228 |  |  | INV_LOSS02 |  | N/A | Not included in project scope.
229 |  |  | BLD_LOSS01 |  | N/A | Not included in project scope.
230 |  |  | CNT_LOSS01 |  | N/A | Not included in project scope.
231 |  |  | INV_LOSS01 |  | N/A | Not included in project scope.
232 |  |  | BLD_LOSS0_2 |  | N/A | Not included in project scope.
233 |  |  | CNT_LOSS0_2 |  | N/A | Not included in project scope.
234 |  |  | INV_LOSS0_2 |  | N/A | Not included in project scope.
235 |  |  | BLD_LSSAAL |  | N/A | Not included in project scope.
236 |  |  | INV_LSSAAL |  | N/A | Not included in project scope.
237 |  |  | CNT_LSSAAL |  | N/A | Not included in project scope.
238 |  |  | HUC8_CODE |  | N/A | Not included in project scope.
239 |  |  | CASE_NO |  | N/A | Not included in project scope.
240 |  |  | VERSION_ID |  | N/A | Not included in project scope.
241 |  |  | SOURCE_CIT |  | N/A | Not included in project scope.
242 | CNMS_ DATASET | S_STUDIES_LN |  |  | N/A | Not included in project scope.
243 |  | S_UNMAPPED_LN |  |  | N/A | Not included in project scope.
244 | GRIDS | BLE_WSE01PCT |  |  | Pass
245 |  | BLE_WSE0_2PCT |  |  | Pass
246 |  | BLE_DEP01PCT |  |  | Pass
247 |  | BLE_DEP0_2PCT |  |  | Pass
248 | L_SOURCE_CIT | SOURCE_CIT |  |  | Pass
249 |  | DFIRM_ID |  |  | Pass
250 |  | CITATION |  |  | Pass
251 |  | PUBLISHER |  |  | Pass
252 |  | TITLE |  |  | Pass
253 |  | AUTHOR |  |  | Pass
254 |  | PUB_PLACE |  |  | Pass
255 |  | PUB_DATE |  |  | Pass
256 |  | WEBLINK |  |  | Pass
257 |  | SRC_SCALE |  |  | Pass
258 |  | MEDIA |  |  | Pass
259 |  | CASE_NO |  |  | Pass
260 |  | VERSION_ID |  |  | Pass
¹ | "Hidden" fields are those not visible to the public in the Region 6 viewer at https://webapps.usgs.gov/infrm/estbfe/.
"New" fields are created for the BLE database and are not described in the Technical References. Refer to the Base Level Engineering, Region 6 Submittal Guidance instead.

## Spatial Checks v1
Study |  | 11130209 Little Wichita Watershed
Reviewer |  | Michael R. Wilson, MS, CFM
Review Date |  | 2024-July-02
Spatial Analyst |  | Iqra Shafi
Response Date |  | 05 July 2024
Line No. | Feature Dataset | Feature Class | Pass/ Fail | Topology Checks² | Reviewer Comment | Response Comment
1 | BASE_DATASET | S_POL_AR | Pass | Not Checked
2 |  | S_HUC_AR | Pass | Not Checked
3 | EBFE_DATASET | SUBBASINS | N/A | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
4 |  | XS_1D | N/A | N/A | Not submitted - XS are not required for 2D modeling areas.
5 |  | BFE_2D |  |  | Data not provided, please include these features in the next submittal. | Uploaded
6 |  | WTR_LN | Fail | Not Checked | Features are not always inside 10PCT_FP.
7 |  | WTR_AR | Pass | Not Checked
8 |  | DTL_STUD_LN |  | Not Checked | Digital data is not available; since Dtl_Stud_Ar is not included, I am not certain of the source of these features.
9 |  | DTL_STUD_AR |  |  | Data not provided, please include these features in the next submittal. | Uploaded
10 |  | FLD_HAZ_AR | Pass | Not Checked
11 |  | 10PCT_FP | Fail | Not Checked | There are some minor topologic errors visible in the dataset; a topology check will easily reveal these.
12 | MIT-HAZ_DATASET | S_AOMI_AR | < ? > | Not Checked | Please re-review locations where FLD_HAZ_AR meets the S_HUC_AR boundary; I'm not sure if all areas were captured. |  | `
13 |  | S_FRAC_AR | Pass | Not Checked
14 |  | S_FRAS_PT |  | N/A | Data not provided, please include these features in the next submittal. If not applicable, please indicate so here. | No data in old gdb
15 | CNMS_DATASET | S_STUDIES_LN | N/A | N/A | Not included in project scope.
16 |  | S_UNMAPPED_LN | N/A | N/A | Not included in project scope.
17 | GRIDS | BLE_WSE_01PCT |  | N/A | Data not provided, please include these features in the next submittal. | Uploaded
18 |  | BLE_WSE_0_2PCT |  | N/A | Data not provided, please include these features in the next submittal. | Uploaded
19 |  | BLE_DEP_01PCT |  | N/A | Data not provided, please include these features in the next submittal. | Uploaded
20 |  | BLE_DEP_0_2PCT |  | N/A | Data not provided, please include these features in the next submittal. | Uploaded
² | The following topology rules are listed in Base Level Engineering, Region 6 Submittal Guidance,Version 6, July 2021, page 30.

## Spatial Checks v2
Study |  | 11130209 Little Wichita Watershed
Reviewer |  | Michael R. Wilson, MS, CFM
Review Date |  | 2024-July-10
Spatial Analyst |  | Iqra Shafi
Response Date
Line No. | Feature Dataset | Feature Class | Pass/ Fail | Topology Checks² | Reviewer Comment | Response Comment
1 | BASE_DATASET | S_POL_AR | Pass | Pass
2 |  | S_HUC_AR | Pass | Pass
3 | EBFE_DATASET | SUBBASINS | N/A | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
4 |  | XS_1D | N/A | N/A | Not submitted - XS are not required for 2D modeling areas.
5 |  | BFE_2D | Pass | Pass
6 |  | WTR_LN | Fail | Pass | Features are not always inside 10PCT_FP. (2nd call ... if this is acceptable for this project, then please indicate that here.
7 |  | WTR_AR | Pass | Pass
8 |  | DTL_STUD_LN | Pass | Pass
9 |  | DTL_STUD_AR | Fail | Pass | There are 39 features that appear to belong to another feature class, perhaps S_AOMI_Ar. Detailed study on panel 48077C0154D does not appear to have been captured. | Corrected
10 |  | FLD_HAZ_AR | Pass | Pass
11 |  | 10PCT_FP | Fail | Fail | There are some minor topologic errors visible in the dataset; a topology check will easily reveal these. (2nd call.)
12 | MIT-HAZ_DATASET | S_AOMI_AR | < ? > | Not Checked | Please resolve the issues with Dtl_Stud_Ar before I complete this review. | Corrected | `
13 |  | S_FRAC_AR | Pass | Pass
14 |  | S_FRAS_PT | N/A | N/A | Not included in project scope.
15 | CNMS_DATASET | S_STUDIES_LN | N/A | N/A | Not included in project scope.
16 |  | S_UNMAPPED_LN | N/A | N/A | Not included in project scope.
17 | GRIDS | BLE_WSE_01PCT | Pass | N/A
18 |  | BLE_WSE_0_2PCT | Pass | N/A
19 |  | BLE_DEP_01PCT | < ? > | N/A | There is a large edge difference across the middle of Lake Arrowhead, but this is not shown in the WSE grids. This could
20 |  | BLE_DEP_0_2PCT | < ? > | N/A | be because of a terrain difference. If so, please note that here, otherwise please address the edge difference.
² | The following topology rules are listed in Base Level Engineering, Region 6 Submittal Guidance,Version 6, July 2021, page 30.

## Attribute Checks v3
Study |  |  | 11130209 Little Wichita Watershed
Reviewer |  |  | Michael R. Wilson, MS, CFM
Review Date |  |  | 2024-July-12
Spatial Analyst |  |  | Iqra Shafi
Response Date
Line No. | Feature Dataset | Feature Class | Field | Field Type¹ | Pass/ Fail | Reviewer Comment | Response Comment
1 | BASE_DATASET | S_POL_AR | DFIRM_ID |  | Pass
2 |  |  | VERSION_ID |  | Pass
3 |  |  | POL_AR_ID |  | Pass
4 |  |  | POL_NAME1 |  | Pass
5 |  |  | POL_NAME2 |  | Pass
6 |  |  | POL_NAME3 |  | Pass
7 |  |  | CO_FIPS |  | Pass
8 |  |  | ST_FIPS |  | Pass
9 |  |  | COMM_NO |  | Pass
10 |  |  | CID |  | Pass
11 |  |  | ANI_TF |  | Pass
12 |  |  | ANI_FIRM |  | Pass
13 |  |  | COM_NFO_ID |  | Pass
14 |  |  | SOURCE_CIT |  | Pass
15 |  | S_HUC_AR | HUC_CODE |  | Pass
16 |  |  | HUC_NAME |  | Pass
17 |  |  | DIGITS |  | Pass
18 |  |  | CASE_NO |  | Pass
19 |  |  | VERSION_ID |  | Pass
20 |  |  | SOURCE_CIT |  | Pass
21 | EBFE_DATASET | SUBBASINS | EST_ID |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
22 |  |  | VERSION_ID |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
23 |  |  | E_SUBAS_ID |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
24 |  |  | E_SUBAS_NM |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
25 |  |  | HUC8_CODE |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
26 |  |  | WTR_NM | Hidden | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
27 |  |  | BASIN_DESC | Hidden | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
28 |  |  | EST_AREA |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
29 |  |  | AREA_UNIT |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
30 |  |  | NODE_ID | Hidden | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
31 |  |  | BASIN_TYP | Hidden | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
32 |  |  | SOURCE_CIT |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
33 |  |  | US_1 | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
34 |  |  | US_2 | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
35 |  |  | US_3 | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
36 |  |  | US_4 | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
37 |  |  | DS_1 | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
38 |  |  | PRECIP_IN | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
39 |  |  | MAINCHSLP | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
40 |  |  | E_Q_10PCT | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
41 |  |  | E_Q_04PCT | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
42 |  |  | E_Q_02PCT | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
43 |  |  | E_Q_01PCT | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
44 |  |  | E_Q_01PLUS | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
45 |  |  | E_Q_01MIN | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
46 |  |  | E_Q_0_2PCT | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
47 |  | XS_1D | EST_ID |  | N/A | Not submitted - XS are not required for 2D modeling areas.
48 |  |  | VERSION_ID |  | N/A | Not submitted - XS are not required for 2D modeling areas.
49 |  |  | XS_LN_ID |  | N/A | Not submitted - XS are not required for 2D modeling areas.
50 |  |  | WTR_NM |  | N/A | Not submitted - XS are not required for 2D modeling areas.
51 |  |  | STREAM_STN |  | N/A | Not submitted - XS are not required for 2D modeling areas.
52 |  |  | START_ID |  | N/A | Not submitted - XS are not required for 2D modeling areas.
53 |  |  | XS_LTR | Hidden | N/A | Not submitted - XS are not required for 2D modeling areas.
54 |  |  | XS_LN_TYP |  | N/A | Not submitted - XS are not required for 2D modeling areas.
55 |  |  | E_WSE_1PCT |  | N/A | Not submitted - XS are not required for 2D modeling areas.
56 |  |  | STRMBED_EL | Hidden | N/A | Not submitted - XS are not required for 2D modeling areas.
57 |  |  | LEN_UNIT | Hidden | N/A | Not submitted - XS are not required for 2D modeling areas.
58 |  |  | V_DATUM |  | N/A | Not submitted - XS are not required for 2D modeling areas.
59 |  |  | PROFXS_TXT |  | N/A | Not submitted - XS are not required for 2D modeling areas.
60 |  |  | MODEL_ID |  | N/A | Not submitted - XS are not required for 2D modeling areas.
61 |  |  | SEQ |  | N/A | Not submitted - XS are not required for 2D modeling areas.
62 |  |  | SOURCE_CIT |  | N/A | Not submitted - XS are not required for 2D modeling areas.
63 |  |  | E_WSE_10PC | New | N/A | Not submitted - XS are not required for 2D modeling areas.
64 |  |  | E_WSE_4PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
65 |  |  | E_WSE_2PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
66 |  |  | E_WSE_1PLU | New | N/A | Not submitted - XS are not required for 2D modeling areas.
67 |  |  | E_WSE_1MIN | New | N/A | Not submitted - XS are not required for 2D modeling areas.
68 |  |  | E_WSE_0_2P | New | N/A | Not submitted - XS are not required for 2D modeling areas.
69 |  |  | E_Q_10PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
70 |  |  | E_Q_04PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
71 |  |  | E_Q_02PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
72 |  |  | E_1_02PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
73 |  |  | E_Q_01PLUS | New | N/A | Not submitted - XS are not required for 2D modeling areas.
74 |  |  | E_Q_01MIN | New | N/A | Not submitted - XS are not required for 2D modeling areas.
75 |  |  | E_Q_0_2PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
76 |  | BFE_2D | EST_ID |  | Pass
77 |  |  | VERSION_ID |  | Pass
78 |  |  | EBFE_LN_ID |  | Pass
79 |  |  | BLELEV1PCT |  | Pass
80 |  |  | LEN_UNIT |  | Pass
81 |  |  | V_DATUM |  | Pass
82 |  |  | SOURCE_CIT |  | Pass
83 |  |  | BFE_LN_TYP | New | Pass
84 |  | WTR_LN | EST_ID |  | Fail | This should be "11130209_BLE" (2nd call). | Corrected
85 |  |  | VERSION_ID |  | Pass
86 |  |  | WTR_LN_ID |  | Pass
87 |  |  | WTR_NM |  | Pass
88 |  |  | SHOWN_FIRM | Hidden | Pass
89 |  |  | SHOWN_INDX | Hidden | Pass
90 |  |  | SOURCE_CIT |  | Pass
91 |  | WTR_AR | EST_ID |  | Pass
92 |  |  | VERSION_ID |  | Pass
93 |  |  | WTR_AR_ID |  | Pass
94 |  |  | WTR_NM |  | Pass
95 |  |  | SHOWN_FIRM | Hidden | Pass
96 |  |  | SHOWN_INDX | Hidden | Pass
97 |  |  | SOURCE_CIT |  | Pass
98 |  | DTL_STUD_LN | DTL_LN_ID |  | Pass
99 |  |  | VERSION_ID |  | Pass
100 |  |  | LOMR_ID | Hidden | Pass
101 |  |  | EFF_DATE |  | Pass
102 |  |  | CASE_NO | Hidden | Pass
103 |  |  | SCALE | Hidden | Pass
104 |  |  | SOURCE_CIT |  | Pass
105 |  |  | STATUS | Hidden | Pass
106 |  |  | FIRM_PAN | New | Pass
107 |  |  | TYPE | New | Pass
108 |  |  | CD_YN | New | Pass
109 |  |  | CD_POC | New | Pass
110 |  |  | CD_ADD1 | New | Pass
111 |  |  | CD_ADD2 | New | Pass
112 |  |  | CD_CTY | New | Pass
113 |  |  | CD_STATE | New | Pass
114 |  |  | CD_ZIP | New | Pass
115 |  |  | CD_PHONE | New | Pass
116 |  |  | CD_EMAIL | New | Pass
117 |  | DTL_STUD_AR | DTL_AR_ID |  | Pass
118 |  |  | VERSION_ID |  | Pass
119 |  |  | LOMR_ID | Hidden | Pass
120 |  |  | EFF_DATE |  | Pass
121 |  |  | CASE_NO | Hidden | Pass
122 |  |  | SCALE | Hidden | Pass
123 |  |  | SOURCE_CIT |  | Pass
124 |  |  | STATUS | Hidden | Pass
125 |  |  | FIRM_PAN | New | Pass
126 |  |  | TYPE | New | Pass
127 |  |  | CD_YN | New | Pass
128 |  |  | CD_POC | New | Pass
129 |  |  | CD_ADD1 | New | Pass
130 |  |  | CD_ADD2 | New | Pass
131 |  |  | CD_CTY | New | Pass
132 |  |  | CD_STATE | New | Pass
133 |  |  | CD_ZIP | New | Pass
134 |  |  | CD_PHONE | New | Pass
135 |  |  | CD_EMAIL | New | Pass
136 |  | FLD_HAZ_AR | EST_ID |  | Pass
137 |  |  | VERSION_ID |  | Pass
138 |  |  | EST_AR_ID |  | Pass
139 |  |  | STUDY_TYP | Hidden | Pass
140 |  |  | FLD_ZONE | Hidden | Pass
141 |  |  | ZONE_SUBTY |  | Pass
142 |  |  | SFHA_TF | Hidden | Pass
143 |  |  | STATIC_BFE | Hidden | Pass
144 |  |  | V_DATUM |  | Pass
145 |  |  | DEPTH | Hidden | Pass
146 |  |  | LEN_UNIT |  | Pass
147 |  |  | VELOCITY | Hidden | Pass
148 |  |  | VEL_UNIT | Hidden | Pass
149 |  |  | AR_REVERT | Hidden | Pass
150 |  |  | AR_SUBTRV | Hidden | Pass
151 |  |  | BFE_REVERT | Hidden | Pass
152 |  |  | DEP_REVERT | Hidden | Pass
153 |  |  | DUAL_ZONE | Hidden | Pass
154 |  |  | SOURCE_CIT |  | Pass
155 |  |  | EST_RISK | New | Pass
156 |  | TENPCT_FP | EST_ID |  | Pass
157 |  |  | VERSION_ID |  | Pass
158 |  |  | EST_AR_ID |  | Pass
159 |  |  | STUDY_TYP | Hidden | Pass
160 |  |  | FLD_ZONE | Hidden | Pass
161 |  |  | ZONE_SUBTY |  | Pass
162 |  |  | SFHA_TF | Hidden | Pass
163 |  |  | STATIC_BFE | Hidden | Pass
164 |  |  | V_DATUM |  | Pass
165 |  |  | DEPTH | Hidden | Pass
166 |  |  | LEN_UNIT |  | Pass
167 |  |  | VELOCITY | Hidden | Pass
168 |  |  | VEL_UNIT | Hidden | Pass
169 |  |  | AR_REVERT | Hidden | Pass
170 |  |  | AR_SUBTRV | Hidden | Pass
171 |  |  | BFE_REVERT | Hidden | Pass
172 |  |  | DEP_REVERT | Hidden | Pass
173 |  |  | DUAL_ZONE | Hidden | Pass
174 |  |  | SOURCE_CIT |  | Pass
175 |  |  | EST_RISK | New | Pass
176 | MIT-HAZ_DATASETS | S_AOMI_AR | AOMI_ID |  | Pass
177 |  |  | CID |  | Pass
178 |  |  | POL_NAME1 |  | Pass
179 |  |  | AOMI_CLASS |  | Pass
180 |  |  | AOMI_TYP |  | Pass
181 |  |  | AOMI_INFO |  | Pass
182 |  |  | HUC8_CODE |  | Pass
183 |  |  | CASE_NO |  | Pass
184 |  |  | VERSION_ID |  | Pass
185 |  |  | SOURCE_CIT |  | Pass
186 |  | S_FRAC_AR | CEN_BLK_ID |  | Pass
187 |  |  | ARV_BG_TOT |  | Pass
188 |  |  | ARV_CN_TOT |  | Pass
189 |  |  | HAZARD_TYP | Hidden | Pass
190 |  |  | SCENAR_ID | Hidden | Pass
191 |  |  | TOT_LOSS10 | Hidden | Pass
192 |  |  | BL_TOT10 | Hidden | Pass
193 |  |  | CL_TOT10 | Hidden | Pass
194 |  |  | TOT_LOSS04 | Hidden | Pass
195 |  |  | BL_TOT04 | Hidden | Pass
196 |  |  | CL_TOT04 | Hidden | Pass
197 |  |  | TOT_LOSS02 | Hidden | Pass
198 |  |  | BL_TOT02 | Hidden | Pass
199 |  |  | CL_TOT02 | Hidden | Pass
200 |  |  | TOT_LOSS01 |  | Pass
201 |  |  | BL_TOT01 |  | Pass
202 |  |  | CL_TOT01 |  | Pass
203 |  |  | TOT_LSS0_2 | Hidden | Pass
204 |  |  | BL_TOT0_2 | Hidden | Pass
205 |  |  | CL_TOT0_2 | Hidden | Pass
206 |  |  | TOT_LSSAAL | Hidden | Pass
207 |  |  | BL_TOTAAL | Hidden | Pass
208 |  |  | CL_TOTAAL | Hidden | Pass
209 |  |  | HUC8_CODE |  | Pass
210 |  |  | CASE_NO |  | Pass
211 |  |  | VERSION_ID |  | Pass
212 |  |  | SOURCE_CIT |  | Pass
213 |  | S_FRAS_PT | FRAS_ID |  | N/A | Not included in project scope.
214 |  |  | CEN_BLK_ID |  | N/A | Not included in project scope.
215 |  |  | HAZARD_TYP |  | N/A | Not included in project scope.
216 |  |  | OCCUP_TYP |  | N/A | Not included in project scope.
217 |  |  | ARV_BG |  | N/A | Not included in project scope.
218 |  |  | SCENAR_ID |  | N/A | Not included in project scope.
219 |  |  | ARV_CN |  | N/A | Not included in project scope.
220 |  |  | BLD_LOSS10 |  | N/A | Not included in project scope.
221 |  |  | CNT_LOSS10 |  | N/A | Not included in project scope.
222 |  |  | INV_LOSS10 |  | N/A | Not included in project scope.
223 |  |  | BLD_LOSS04 |  | N/A | Not included in project scope.
224 |  |  | CNT_LOSS04 |  | N/A | Not included in project scope.
225 |  |  | INV_LOSS04 |  | N/A | Not included in project scope.
226 |  |  | BLD_LOSS02 |  | N/A | Not included in project scope.
227 |  |  | CN_LOSS02 |  | N/A | Not included in project scope.
228 |  |  | INV_LOSS02 |  | N/A | Not included in project scope.
229 |  |  | BLD_LOSS01 |  | N/A | Not included in project scope.
230 |  |  | CNT_LOSS01 |  | N/A | Not included in project scope.
231 |  |  | INV_LOSS01 |  | N/A | Not included in project scope.
232 |  |  | BLD_LOSS0_2 |  | N/A | Not included in project scope.
233 |  |  | CNT_LOSS0_2 |  | N/A | Not included in project scope.
234 |  |  | INV_LOSS0_2 |  | N/A | Not included in project scope.
235 |  |  | BLD_LSSAAL |  | N/A | Not included in project scope.
236 |  |  | INV_LSSAAL |  | N/A | Not included in project scope.
237 |  |  | CNT_LSSAAL |  | N/A | Not included in project scope.
238 |  |  | HUC8_CODE |  | N/A | Not included in project scope.
239 |  |  | CASE_NO |  | N/A | Not included in project scope.
240 |  |  | VERSION_ID |  | N/A | Not included in project scope.
241 |  |  | SOURCE_CIT |  | N/A | Not included in project scope.
242 | CNMS_ DATASET | S_STUDIES_LN |  |  | N/A | Not included in project scope.
243 |  | S_UNMAPPED_LN |  |  | N/A | Not included in project scope.
244 | GRIDS | BLE_WSE01PCT |  |  | Pass
245 |  | BLE_WSE0_2PCT |  |  | Pass
246 |  | BLE_DEP01PCT |  |  | Pass
247 |  | BLE_DEP0_2PCT |  |  | Pass
248 | L_SOURCE_CIT | SOURCE_CIT |  |  | Pass
249 |  | DFIRM_ID |  |  | Pass
250 |  | CITATION |  |  | Pass
251 |  | PUBLISHER |  |  | Pass
252 |  | TITLE |  |  | Pass
253 |  | AUTHOR |  |  | Pass
254 |  | PUB_PLACE |  |  | Pass
255 |  | PUB_DATE |  |  | Pass
256 |  | WEBLINK |  |  | Pass
257 |  | SRC_SCALE |  |  | Pass
258 |  | MEDIA |  |  | Pass
259 |  | CASE_NO |  |  | Pass
260 |  | VERSION_ID |  |  | Pass
¹ | "Hidden" fields are those not visible to the public in the Region 6 viewer at https://webapps.usgs.gov/infrm/estbfe/.
"New" fields are created for the BLE database and are not described in the Technical References. Refer to the Base Level Engineering, Region 6 Submittal Guidance instead.

## Spatial Checks v3
| Study |  | 11130209 Little Wichita Watershed
| Reviewer |  | Michael R. Wilson, MS, CFM
| Review Date |  | 2024-July-12
| Spatial Analyst |  | Iqra Shafi
Response Date
| Line No. | Feature Dataset | Feature Class | Pass/ Fail | Topology Checks² | Reviewer Comment | Response Comment
| 1 | BASE_DATASET | S_POL_AR | Pass | Pass
| 2 |  | S_HUC_AR | Pass | Pass
| 3 | EBFE_DATASET | SUBBASINS | N/A | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
| 4 |  | XS_1D | N/A | N/A | Not submitted - XS are not required for 2D modeling areas.
| 5 |  | BFE_2D | Pass | Pass
Talk to Michael 10 pct? | 6 |  | WTR_LN | Pass | Pass
| 7 |  | WTR_AR | Pass | Pass
| 8 |  | DTL_STUD_LN | Pass | Pass
| 9 |  | DTL_STUD_AR | Fail | Pass | Detailed study on panel 48077C0154D does not appear to have been captured. | Corrected
| 10 |  | FLD_HAZ_AR | Pass | Pass
Working | 11 |  | 10PCT_FP | Fail | Fail | There are some minor topologic errors visible in the dataset; a topology check will easily reveal these. (3rd call.) | Corrected
| 12 | MIT-HAZ_DATASET | S_AOMI_AR | Pass | Pass |  |  | `
| 13 |  | S_FRAC_AR | Pass | Pass
| 14 |  | S_FRAS_PT | N/A | N/A | Not included in project scope.
| 15 | CNMS_DATASET | S_STUDIES_LN | N/A | N/A | Not included in project scope.
| 16 |  | S_UNMAPPED_LN | N/A | N/A | Not included in project scope.
| 17 | GRIDS | BLE_WSE_01PCT | Pass | N/A
| 18 |  | BLE_WSE_0_2PCT | Pass | N/A
| 19 |  | BLE_DEP_01PCT | Pass | N/A
| 20 |  | BLE_DEP_0_2PCT | Pass | N/A
| ² | The following topology rules are listed in Base Level Engineering, Region 6 Submittal Guidance,Version 6, July 2021, page 30.

## Sheet1
grid index features
5000 m 500 m

## QC_Workflow
Things to check for:
Correct projection
Correct cell size
Everything smaller than HUC area
10PCT_FP smaller than 100 year
BFE_2D contained within 100 year
WTR_AR only contains named streams or streams greater than x acres
DtlStdln has a line in every feature included in dtl_STD_AR
DtlStdln not extending outside of dtl_STD_AR
Does DTL_STD_AR cover approriate area of both effective and BLE mapping?