## Instructions
Engineering Files QC Checklists
1 | Please insert Study Name on Sign Off tab. This will automatically populate the remainder of the spreadsheets. Please insert the Feme Case No in front of the document name, and save the file with that name on your network.
2 | Please enter name (and initials) on Sign Off tab. If additional lines are required, copy the last line and insert below. As you complete the spreadsheets, you will need only to insert your initials.
3 | Please enter the name of the basin, stream reach, or coastal beach that you are reviewing in the appropriate space at the top of the sheet. The first of each set of forms requires names and dates to be added at the top of each column.
4 | Technical Review refers to the final review of work. This will be accomplished by an independent team of subject matter experts. Work should be considered as complete and ready to submit when submitted to this team. Be certain to add initials to the form.
5 | QA Verification refers to the determination that the work is ready to deliver. It is accomplished by a representative of the QA Manager. This review is cursory and involves review of records and spot checks of errors that appear to be systemic. The purpose of this review is to first ensure that all errors have been corrected, files are ready to be submitted and all records are ready for archival. Secondly, the review will focus on whether errors are systemic (requiring adjustment to procedure, or perhaps further training) or random (requiring review of schedules, budgets, etc.) Be certain to add initials to the form.
6 | Should there be a requirement to review data a second (or more) time, simply copy the appropriate columns and insert them to the right of the original review columns.
7 | A separate worksheet may be required for each basin, stream reach or model, and coastal beach. In this case copy the worksheet and insert into the workbook in the proper sequential order. Please label the tab with the basin name, stream reach or model number(s), or beach to make use of the workbook easier.
8 | Please indicate status of each item by responding P (Pass), F (Fail), NA (Not applicable).
9 | When your review is complete and you are satisfied with the quality of the work, please sign a hard copy of the sign off sheet. Please be certain to retain the signed sheet with other project documents and be sure the next reviewer knows where to locate it. QA Verification reviewer, please scan the sign off sheet and add to the document files for the project.

## Sign off-QC Stamp
ATKINS QUALITY REVIEW CHECKLIST SIGN OFF FORM
Study / Stream Name | Little Wichita 2D BLE
Deliverable | H&H model
MIP Case #:
PM: | Seth Ahrens
QC REVIEW ACTIVITY
Ready for QC | *Originator / Date : | Watearth
2023-03-03
QC Review | *Reviewer / Date : | Shrinivas Kaulgud 03/06/2023
Changes Made | *Originator/ Date : | Watearth
2023-04-07
QC Verification | *QC Reviewer: | Solaleh Khezri
| Date: | 2023-08-24
PQM Approval | *QA: | Vikram Shrivastava
| Date: | 2023-10-10

## Model Geometry
Hydraulics
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Little Wichita 901 - headwater |  |  |  |  | Shrinivas Kaulgud |  | 2023-03-06
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
Folder sturcture / Model naming
1 | Is model folder follow TWDB guidelines folder structure |  | Fail | Missing DSS folder. Please add HMS output DSS under DSS folder. Precipitation folder missing from submitted model so can't review precip data We were asked to remove spaces from folder names. Please remove space in Land Classification | Agree, Changes Made |  | SK | Done.
2 | Per H&H workshop the model name should be short should have 3-4 letter acronym. For example instead of UpperFrio_123 the model name should UPFR_(last 3 digits of HUC10) |  | Pass | Comment in row 1 still applies here | Agree, Changes Made |  | SK | Done.
RAS Mapper Setup
2 | Is correct projection used for model. |  | Pass
3 | Does the terrain and model projections match |  | Pass
4 | Is the model geometry linked to Terrain, Land Cover, and Infiltration layers |  | Pass | linked to wrong terrain. The hydro enforced terrain is linked, which does not include the terrain modifications. Revise the terrain names. | Agree, Changes Made |  | SK | Done.
5 | Do the model results show Terrain, Landcover and Infiltration layers linked |  | Pass | see comment above. | Agree, Changes Made |  | SK | Done.
6 | Are there two terrains present in the model. Second terrain is clone of actual terrain and include terrain modifications |  | Pass | Naming should be revised. Hydro-enforced terrain which includes modification should be linked to results and geometry. | Agree, Changes Made |  | SK | Done.
2D Mesh
7 | Does the digital terrain model input for the 2D model cover the entire 2D study area? |  | Pass
8 | Within the modeled area does the 2D domain extent use larger of the USGS HUC8 boundary and computed HUC8 boundary. |  | Pass
9 | Is nominal cell spacing for the 2D mesh set at 200' X200'. Do break lines and refinement regions use 100'X100' nominal cell spacing. Do any areas use less than 100'X100' nominal spacing. |  | Pass
10 | Is the model domain delineated properly to capture all contributing flows through rain-on-grid or external hydrograph? |  | Pass
11 | Are there any 2D mesh errors? |  | Fail | please fix the mesh errors. | Agree, Changes Made |  | SK | Done.
Breaklines
12 | Are break lines sufficiently detailed to capture streamline, roads, railroads, dam crests, dam spillways, any berms? |  | Pass
13 | Where break lines are conflicting with other break lines or refinement regions are break line conflicts resolved. Simplify mesh by removing some of the break lines or adjusting refinement regions |  | Pass
14 | Are the break lines planarized |  | Pass
15 | Are break lines added such that the grid is not leaking. |  | Pass
Refinement Regions
16 | Are refinement regions added along stream lines and at urban areas? |  | Fail | refinement region for urban area is missing | Agree, Changes Made |  | SK | OK
17 | Ussually 100' buffer for most channel. If channel width more than 200' the refinement region extended to cover open channel. |  | Pass
Manning's n
18 | Do the roughness coefficients match TWDB BLE Guidelines? |  | Fail | There is no maning N values in the model. Please add them. | Agree, Changes Made |  | SK | Done.
19 | Are channel Manning's n values reasonable? Have the channel region Polygon override for manning's n Values? |  | Pass | To be checked after validation |  |  | SK | Done.
20 | Is the Manning's n dataset associated with the geometry file? |  | Pass
Infiltration Layer
21 | Do Curve Numbers (CN) values match TWDB BLE Guidelines Table 2.4. |  | Fail | CN values used for low/ medium/high intensity development and not within TWDB range. | Agree, Changes Made |  | SK | Done.
22 | Are the Curve Numbers reasonable? No curve number values are less than 30. |  | Pass |  |  |  | SK | OK
23 | Has the Infiltration Layer been correctly assigned to the geometry |  | Pass
Hydraulics Structures (including dams)
24 | Has a copy of the Terrain layer (Terrain.HydroEnforced) been created ? |  | Pass | See comment in row 6. | Agree, Changes Made |  | SK | Done.
25 | Have hydro forcing burn lines been applied at all crossing using the Terrain Channel Modification Tool? Are the bottom width, and max extent widths of each line appropriately estimated to match the current structure size? Changing the side slopes can cause some issues with stability if it is too steep or vertical. |  | Fail | Please see QC shapefile. Please make sure the culvert length are sufficient. | Agree, Changes Made |  | SK | Done.
26 | Has the Terrain.HydroEnforced.hdf file been correctly assigned to the geometry? |  | Fail | See comment in row 6. | Agree, Changes Made |  | SK | Done.
27 | Does the model account for any significant flow-regulating dams? |  | Fail | Add break lines and refinement regions for dams greater than 10 ac. | Agree, Changes Made |  | SK | Done.
28 | Were 2D connections appropriately set-up to model the regulated outflow from the dams? |  | Pass
29 | Are the sources for the dam operations documented? |  | Pass
Other
30 | Are comparison points/lines (i.e., internal 2-D connections) captured and compared against applicable benchmarks? (gage, high water mark, effective BFE, etc.) |  | Pass
31 | If applicable, is the transfer line between this model and a downstream model well away from any boundary condition effects? |  | Pass
32 | Are perimeter boundary conditions applied where flow is leaving the 2D area? |  | Pass | Please make sure the perimiter BC one continuous line. | Agree, Changes Made |  | SK | OK
33 | Are boundary conditions applied such the flow does not build up at the boundary of the 2D mesh? |  | Pass | To be checked in next round | Agree, Changes Made |  | SK | OK
34 | Are there any other comments related to the model geometry? |  | Pass
Total QC citations for this review |  |  | 7
Percent Passing |  |  | 72%
Other Comments

## Unsteady Flow Data
Hydrology
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Little Wichita 901 |  |  |  |  | Shrinivas Kaulgud |  | 2023-03-06
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
1 | Are the precipitation depths reasonable, and sufficiently documented? Was a reasonable temporal storm distribution used? |  | Unsure - See Reviewer Comments | No data provided for review.
2 | Have the flow files for the Pluvial events been assigned correctly ? |  | Pass
3 | Are the flow files based on proper naming convention for the event, precip source ? |  | Pass | To be checked in multi profile |  |  | SK | OK
4 | Has the SA/2D flow area been assigned the correct DSS precipitation file from the hydrology folder? Has the appropriate event in the DSS file been selected? |  | Unsure - See Reviewer Comments | No data provided for review. |  |  | SK | OK
5 | Does the model include all required and scoped events / frequencies? |  | Pass | To be checked in multi profile |  |  | SK | OK
6 | Does model plan and precip have same AEP event. For example, 10% AEP plan use 10% AEP rainfall. |  | Pass | To be checked in multi profile. Matched for 1% and 0.2%. |  |  | SK | OK
7 | per |  | Not Applicable for This
8 | Are the incoming hydrographs being applied properly? (location, shapes, timing, etc.). Confirm that any incoming hydrographs have the same time and magnitude of peak flow by opening up the upstream RAS models |  | Pass
9 | For hydrographs transferred from one RAS model to a downstream RAS model, are the incoming and outgoing hydrographs being applied at a coincident location? |  | Pass | Will check DS model later. |  |  | SK | Done
10 | If using a direct flow transfer from an upstream model, does the time interval for the inflowing hydrograph match the time interval of the extracted hydrograph from the upstream model? |  | Pass | To be checked in next submittal |  |  | SK | Done
11 | Do all boundary conditions have a hydrograph or elevation/slope data assigned? |  | Pass
12 | Is the downstream boundary condition consistent with ground slope or know downstream WSEL? |  | Pass | To be checked in multi profile |  |  | SK | Done
13 | Are there any other comments related to the unsteady flow data? |  | Pass
Total QC citations for this review |  |  | 0
Percent Passing |  |  | 100%
Other Comments

## Model Execution and Results
Hydraulics
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Little Wichita 901 |  |  |  |  | Solaleh Khezri
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
Model Execution
1 | Is the Diffusion Wave Equation being used? |  | Pass
2 | Is the timestep appropriate for the mesh size and calculated velocities? |  | Pass
3 | Are the Computation Options and Tolerances set to the default values? If no, is it documented and justified? |  | Pass
4 | Are the advanced time step control tab settings selected properly ? Are Variable time step parameters reasonable / Meet project needs ? |  | Pass
5 | Are both the "hydrograph output interval" and "mapping output interval" set at a reasonable interval to capture peak flows within the model? |  | Pass
6 | Are there any other comments related to the HEC-RAS Unsteady Plan settings? |  | Pass
Model Results
7 | Does the model run with no cell errors? |  | Fail | Please fix the mesh errors. | Agree, Changes Made |  | SK | Done
8 | Does the model have acceptable volume conservation (less than 3%) |  | Pass | Will check other plans later. |  |  | SK | Done
9 | Is the Courant number generally less than 2 but no greater than 5? |  | Pass
10 | Was the model simulation long enough to pass the entire hydrograph(s) through the model? |  | Pass
11 | Is any flow trapped at the 2D boundary? |  | Pass
12 | Are all water-surface elevation convergence warning messages acceptable per computation tolerances? |  | Pass
13 | Are contributing areas contained within the 2D mesh or accounted for with inflow hydrographs? |  | Pass
14 | Are hydrographs at the internal and external boundary conditions smooth? |  | Fail | There is a jump at the beginnning of BC-1 the outer outflow boundary. Please also revise the naming to differentiate between different types of BC line, general-outflow for perimiter boundary, and inflow and outflow boundary for inflow and outflow BCs. | Agree, Changes Made |  | SK | OK
15 | Check to make sure the computed maximum depth, WSEL, and velocity values are not from numerical surge (i.e. Beginning of model). |  | Pass
16 | Are the water surface and depth grids reasonable with no artificial dips or spikes? |  | Pass
17 | Is there any ponding behind road embankments? If so, is it reasonable or should the model be modified to allow flow through the embankment? |  | Fail | Please see QC shapefile. | Agree, Changes Made |  | SK | Done
18 | Do the velocity grids appear reasonable with no unusually high velocity areas? |  | Pass
19 | Have instances of model instabilities at the beginning of the simulation due to initial wetting of a dry grid been addressed? Should a initial condition (wet start) be used? |  | Pass
20 | Are there other comments related to the model results? |  | Pass
Total QC citations for this review |  |  | 3
Percent Passing |  |  | 85%
Other Comments

## Model Validation
Calibration and Validation
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Little Wichita 901 |  |  |  |  | Solaleh Khezri
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
Validation is Performed for the 100-yr Only
1 | Is the method and parameters adjusted for model validation documented? |  | Pass
2 | Are the modifications to the Curve Number's and/or Manning's n reasonable? |  | Pass
3 | Have representative points in the watershed been used to check pluvial flows to confirm they are within the 1% regression bounds? |  | Pass
4 | Do the peak discharges compare favorably to gages, effective studies, INFRM flows, or other approved benchmarks? If not, have attempts been made to calibrate? |  | Pass
5 | Are there other comments related to model validation?
Joint Probability Checks
6 | Was the JP rainfall adjusted for calibration? If so, is it within the acceptable limits outlined in Appendix B of FEMA's best practices document? |  | Not Applicable for This
Total QC citations for this review |  |  | 0
Percent Passing |  |  | 100%
Other Comments

## Model Clean-up
Model Clean-up
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Little Wichita 901 |  |  |  |  | Solaleh Khezri
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
For Submission to Water Board
1 | HEC-RAS Project files: Have all temporary and interim project files been deleted from the model? (*.p##, *.g##, *.u##) |  | Pass
2 | HEC-RAS Output files: Have all unused output files been deleted from the project directory? (*.O##,*.hyd##, *.c##,*.b##, *.bco##, *.g##.hdf, *.p##.hdf, *.p##.blf, *.IC.O##, *.x##) |  | Pass
3 | HEC-RAS DSS Output file: Have any unused model outputs associated with plans no longer in use been deleted from the HEC-DSS Output file? |  | Pass
4 | HEC-RAS DSS Output file: Do hydrographs for all 7 recurrence interval events (10%, 4%, 2%, 1%, 0.2%, and 1% (+/-)) show up under the "Plot Stage and Flow Hydrographs" option within HEC-RAS? |  | Pass
5 | Have all old versions of geometries and plans been removed from the tree list within RAS Mapper? |  | Pass
6 | Have all non-essential shapefiles been removed from RAS Mapper? |  | Pass
7 | Is there a projection defined within RAS Mapper and is it correct? |  | Pass
8 | Are the terrain and land cover files correctly associated with the geometry and results layers? |  | Pass
9 | Have all folders and/or files that are not necessary for viewing results been deleted from the project folder (i.e. shapefiles, Excel documents, etc.)? |  | Pass
10 | Have all old and non-relevant comments within each unsteady flow plan been removed? |  | Pass
11 | Can the "computation log file" and "runtime messages" be seen for each plan? |  | Pass
Total QC citations for this review |  |  | 0
Percent Passing |  |  | 100%
Other Comments

## Drop Down List
Pass
Fail
Unsure - See Reviewer Comments
Not Applicable for This
Agree, Changes Made
Disagree, No Changes Made
Other, See Orignator Comments