## Submittal Data
The following data should be included for independent review when applicable:
Hydrology
HMS model(s)
Reporting/Documentation of methods
Hydraulics
Input hydrology (e.g. DSS)
Land Use/Cover data
RAS model data (applicable geometry, plan, projection, rasmapper, dss/dsc outputs, etc)
Terrain (terrain DEM used in model)
Reporting/Documentation of methods
Mapping
Scoped flooding sources spatial file (e.g. flooding sources and reaches that are either effective or drain greater than 1 sqmi with a depth greater than 1')
Raw model 10, 4, 2, 1-, 1, 1+, 0.2% water surface elevation grids
Raw model 10, 4, 2, 1-, 1, 1+, 0.2% depth grids
Raw model 1% velocity grid
SFHA Clipped 10, 4, 2, 1, 0.2% water surface elevation grids
SFHA Clipped 10, 4, 2, 1, 0.2% depth grids
Percent annual chance grid
Percent 30-year grid
S_Fld_Haz_Ar feature class
S_CSLF_Ar feature class
Additional_1pct feature class (non-SFHA 1% inundation)
Reporting/Documentation of methods

## Hydrology & Hydraulics
| 2-D BLE QC Review Checklist | Date: |  |  | QC Checkpoint 1 is a project-level QC that should be performed for the entire project footprint prior to executing runs in individual work areas.
| Originator: Mafuzur Rahaman | 2022-10-08
| QC Checkpoint 1 Review By: Seyoum Asamenaw | 2022-10-10 |  |  | QC Checkpoint 2 should be completed after the 1% run is calibrated and finalized but prior to the full run of all recurrence intervals.
| QC Checkpoint 1 Review Complete Date: | 2022-10-10
| QC Checkpoint 2 Review By:Seyoum Asamenaw | 2022-10-10 |  |  | QC Checkpoint 3 is the final QC and should be performed after floodplain mapping is complete.
| QC Checkpoint 2 Review Complete Date: | 2022-10-10
| QC Checkpoint 3 Review By: Seyoum Asamenaw | 2023-01-06 |  |  | *If the cells are shaded, it is not necessary to complete that individual check at that checkpoint.
| QC Checkpoint 3 Review Complete Date: | 2023-01-06
| QC Check and Description | FEMA Citation | Self Check Complete | QC Checkpoint 1 |  |  | Self Check Complete | QC Checkpoint 2 |  |  | Self Check Complete | QC Checkpoint 3
|  | Reference |  | P/F/NA | Comment | Modeler Disposition |  | P/F/NA | Comment | Modeler Disposition |  | P/F/NA | Comment | Modeler Disposition
General
| Is the product scalable? (i.e., can the model be upgraded to meet regulatory requirements?) | Base Level Engineering Analyses and Mapping 1.0 |  | P |  |  |  | P |  |  |  | P
| Is a 2-Dimensional model appropriate for this study? | Guidance for Flood Risk Analysis and Mapping Hydraulics: Two-Dimensional Analysis 2016, Section 1.2.1 |  | P |  |  |  | P |  |  |  | P
| Is the correct unit system being used (i.e. SI vs. U.S. Customary)? Options -> "Unit System (US Customary/SI)…" |  |  | P |  |  |  | P |  |  |  | P
Terrain
| Does the digital terrain cover the entire 2D study area? | SID 50 Two-Dimensional Analysis: 3.1 Topographic Information |  | P
| Is the model hydrology based on a DEM with an appropriate resolution? (HUC 10 or smaller should use 10-meter or better. Larger than HUC 10 should use 30-meter or better.) | Automated Engineering 2.1.1 |  | P
| Does the model use terrain data at least as current as the current effective study and meet FEMA topo standards? | Hydraulics: Two-Dimensional Analysis 3.1 |  | P
| Is the input topography reasonably dense? (Cell size should be 10-foot or less.) | Hydraulics: Two-Dimensional Analysis 3.1 |  | P
| Have topographic abnormalities been corrected? (No. drops or rises due to underlying data errors.) | Hydraulics: Two-Dimensional Analysis 3.1 | [5 empty] | P
Incoming Hydrographs (HMS and/or gage based)
| Are the basin delineations reasonable? | SID 61, 90, 93 |  | P
| Are curve numbers reasonable, and sufficiently documented? | SID 57, 59, 61 |  | P
| Are the precipitation depths reasonable, and sufficiently documented? -Confirm that peak rainfall values match HMS output -Confirm that the latest DSS files are being used in HEC-RAS | SID 61, 90, 93 |  | NA | Spatially varied preciptiation DSS files drived from NOAA Atlas 14 were used for Hydrology in RAS Mapper
| Is the time of concentration determination reasonable for all HMS subbasin elements? | SID 61, 90, 93 |  | NA | Spatially varied preciptiation DSS files drived from NOAA Atlas 14 were used for Hydrology in RAS Mapper
| Was a reasonable temporal storm distribution used? | SID 61, 90, 93 |  | P
| Was the appropriate areal reduction factor used for any contributing drainage area inflow modeled using rainfall-runoff? | SID 61, 90, 93 |  | NA | Areal reduction factor was not used
| If PeakFQ is used, was the correct confidence interval used? (Should be 0.84 instead of default 0.95) | SID 61, 84, 90, 93 |  | P
| Is gage-based hydrology reasonable? Does the gage-analysis follow identified best practices for this project? (If USGS report is available for the gages in this area, the same methodology should be applied to this project, or reasons for deviation should be documented.) | SID 61, 90, 93 |  | P
| Does the Period of Record (POR) for all gage analyses represent current conditions (i.e. post construction of large reservoirs/dams, post construction of major diversion flows, etc.)? | SID 57, 61, 90 |  | P
| Does the shape and time-to-peak of the inflowing hydrograph closely resemble past documented large storm events? | SID 59, 61, 90, 93 |  | P
| If using a direct flow transfer from an upstream model, does the time interval for the inflowing hydrograph match the time interval of the extracted hydrograph from the upstream model? | Two-Dimensional Analysis: 3.5 Hydrologic Inputs |  | P
| Post Base Flood Reasonability Checks: Does the peak discharge compare favorably to gages, effective studies, regional regression studies, or other approved benchmark? If not, have attempts been made to calibrate? (This applies to both the study area and incoming hydrograph models.) | SID 59 Guidance for Flood Risk Analysis and Mapping General Hydrologic Considerations 7.0 | [5 empty] | P |  |  |  | P
Hydrology
| Does the model include all frequencies? (10%, 4%, 2%, 1% and 0.2%) | SID 84 | [5 empty] | P |  |  |  | P
| Does the model include the 1%-plus and 1%-minus flood events? | SID 84 | [5 empty] | P |  |  |  | P
| Was the appropriate areal reduction factor used for the 2D mesh? | Hydrology: Rainfall-Runoff Analysis 2.1 | [5 empty] | NA | Areal reduction factor was not used |  |  | NA | Areal reduction factor was not used
| Are curve numbers reasonable, and sufficiently documented? N:\Texas_2d\BLE_2D_Reference\TWDB\Hydrology\TWDB_Hydrology_Notebook.docx | SID 57, 59, 81 | [5 empty] | P |  |  |  | P
| Are the incoming hydrographs being applied properly? (location, shapes, timing, etc.) - Confirm that any incoming hydrographs have the same time and magnitude of peak flow by opening up the upstream RAS models | SID 61, 90, 93 | [5 empty] | P |  |  |  | P
| For hydrographs transferred from one RAS model to a downstream RAS model, are the incoming and outgoing hydrographs being applied a coincident location? | Two-Dimensional Analysis: 3.1 Topographic Information Two-Dimensional Analysis: 3.5 Hydrologic Inputs | [5 empty] | P |  |  |  | P
| If applicable, does the peak discharge compare favorably to gages or effective studies? If not, have attempts been made to calibrate? (This applies to both the study area and incoming hydrograph models.) | SID 59 Guidance for Flood Risk Analysis and Mapping General Hydrologic Considerations 7.0 Two-Dimensional Analysis: 4.0 Calibration of Hydraulic Models | [5 empty] | P | No USGS gage in this study area. The peak water surface elevations are within a USGS gage range in the downstream model (DMF4). |  |  | P | No USGS gage in this study area. The peak water surface elevations are within a USGS gage range in the downstream model (DMF4).
| Does the model account for any significant flow-regulating dams? | Automated Engineering 2.1.2 | [5 empty] | P |  |  |  | P
| Confirm that precip values are based on DSS file and not hardcoded (or that any hardcoding of precip values are explained in the plan notes). | [6 empty] | NA | Precipitations are based on spatially distributed DSS gridded precipitation. |  |  | NA | Precipitations are based on spatially distributed DSS gridded precipitation.
| For all RAS unsteady flow files that use hardcoded precip values, does the timestep match the original derived excess precipitation hyetographs? | [6 empty] | NA |  |  |  | NA
| For all RAS unsteady flow files that use DSS hydrology, the hardcoded table is empty (and vice versa) | [6 empty] | P |  |  |  | P
| For all RAS unsteady flow files that use DSS hydrology, is the DSS file placed within the RAS model folder? | [6 empty] | P |  |  |  | P
| For all RAS unsteady flow files that use DSS hydrology, confirm that the user defined timestep and start date match the DSS file. | [6 empty] | P |  |  |  | P
Hydraulics
| Does the software meet FEMA's requirements for Nationally and Locally accepted models | https://www.fema.gov/hydraulic-numerical-models-meeting-minimum-requirement-national-flood-insurance-program |  | P |  |  |  | P |  |  |  | P
| Is the 2D mesh reasonably sized to limit cell count and obtain reasonable velocities? -200ft default cell size, 50ft for populated places - Breaklines cell size 100ft (50ft if breaklines fall within refinement regions) | SID 61, 90, 93 | [5 empty] | P
| Is the timestep appropriate for the mesh size and calculated velocities? -can be 15s-1min, with 30s as default. | SID 61, 90, 93 | [5 empty] | P
| Is the model domain delineated properly to capture all contributing flows through rain-on-grid or external hydrograph? | Engineering Judgement | [5 empty] | P
| Is the timestep appropriate for the mesh size and calculated velocities (are the associated Courant numbers reasonable)? -max courant of 1-3, min courant of 0.5 - If a coastal boundary condition is used - ideally theta to be set as 0.6 and incrementally increased if errors persist (range of theta 0.6 -1.0) | Best Practice for Flood Risk Analysis and Mapping 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 2.7.1.2 | [5 empty] | P
| Is the source of the roughness coefficients or criteria for selecting default roughness coefficients documented in the report? N:\Texas_2d\BLE_2D_Reference\TWDB\TWDB_ManningsN_Values_v2.xlsx | Automated Engineering 2.2.2.5 Two-Dimensional Analysis 3.4 Energy Loss Coefficients | [5 empty] | P
| Do the roughness coefficients correctly represent existing or proposed conditions? | Guidance for Flood Risk Analysis and Mapping Hydraulics: Two-Dimensional Analysis 3.4 | [5 empty] | F | Curve numbers are unreasonably low. For instance, Mixed forest shows a CN of 10. The minimum CN NRCS recommends is 30. Please revise. | revised
| Are significant hydraulic structures and embankments accounted for? (breaklines along road and bridges, with v-notches to represent culverts, breaklines with 100ft cell spacing in 1sqr mile stream centerlines) | Automated Engineering 2.2.2.9 | [5 empty] | F | Please address comments on the "SAA_comments" Tab | NA
| Does the model account for any significant flow-regulating dams? | [6 empty] | NA
| Are comparison points/lines (2D connections used for gages and profile lines used for effective data and regression) captured and compared against applicable benchmarks? (gage, regression equations, effective BFE, etc.) Note: Make sure 2D connection/profile lines are drawn all the way across 1% floodplain | General Hydraulics Considerations 4.5 Two-Dimensional Analysis 4.0 Calibration of Hydraulic Modes | [5 empty] | P
| Are the boundary conditions established, documented, and reasonable? | SID 61, 90, 93 Two-Dimensional Analysis: 3.5.2 Boundary Conditions | [5 empty] | P
| If applicable, is a stage hydrograph used for the boundary conditions along the coast? Is it set to a reasonable elevation (MHHW) compared to the nearby tidal gages? | [6 empty] | NA
| Peak outflows have been compared to HEC-HMS's peak outflows (lag time within the HEC-HMS model needs to be updated based on timing of the modeled HEC-RAS flood wave) | SID 61, 90, 93 Two-Dimensional Analysis 4.0 Calibration of Hydraulic Modes | [5 empty] | NA | RAS mapper was used for rain on grid preciptiation. |  |  | NA | RAS mapper was used for rain on grid preciptiation.
| If applicable, is the transfer line between this model and a downstream model well away from any boundary condition effects? | SID 61, 90, 93 | [5 empty] | P
| Are the initial conditions and final conditions reasonable? | Hydraulics: Two-Dimensional Analysis 3.5.1; General Hydraulic Considerations 9.5 | [5 empty] | P |  |  |  | P
| Is the mass balance/volume conservation reasonable? A percent error less than or equal to 1% would be ideal however, values of 2-3% can be acceptable (i.e. rain on grid). Percent error values greater than 3% indicate that there are major problems with the model | TUFLOW User's Manual, Table 14-1 | [5 empty] | P |  |  |  | P
| Are all water-surface elvation convergence warning messages acceptable per computation tolerances? | [10 empty] | P
| Has the Courant Number been calculated per the 2D equation used? Does the Courant Number justify the 2D cell size and computation time step? | Best Practices 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 2.7.1.2 | [9 empty] | P
| Was the model simulation long enough to pass the entire hydrograph(s) through the model? Are the hydrographs reasonable when compared to the other return periods? The shapes should be similar, and hydrographs from different events should not intersect unless there is an engineering reason. Peak flows from a lower return period event should not be higher than a higher return period event. | SID 61, 90, 93 | [5 empty] | P |  |  |  | P
| Check to make sure the computed maximum depth, WSEL, and velocity values are not from numerical surge (i.e.beginning of model). | Engineering Judgement | [5 empty] | P |  |  |  | P
| Where applicable, have USGS gage rating curve(s) been used to verify model results? | Best Practices 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 2.7 | [5 empty] | NA | No USGS gage rating curves available |  |  | NA | No USGS gage rating curves available
| Has a profile through the enhancement reach been cut in RAS Mapper to review WSEL profiles? Have instances of significant crossing profiles or adverse slopes been investigated for modeling errors? | Guidance for Flood Risk Analysis and Mapping General Hydraulic Considerations. Section 9.8 | [5 empty] | P |  |  |  | P
| Are both the "hydrograph output interval" and "mapping output interval" set at a reasonable interval to capture peak flows within the model? Hydrograph Output Interval does not significantly increase the DSS file size for a purely 2D model (DSS entries wlll be created for 2D connections and boundary conditions, but there are not as many of those as there would be cross sections in a 1D model), so this can be relatively high resolution. For large models, the Mapping Output Interval will have a very large effect on the .hdf's file size and will not affect the "WSE (Max)" raster value. While it may be helpful to have this value set fairly low during model development, dialing this back for submittal (or at least for return periods other then the 1%) can save significant amounts of disk space. | Engineering Judgement | [5 empty] | P |  |  |  | P
| Have instances of model instabilities at the beginning of the simulation due to initial wetting of a dry grid been addressed? Should a initial condition (wet start) be used? | Engineering Judgement | [5 empty] | P |  |  |  | P
| Have instances of significant crossing profiles or adverse slopes been investigated for modeling errors? | Automated Engineering 2.2.2.12; General Hydraulic Considerations 9.3 | [5 empty] | P |  |  |  | P
| Have sufficient v-notch breaklines been added to assure flow is not being restricted upstream? | SID 61, 90, 93 | [5 empty] | P |  |  |  | P
| Is the correct equation set being used (Diffusion Wave)? | [6 empty] | P |  |  |  | P
| Has the appropriate flow regime been selected (i.e. subcritical flow vs. mixed flow regime)? | [6 empty] | P |  |  |  | P
Mapping Outputs
| Do the boundaries look reasonable? | Automated Engineering 2.3 | [9 empty] | P
| Are WSELs in correct order according to return period? i.e. 0.2% > 1% > 2% > 4% > 10% -If there are inflow hydrographs, check at least one cell in each main channel as well as at least one location with flooding that is driven purely by precipitation -Use automated tool to check 500+ points within the fluvial and pluvial controlled flooding areas to confirm that WSELs increase for higher return period events. | SID 78 | [9 empty] | P
Model Clean-up / File Management
| HEC-RAS Project files: Have all temporary and interim project files been deleted from the model? (*.p##, *.g##, *.u##) | [10 empty] | P
| HEC-RAS Output files: Have all unused output files been deleted from the project directory? (*.O##,*.hyd##, *.c##,*.b##, *.bco##, *.g##.hdf, *.p##.hdf, *.p##.blf, *.IC.O##, *.x##) | [10 empty] | P
| HEC-RAS DSS Output file: Have any unsed model outputs associated with plans no longer in use been deleted from the HEC-DSS Output file? | [10 empty] | P
| HEC-RAS DSS Output file: Do hydrographs for all 7 recurrence interval events (10%, 4%, 2%, 1%, 0.2%, and 1% (+/-)) show up under the "Plot Stage and Flow Hydrographs" option within HEC-RAS? | [10 empty] | P
| Have all old versions of geometries and plans been removed from the tree list within RAS Mapper? | [10 empty] | P
| Have all non-essential shapefiles been removed from RAS Mapper? | [10 empty] | P
| Is there a projection defined within RAS Mapper and is it correct? | [10 empty] | P
| Are the terrain and land cover files correctly associated to the geometry and results layers? | [10 empty] | P
| Have all folders and/or files that are not necessary for viewing results been deleted from the project folder (i.e. shapefiles, Excel documents, etc.)? | [10 empty] | P
| Have all old and non-relevant comments within each unsteady flow plan been removed? | [10 empty] | P
| Can the "computation log file" and "runtime messages" be seen for each plan? | [10 empty] | P
Additional Comments
| Engineering analyses are documented and easily reproducible and include study methods, reasoning for method selection, input data and parameters, sources of data results, and justifications for major changes in computed flood hazard parameters. | SID 61, 186 |  | F | The engineering report is not yet ready |  |  | F | The engineering report is not yet ready |  |  | F | The engineering report is not yet ready
| Model, plans, flows, geometry, etc. names are correct - 1PAC, 1PACPlus, etc. | SID 61, 90, 93 |  | F | Only 1 PAC plan was created |  |  | F | Only 1 PAC plan was created | All the naming convention is revised according to guidance. |  | P
General comments
1 | Please update/verify the highlighted section on the project description
updated
2. Please place a breakline through the top of the pond embankment
can't find any visible opening from google imagery
can't find any visible opening from google imagery
3. Please add a v-notch at the following locations.
V-notch added
V-notch added
V-notch added
| 3. Please check the tie-in between DMF 3 and the upstream and downstream models. |  |  |  |  | Tie-ins are confirmed both U/S and D/S work-areas

## Floodplain Mapping
| 2D BLE Floodplain Mapping QC Checklist | [7 empty] | Pass
| Originator | [6 empty] | Fail
Reviewer
Date of Review:
Originator Response Date:
Review Verification (Completion) Date:
Review S_FLD_HAZ_AR feature class and assure the following checks have been completed to appropriately represent 1 and 0.2% annual chance inundation along effective Zone A and newly mapped flooding sources.
QC Check Number | QC Check and Description | Review Considerations | Technical Review |  | Originator Response | QA Verification
|  |  | Pass / Fail / NA | QC Review Comment |  | Pass / Fail / NA | Comment
1 | S_FLD_HAZ_AR represented across the watershed or study footprint includes mapping for new study streams and effective flooding sources | Review S_FLD_HAZ_AR feature class against study streams (e.g. 1 square mile streams), effective data (e.g. NFHL, CNMS, FIRMs, Q3), and work area boundary to assess disconnects and/or voids
2 | S_FLD_HAZ_AR Fld_Zone attributed appropriately based as either Zone A from the 1% or Shaded X from the 0.2% | All features should be attributed as either A, X, or TBD (or other attribute indicating need for additional assessment [e.g. flooding upstream of a road but not modeled with a breakline and not accounted for through input/effective flooding sources])
4 | S_FLD_HAZ_AR spatially ties-in to valid effective Zone AE boundaries | Use NFHL or CNMS database to identify effective valid Zone AE areas and ensure Zones A and Shaded X polygons spatially tie-in to valid AE and X boundaries
5 | S_FLD_HAZ_AR spatially ties-in at upstream and/or downstream models where multiple hydraulic models were used for a project footprint | Check for significant differences in upstream and/or downstream work area(s) mapping that may require engineering input and resolution
6 | S_FLD_HAZ_AR only extends to model boundary at inflow and outflow locations | Ensure S_FLD_HAZ_AR contained within respective model area except at inflow and outflow locations (rain on grid watershed area should not clip a tributary flood hazard polygon
7 | Zone A features aligned with 1% WSEL/Depth grid extent | Pan across work area to visually inspect agreement between SFHA and 1% WSEL/Depth grid…these should be aligned
8 | Shaded X features align with 0.2% WSEL/Depth grid extent | Pan across work area to visually inspect agreement between Shaded X and 0.2% WSEL/Depth grid…these should be aligned
9 | New SFHA developed for study streams where the reach drains greater than 1 square mile and has continuous BLE 1% depths greater than or equal to 1 foot | Pan across the Zone A polygons to remove any tributaries that do no have a 1sq mi/CNMS stream and or 1ft of depth. Remove any polygons upstream if there is a break in 1ft of depth.
10 | S_FLD_HAZ_AR free of inconsistencies in floodplain boundary polygons (no triangulation artifacts, stair-stepping from raster, impractical termination, etc) | Pan across work area to visually inspect for anomalies
11 | S_FLD_HAZ_AR contains flood hazard polygons for a flooding source that may be disconnected by roads or other terrain obstruction higher than the correspondng water surface elevation grid | Compare S_FLD_HAZ_AR feature class against raw 1 and/or 0.2% WSEL/Depth grids for missing areas where flooding is disconnected by roads or embankments (offset breaklines may be used to ensure engineering intent to connect flows)
12 | Holes in S_FLD_HAZ_AR less than 15,625 square feet have been filled (size represents minimum visibility on 500-scale panel) | Check to ensure small holes not visibly discernable on 500-scale panels within the contiguous S_FLD_HAZ_AR are filled (use GIS processing [e.g. Erase] to evaluate holes and area) (note if an alternative fill size was used and assurance no adverse impact to structures)
13 | S_FLD_HAZ_AR topology enforced | FIRM database topology rules should be enforced (i.e. no gaps in between adjacent polygon features [exception: areas larger than 1 acre intended to be Unshaded X]; No overlapping polygons)

## Depth and Analysis Grids
Depth and Analysis Grids Checklist / Quality Record
Study Name |  | Reviewer |  |  |  | Date
Example Study |  | Example Reviewer |  |  |  | 2552537
ID | Raster Products Compliance Check | Guidance Location | Pass / Fail | Reviewer Comments | Originator Disposition | Originator Comments | Approver Verification (Initials) | Approver Comments
1 | Raster datasets have proper naming conventions.
2 | Raster data exists to the full extent of the underlying modeling, and uses same terrain/bathymetry.
3 | All Rasters are 32-bit Floating Point, share the same spatial reference, origin, rotation, and cell size resolution, values rounded to 0.1 units.
4 | All rasters use the same coordinate system as the source terrain and hydrualic models.
5 | Water surface elevation rasters reference the North American Vertical Datum of 1988 (NAVD88, Feet).
6 | Grid cell size is based on the density of the ground elevation data used and the appropriate precision that can be supported by the data.
7 | Grid data is clipped at the project area boundary.
8 | Negative elevations have been removed from all depth grids.
9 | The pixels of all the grids are aligned (raster snapping).
10 | All grids should be aligned (raster snapping)
11 | Riverine depth and water surface grids for new studies include the 10%, 4% 2%, 1%, 0.2%, and 1% Plus annual chance flood events (unless scoped for less).
12 | For the 1% annual chance depth grid, the depth grid covers the horizontal extent of the respective 1% annual chance floodplain.
13 | For the 0.2% annual chance depth grid, the depth grid covers the horizontal extent of the respective 0.2% annual chance floodplain.
14 | Depth grids of the 10%, 4% 2% (or other lower frequencies) are contained within the 1% annual chance floodplain.
15 | The data value ranges for all depth grids appear reasonable.
17 | Supporting documentation is included for locations where the flood depth grid has large gaps due to issues with the underlying terrain data.
19 | Ensure values for more frequent events are smaller in value than less frequent Depth Grids in corresponding cells (for example, 10% < 4% < 2% < 1% < than 0.2%, etc).
20 | Depth grids should be compatible with mapped AO and AH zones shown on the FIRM for 1%.
24 | Water Surface Elevations in the WSE grids reflect proposed regulatory elevations, including backwater at confluences.
25 | Water surface grid has been limited to the extent of the appropriate annual chance flood event.
27 | The data value ranges for all WSEL grids are reasonable.
28 | Percent Annual Chance Raster values represent the percent annual chance of flooding for locations along the flooding source within the 0.2% chance floodplain, with values between .2 and 10.
29 | The percent chance grids are reported in percentages (i.e. 4.6% = "4.6" in the grid instead of "0.046").
30 | Percent annual chance grid values were calculated using the correct methodology/equation based on the final delivered grids (refer to FEMA's "Flood Depth and Analysis Grids - Guidance for Flood Risk Analysis and Mapping" document, May 2014).
31 | Percent annual chance grid values should closely correspond to edges of associated depth grids.
32 | The Percent Annual Chance grid's values are rounded to the nearest tenth of a unit.
33 | Percent 30 year chance grids have values ranging from 0 to 100.
34 | Spot checks have been performed comparing 30 year chance grid and the most recent percent annual chance grid.
35 | The Percent 30-yr Chance grid's values are reported in percentages (i.e. 10.6% = "10.6" in the grid instead of "0.106").
36 | The Percent 30-yr Chance grid's values are rounded to the nearest tenth of a unit.
37 | The Percent 30-yr Chance grid is created using the same terrain source as those used to produce the WSE and Depth grids .
38 | The Percent 30-yr Chance grid was calculated using the following equation, with the Percent Annual Chance grid as input ("p"): Pct30yrChance = 1 - (1-p)^30.
Other Comments
Formulas:
Date = '[1]Detail and Sign-Off'!$G5

## Changes Since Last FIRM
Changes Since Last FIRM Checklist / Quality Record
| Study Name |  | Reviewer |  |  |  | Date
| Example Study |  | Example Reviewer |  |  |  | 2552537
| ID | Changes Since Last FIRM Compliance Check | Guidance Location | Pass / Fail | Reviewer Comments | Originator Disposition | Originator Comments | Approver Verification (Initials) | Approver Comments
S_CSLF_Ar | 1 | Uniform units of measure are used.
| 2 | Final S_CSLF_Ar created after new FIRM database has passed QRs 1 and 2.
| 3 | The S_CSLF_Ar polygon feature class depicts the changes in spatial extents between the previous and newly revised FIRMs.
| 4 | National Flood Hazard Layer (or other comparable dataset with all effective FIRMs and LOMRs incorporated) is used as the source of effective flood hazard area. Q3 data has NOT been used to represent the previous FIRM (unless Regional approval obtained due to lack of other data).
| 5 | CSLF is subdivided (unioned) by Source (Pre- and New-SFHA), Hydro/Hydra model, political boundaries, and contributing engineering factors when available.
| 6 | Where CSLF polygon spans FIRM panels that have different effective dates, those polygons have been divided at the panel boundaries.
| 7 | Contributing engineering factors assigned as "Unknown" are used appropriately (if applicable).
| 8 | Areas that were previously mapped as unshaded Zone X in the effective flood hazard areas and that remain as unshaded Zone X in the new flood hazard areas shall not be delivered as part of CSLF data.
| 9 | L_Source_Cit table is attributed for Previous and New Flood Hazards.
| 10 | S_CSLF_Ar is clipped to the project footprint (S_FRD_Proj_Ar) or at the limits of the new study, whichever is greatest.
| 11 | Where the limits of study extend beyond the watershed boundary, the S_CSLF_Ar has NOT been clipped to the watershed boundary.
Check that following CSLF datasets exist, and that their fields are properly attributed, have proper null values (required vs. as appropriate), proper domain coding, and consistent unit measure.
| 12 | CSLF_ID
CNMS_ID
AREA_SF
PRE_ZONE
PRE_ZONEST
PRE_MODEL
PRE_TOPO
PRE_SRCCIT
NEW_ZONE
NEW_ZONEST
NEW_MODEL
NEW_TOPO
NEW_SRCCIT
PEAKDSCHG [Enhanced]
MDLMETHODS [Enhanced]
FLD_CTRLCHG [Enhanced]
HYDSTRCHG [Enhanced]
TOPOCHG [Enhanced]
SEDCHG [Enhanced]
EROSIONCHG [Enhanced]
CHANNELCHG [Enhanced]
LEVEECHG [Enhanced]
RUNOFFCHG [Enhanced]
DUNECHG [Enhanced]
OTHCHG [Enhanced]
SFHACHG
NONSFHACHG
FLDWYCHG
CHHACHG
CID
HUC8_CODE
CASE_NO
VERSION_ID
SOURCE_CIT
STRUCTURES [Enhanced]
POPULATION [Enhanced]
| 13 | CNMS_ID matches CNMS_ID value in official CNMS database
L_CSLF_Summary | 14 | CSLFSUMMID
POL_NAME1
LOCATION
AREA_SM
AREA_INCR
AREA_DECR
AREA_NET
HUC8_CODE
CASE_NO
VERSION_ID
POP_INCR [Enhanced]
POP_DECR [Enhanced]
POP_NET [Enhanced]
BLDG_INCR [Enhanced]
BLDG_DECR [Enhanced]
BLDG_NET [Enhanced]
| 15 | For those project total summary records, the CSLFSUMMID field should be populated with the FEMA Case Number.
| 16 | If CSLF polygons extend outside S_FRD_Proj_Ar, only the portion within the project footprint should be aggregated in the L_CSLF_Summary table.
| 17 | L_CSLF_Summary table only includes summaries for the portion of each community that lies within the project boundary. The aggregated values should represent the totals for portions of the communities in the project area.
| 18 | L_CSLF_Summary table contains up to four records for each community and the project total summary with a unique CID in the project area. The four records are for the SFHA, non-SFHA, Floodway, and Coastal High Hazard areas for each community.
FRD_Model_Info | 19 | MDL_NFO_ID
STD_NFO_ID
EFF_DATE
ANLYS_DATE
STUDY_TYP
HYDRO_MDL
HYDRA_MDL
SURGE_MDL
WAVEHT_MDL
RUNUP_MDL
HUC8_CODE
CASE_NO
VERSION_ID
| 20 | FRD_Model_Info table is populated with model information referenced from S_CSLF_Ar.
| 21 | FRD_Model_Info table has one record for each unique combination of models used to create the SFHAs that were used to develop S_CSLF_Ar.
FRD_Study_Info | 22 | STD_NFO_ID
DFIRM_ID
STUDY_PRE
STUDY_NM
STATE_NM
CNTY_NM
JURIS_TYP
H_DATUM
V_DATUM
PROJECTION
PROJ_ZONE
PROJ_UNIT
CASE_NO
VERSION_ID
| 23 | FRD_Study_Info table is populated with FIRM database information in areas where S_CSLF_Ar is produced.
Other Comments
Formulas:
Date = '[1]Detail and Sign-Off'!$G5