## Sign off-QC Stamp
ATKINS QUALITY REVIEW CHECKLIST SIGN OFF FORM
Study / Stream Name | Middle Colorado BLE
Deliverable
MIP Case #:
PM: | Seth Ahrens
QC REVIEW ACTIVITY
Ready for QC | *Originator / Date :
QC Review | *Reviewer / Date : | Avi Eskenazi 4/22/2024
Changes Made | *Originator/ Date :
QC Verification | *QC Reviewer:
Date:
PQM Approval | *QA:
Date:

## Attribute Checks v1
Study |  |  | Middle Colorado BLE
Reviewer |  |  | Avi Eskenazi
Review Date |  |  | 4/22/2024
Spatial Analyst
Response Date
Line No. | Feature Dataset | Feature Class | Field | Field Type¹ | Pass/ Fail | Reviewer Comment | Response Comment
1 | BASE_DATASET | S_POL_AR | DFIRM_ID |  | P
2 |  |  | VERSION_ID |  | P
3 |  |  | POL_AR_ID |  | P
4 |  |  | POL_NAME1 |  | P
5 |  |  | POL_NAME2 |  | P
6 |  |  | POL_NAME3 |  | P
7 |  |  | CO_FIPS |  | P
8 |  |  | ST_FIPS |  | P
9 |  |  | COMM_NO |  | P
10 |  |  | CID |  | P
11 |  |  | ANI_TF |  | P
12 |  |  | ANI_FIRM |  | P
13 |  |  | COM_NFO_ID |  | P
14 |  |  | SOURCE_CIT |  | P
15 |  | S_HUC_AR | HUC_CODE |  | P
16 |  |  | HUC_NAME |  | P
17 |  |  | DIGITS |  | P
18 |  |  | CASE_NO |  | P
19 |  |  | VERSION_ID |  | P
20 |  |  | SOURCE_CIT |  | P
21 | EBFE_DATASET | SUBBASINS | EST_ID |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
22 |  |  | VERSION_ID |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
23 |  |  | E_SUBAS_ID |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
24 |  |  | E_SUBAS_NM |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
25 |  |  | HUC8_CODE |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
26 |  |  | WTR_NM | Hidden | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
27 |  |  | BASIN_DESC | Hidden | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
28 |  |  | EST_AREA |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
29 |  |  | AREA_UNIT |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
30 |  |  | NODE_ID | Hidden | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
31 |  |  | BASIN_TYP | Hidden | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
32 |  |  | SOURCE_CIT |  | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
33 |  |  | US_1 | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
34 |  |  | US_2 | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
35 |  |  | US_3 | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
36 |  |  | US_4 | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
37 |  |  | DS_1 | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
38 |  |  | PRECIP_IN | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
39 |  |  | MAINCHSLP | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
40 |  |  | E_Q_10PCT | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
41 |  |  | E_Q_04PCT | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
42 |  |  | E_Q_02PCT | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
43 |  |  | E_Q_01PCT | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
44 |  |  | E_Q_01PLUS | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
45 |  |  | E_Q_01MIN | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
46 |  |  | E_Q_0_2PCT | New | N/A | Not submitted - Subbasins are not required for 2D modeling areas.
47 |  | XS_1D | EST_ID |  | N/A | Not submitted - XS are not required for 2D modeling areas.
48 |  |  | VERSION_ID |  | N/A | Not submitted - XS are not required for 2D modeling areas.
49 |  |  | XS_LN_ID |  | N/A | Not submitted - XS are not required for 2D modeling areas.
50 |  |  | WTR_NM |  | N/A | Not submitted - XS are not required for 2D modeling areas.
51 |  |  | STREAM_STN |  | N/A | Not submitted - XS are not required for 2D modeling areas.
52 |  |  | START_ID |  | N/A | Not submitted - XS are not required for 2D modeling areas.
53 |  |  | XS_LTR | Hidden | N/A | Not submitted - XS are not required for 2D modeling areas.
54 |  |  | XS_LN_TYP |  | N/A | Not submitted - XS are not required for 2D modeling areas.
55 |  |  | E_WSE_1PCT |  | N/A | Not submitted - XS are not required for 2D modeling areas.
56 |  |  | STRMBED_EL | Hidden | N/A | Not submitted - XS are not required for 2D modeling areas.
57 |  |  | LEN_UNIT | Hidden | N/A | Not submitted - XS are not required for 2D modeling areas.
58 |  |  | V_DATUM |  | N/A | Not submitted - XS are not required for 2D modeling areas.
59 |  |  | PROFXS_TXT |  | N/A | Not submitted - XS are not required for 2D modeling areas.
60 |  |  | MODEL_ID |  | N/A | Not submitted - XS are not required for 2D modeling areas.
61 |  |  | SEQ |  | N/A | Not submitted - XS are not required for 2D modeling areas.
62 |  |  | SOURCE_CIT |  | N/A | Not submitted - XS are not required for 2D modeling areas.
63 |  |  | E_WSE_10PC | New | N/A | Not submitted - XS are not required for 2D modeling areas.
64 |  |  | E_WSE_4PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
65 |  |  | E_WSE_2PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
66 |  |  | E_WSE_1PLU | New | N/A | Not submitted - XS are not required for 2D modeling areas.
67 |  |  | E_WSE_1MIN | New | N/A | Not submitted - XS are not required for 2D modeling areas.
68 |  |  | E_WSE_0_2P | New | N/A | Not submitted - XS are not required for 2D modeling areas.
69 |  |  | E_Q_10PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
70 |  |  | E_Q_04PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
71 |  |  | E_Q_02PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
72 |  |  | E_1_02PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
73 |  |  | E_Q_01PLUS | New | N/A | Not submitted - XS are not required for 2D modeling areas.
74 |  |  | E_Q_01MIN | New | N/A | Not submitted - XS are not required for 2D modeling areas.
75 |  |  | E_Q_0_2PCT | New | N/A | Not submitted - XS are not required for 2D modeling areas.
76 |  | BFE_2D | EST_ID |  | P
77 |  |  | VERSION_ID |  | P
78 |  |  | EBFE_LN_ID |  | P
79 |  |  | BLELEV1PCT |  | P
80 |  |  | LEN_UNIT |  | F | Should be populated with "Feet" | Corrected
81 |  |  | V_DATUM |  | F | Should be populated with "NAVD88" | Corrected
82 |  |  | SOURCE_CIT |  | P
83 |  |  | BFE_LN_TYP | New | P
84 |  | WTR_LN | EST_ID |  | P
85 |  |  | VERSION_ID |  | P
86 |  |  | WTR_LN_ID |  | F | Duplicates and extra leading zeros - give each feature a unique identifier | Corrected
87 |  |  | WTR_NM |  | P
88 |  |  | SHOWN_FIRM | Hidden | P
89 |  |  | SHOWN_INDX | Hidden | P
90 |  |  | SOURCE_CIT |  | P
91 |  | WTR_AR | EST_ID |  | F | Drop the "_BLE" to match with WTR_LN | Corrected
92 |  |  | VERSION_ID |  | F | Change to "BLE_072021" | Corrected
93 |  |  | WTR_AR_ID |  | F | Give a unique identifier to each feature with leading zero's | Corrected
94 |  |  | WTR_NM |  | P
95 |  |  | SHOWN_FIRM | Hidden | P
96 |  |  | SHOWN_INDX | Hidden | P
97 |  |  | SOURCE_CIT |  | P
98 |  | DTL_STUD_LN | DTL_LN_ID
99 |  |  | VERSION_ID
100 |  |  | LOMR_ID | Hidden
101 |  |  | EFF_DATE
102 |  |  | CASE_NO | Hidden
103 |  |  | SCALE | Hidden
104 |  |  | SOURCE_CIT
105 |  |  | STATUS | Hidden
106 |  |  | FIRM_PAN | New
107 |  |  | TYPE | New
108 |  |  | CD_YN | New
109 |  |  | CD_POC | New
110 |  |  | CD_ADD1 | New
111 |  |  | CD_ADD2 | New
112 |  |  | CD_CTY | New
113 |  |  | CD_STATE | New
114 |  |  | CD_ZIP | New
115 |  |  | CD_PHONE | New
116 |  |  | CD_EMAIL | New
117 |  | DTL_STUD_AR | DTL_AR_ID |  | P
118 |  |  | VERSION_ID |  | P
119 |  |  | LOMR_ID | Hidden | P
120 |  |  | EFF_DATE |  | P
121 |  |  | CASE_NO | Hidden | P
122 |  |  | SCALE | Hidden | P
123 |  |  | SOURCE_CIT |  | F | Should be populated with appropriate citation | Corrected
124 |  |  | STATUS | Hidden | P
125 |  |  | FIRM_PAN | New | P
126 |  |  | TYPE | New | P
127 |  |  | CD_YN | New | F | Should be NP | Corrected
128 |  |  | CD_POC | New | P
129 |  |  | CD_ADD1 | New | P
130 |  |  | CD_ADD2 | New | P
131 |  |  | CD_CTY | New | P
132 |  |  | CD_STATE | New | P
133 |  |  | CD_ZIP | New | P
134 |  |  | CD_PHONE | New | P
135 |  |  | CD_EMAIL | New | P
136 |  | FLD_HAZ_AR | EST_ID |  | F | Add "_BLE" | Corrected
137 |  |  | VERSION_ID |  | P
138 |  |  | EST_AR_ID |  | P
139 |  |  | STUDY_TYP | Hidden | P
140 |  |  | FLD_ZONE | Hidden | P
141 |  |  | ZONE_SUBTY |  | P
142 |  |  | SFHA_TF | Hidden | P
143 |  |  | STATIC_BFE | Hidden | P
144 |  |  | V_DATUM |  | P
145 |  |  | DEPTH | Hidden | P
146 |  |  | LEN_UNIT |  | P
147 |  |  | VELOCITY | Hidden | P
148 |  |  | VEL_UNIT | Hidden | P
149 |  |  | AR_REVERT | Hidden | P
150 |  |  | AR_SUBTRV | Hidden | P
151 |  |  | BFE_REVERT | Hidden | P
152 |  |  | DEP_REVERT | Hidden | P
153 |  |  | DUAL_ZONE | Hidden | P
154 |  |  | SOURCE_CIT |  | P
155 |  |  | EST_RISK | New | P
156 |  | TENPCT_FP | EST_ID |  | P
157 |  |  | VERSION_ID |  | P
158 |  |  | EST_AR_ID |  | F | Numbers are not in sequential order | Corrected
159 |  |  | STUDY_TYP | Hidden | P
160 |  |  | FLD_ZONE | Hidden | P
161 |  |  | ZONE_SUBTY |  | F | Should be "NP" | Corrected
162 |  |  | SFHA_TF | Hidden | P
163 |  |  | STATIC_BFE | Hidden | P
164 |  |  | V_DATUM |  | P
165 |  |  | DEPTH | Hidden | P
166 |  |  | LEN_UNIT |  | P
167 |  |  | VELOCITY | Hidden | P
168 |  |  | VEL_UNIT | Hidden | P
169 |  |  | AR_REVERT | Hidden | P
170 |  |  | AR_SUBTRV | Hidden | P
171 |  |  | BFE_REVERT | Hidden | P
172 |  |  | DEP_REVERT | Hidden | P
173 |  |  | DUAL_ZONE | Hidden | P
174 |  |  | SOURCE_CIT |  | P
175 |  |  | EST_RISK | New | P
* |  |  | area_acres |  | F | Remove field | Corrected
176 | MIT-HAZ_DATASETS | S_AOMI_PT | AOMI_ID |  | P
177 |  |  | CID |  | P
178 |  |  | POL_NAME1 |  | P
179 |  |  | AOMI_CLASS |  | P
180 |  |  | AOMI_TYP |  | P
181 |  |  | AOMI_CAT |  | P
182 |  |  | AOMI_SRCE |  | P
183 |  |  | AOMI_INFO |  | P
184 |  |  | NOTES |  | P
185 |  |  | HUC8_CODE |  | P
186 |  |  | CASE_NO |  | P
187 |  |  | VERSION_ID |  | P
188 |  |  | SOURCE_CIT |  | P
189 |  | S_AOMI_AR | AOMI_ID |  | P
190 |  |  | CID |  | P
191 |  |  | POL_NAME1 |  | P
192 |  |  | AOMI_CLASS |  | P
193 |  |  | AOMI_TYP |  | P
194 |  |  | AOMI_INFO |  | P
195 |  |  | HUC8_CODE |  | P
196 |  |  | CASE_NO |  | P
197 |  |  | VERSION_ID |  | P
198 |  |  | SOURCE_CIT |  | P
199 |  | S_FRAC_AR | CEN_BLK_ID |  | P
200 |  |  | ARV_BG_TOT |  | P
201 |  |  | ARV_CN_TOT |  | P
202 |  |  | HAZARD_TYP | Hidden | P
203 |  |  | SCENAR_ID | Hidden | P
204 |  |  | TOT_LOSS10 | Hidden | P
205 |  |  | BL_TOT10 | Hidden | P
206 |  |  | CL_TOT10 | Hidden | P
207 |  |  | TOT_LOSS04 | Hidden | P
208 |  |  | BL_TOT04 | Hidden | P
209 |  |  | CL_TOT04 | Hidden | P
210 |  |  | TOT_LOSS02 | Hidden | P
211 |  |  | BL_TOT02 | Hidden | P
212 |  |  | CL_TOT02 | Hidden | P
213 |  |  | TOT_LOSS01 |  | P
214 |  |  | BL_TOT01 |  | P
215 |  |  | CL_TOT01 |  | P
216 |  |  | TOT_LSS0_2 | Hidden | P
217 |  |  | BL_TOT0_2 | Hidden | P
218 |  |  | CL_TOT0_2 | Hidden | P
219 |  |  | TOT_LSSAAL | Hidden | P
220 |  |  | BL_TOTAAL | Hidden | P
221 |  |  | CL_TOTAAL | Hidden | P
222 |  |  | HUC8_CODE |  | P
223 |  |  | CASE_NO |  | P
224 |  |  | VERSION_ID |  | P
225 |  |  | SOURCE_CIT |  | P
226 | CNMS_ DATASET | S_STUDIES_LN
227 |  | S_UNMAPPED_LN
228 | GRIDS | BLE_WSE01PCT
229 |  | BLE_WSE0_2PCT
230 |  | BLE_DEP01PCT
231 |  | BLE_DEP0_2PCT
232 | L_SOURCE_CIT | SOURCE_CIT |  |  | P
233 |  | DFIRM_ID |  |  | P
234 |  | CITATION |  |  | P
235 |  | PUBLISHER |  |  | P
236 |  | TITLE |  |  | P
237 |  | AUTHOR |  |  | P
238 |  | PUB_PLACE |  |  | P
239 |  | PUB_DATE |  |  | P
240 |  | WEBLINK |  |  | P
241 |  | SRC_SCALE |  |  | P
242 |  | MEDIA |  |  | P
243 |  | CASE_NO |  |  | P
244 |  | VERSION_ID |  |  | P
¹ | "Hidden" fields are those not visible to the public in the Region 6 viewer at https://webapps.usgs.gov/infrm/estbfe/.
"New" fields are created for the BLE database and are not described in the Technical References. Refer to the Base Level Engineering, Region 6 Submittal Guidance instead.

## Spatial Checks v1
Study |  | Middle Colorado BLE
Reviewer |  | Avi Eskenazi
Review Date |  | 4/22/2024
Spatial Analyst
Response Date
Line No. | Feature Dataset | Feature Class | Pass/ Fail | Topology Checks² | Reviewer Comment | Response Comment
1 | BASE_DATASET | S_POL_AR
2 |  | S_HUC_AR
3 | EBFE_DATASET | SUBBASINS
4 |  | XS_1D
5 |  | BFE_2D
6 |  | WTR_LN
7 |  | WTR_AR
8 |  | DTL_STUD_LN
9 |  | DTL_STUD_AR
10 |  | FLD_HAZ_AR
11 |  | 10PCT_FP
12 | MIT-HAZ_DATASET | S_AOMI_PT |  |  |  |  | `
13 |  | S_AOMI_AR
14 |  | S_FRAC_AR
15 | CNMS_DATASET | S_STUDIES_LN
16 |  | S_UNMAPPED_LN
17 | GRIDS | BLE_WSE_01PCT
18 |  | BLE_WSE_0_2PCT |  |  | Small Zone X polygon that does not have raster cells, location is in ITR Comments shapfile named MiddleCO_QC, FID 37
19 |  | BLE_DEP_01PCT
20 |  | BLE_DEP_0_2PCT
² | The following topology rules are listed in Base Level Engineering, Region 6 Submittal Guidance,Version 6, July 2021, page 30.

## Sheet1
Middle Colorado Raster Check | Rachel Forster | 20240423
| Jim Ned | Middle Colorado
100 year | Incorrect (It looks like the Jim Ned side of things are pulling from the 10 year 802 A3) | Correct
500 year | Incorrect (Currently using 100 year from Middle Colorado side ) | Correct