## Instructions
Engineering Files QC Checklists
1 | Please insert Study Name on Sign Off tab. This will automatically populate the remainder of the spreadsheets. Please insert the Feme Case No in front of the document name, and save the file with that name on your network.
2 | Please enter name (and initials) on Sign Off tab. If additional lines are required, copy the last line and insert below. As you complete the spreadsheets, you will need only to insert your initials.
3 | Please enter the name of the basin, stream reach, or coastal beach that you are reviewing in the appropriate space at the top of the sheet. The first of each set of forms requires names and dates to be added at the top of each column.
4 | Technical Review refers to the final review of work. This will be accomplished by an independent team of subject matter experts. Work should be considered as complete and ready to submit when submitted to this team. Be certain to add initials to the form.
5 | QA Verification refers to the determination that the work is ready to deliver. It is accomplished by a representative of the QA Manager. This review is cursory and involves review of records and spot checks of errors that appear to be systemic. The purpose of this review is to first ensure that all errors have been corrected, files are ready to be submitted and all records are ready for archival. Secondly, the review will focus on whether errors are systemic (requiring adjustment to procedure, or perhaps further training) or random (requiring review of schedules, budgets, etc.) Be certain to add initials to the form.
6 | Should there be a requirement to review data a second (or more) time, simply copy the appropriate columns and insert them to the right of the original review columns.
7 | A separate worksheet may be required for each basin, stream reach or model, and coastal beach. In this case copy the worksheet and insert into the workbook in the proper sequential order. Please label the tab with the basin name, stream reach or model number(s), or beach to make use of the workbook easier.
8 | Please indicate status of each item by responding P (Pass), F (Fail), NA (Not applicable).
9 | When your review is complete and you are satisfied with the quality of the work, please sign a hard copy of the sign off sheet. Please be certain to retain the signed sheet with other project documents and be sure the next reviewer knows where to locate it. QA Verification reviewer, please scan the sign off sheet and add to the document files for the project.

## Sign off-QC Stamp
ATKINS QUALITY REVIEW CHECKLIST SIGN OFF FORM
Study / Stream Name | Pecan Bayou - 0704_A5
Deliverable
MIP Case #:
PM: | Seth Ahrens
QC REVIEW ACTIVITY
Ready for QC | *Originator / Date : | Mark Jendrisak
2022-05-09
*By signing this you are certifying that you have performed a self check on each FIRM Panel using the checks within this checklist
QC Review | *Reviewer / Date : | Sravan Krovidi
2022-05-12
*By signing this you are certifying that you have performed a self check on each FIRM Panel using the checks within this checklist
Changes Made | *Originator/ Date : | Mark Jendrisak
2022-05-18
*By signing this you are certifying that you have corrected each QC citation and not introduced additional errors
QC Verification | *QC Reviewer: | Sravan Krovidi
| Date: | 2022-05-27
*By signing this you are certifying that each QC citation has been resolved
PQM Approval | *QA: | Vikram Shrivastava
| Date: | 2022-05-27
*By signing this you are certifying that, to the best of your ability, all project requirements have been met and all QC citations were properly resolved.

## Model Geometry
Hydraulics
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Pecan Bayou - 0705_A6 |  |  |  |  | Sravan Krovidi |  | 2022-05-12
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
RAS Mapper Setup
1 | Is the model projection correct? |  | Pass
2 | Does the terrain and model projections match |  | Pass
3 | Is the model geometry linked to Terrain, Land Cover, and Infiltration layers |  | Pass
4 | Do the model results show Terrain, Landcover and Infiltration layers linked |  | Pass
2D Mesh
1 | Does the digital terrain model input for the 2D model cover the entire 2D study area? |  | Pass
2 | Is the 2D mesh reasonably sized to limit cell count and obtain reasonable velocities? (Generally 200 ft and refined where needed) |  | Fail | suggest to remove sharp angles in refinement region buffers for better cell alignment | Agree, Changes Made | Re-Applied buffer to refinement region to reduce sharp angles. | SK | OK
3 | Is the model domain delineated properly to capture all contributing flows through rain-on-grid or external hydrograph? |  | Pass
4 | Are there any 2D mesh errors? |  | Pass
Breaklines
5 | Are breaklines sufficiently detailed to capture features (thalweg, roads, banks, berms, etc.)? |  | Fail | need to add breaklines along dams and spillways (ex: near breakline #133, #134, #141 etc); add for railroads as well | Agree, Changes Made | Added Breaklines as specified dams and for railroads. Reviewed breaklines at all dams. | SK | OK
6 | Are breaklines consistent with the terrain data? |  | Pass
7 | Have sufficient offset breaklines been added to assure flow is not being restricted upstream? |  | Pass
8 | Are breaklines added such that the grid is not leaking. |  | Fail | avoid overlapping breaklines (between refinement regions and regular breaklines - ex: regions #122/ 54, #122 & #98 etc.) | Agree, Changes Made | Reviewed overlapping breaklines, and adjusted. | SK | double check the overlapping regions to ensure correct mannings n value is assigned
Manning's n
9 | Is the source of the roughness coefficients or criteria for selecting default roughness coefficients documented? |  | Pass
10 | Are channel Manning's n values reasonable? Has 50pct plan been ran to delineated the channel region Polygon override for manning's n Values? |  | Fail | the buffer seems to be wider in general, also the channel n-value used (0.03) seem low; please consider smaller buffer and /or higher n-value; locations where buffer is close to road breakline, its modified and the n-value may not be represented correctly; please review and justify in general | Agree, Changes Made | Buffer is 5ft on each side of refinement region, and updated Mannings N to 0.04. Updated N values at roadway crossings to reflect channel N values. This was done by adding roadway crossings to classification polygons. | SK | OK
11 | Is the Manning's n dataset associated with the geometry file? |  | Pass
Infiltration Layer
12 | Are Curve Numbers (CN) values reasonable, and sufficiently documented? |  | Fail | CN values don’t correspond well with TR-55; suggest to document the source if its not TR-55 otherwise update the values used in model | Other, See Orignator Comments | Agree that it should vary with Soil Type, utilized direct flow process doc. | SK
13 | Are the Curve Numbers reasonable? |  | Fail | CN values used in model do not vary with soil group; also they should vary with the cover type | Other, See Orignator Comments | Agree that it should vary with Soil Type, utilized direct flow process doc. | SK
14 | Has the Infiltration Layer been correctly assigned to the geometry |  | Pass
Hydraulics Structures (including dams)
15 | Has a copy of the Terrain layer (Terrain.HydroEnforced) been created ? |  | Pass
16 | Have hydro forcing burn lines been applied at all crossing using the Terrain Channel Modification Tool? Are the bottom width, and max extent widths of each line appropriately estimated to match the current structure size? Changing the side slopes can cause some issues with stability if it is too steep or vertical. |  | Pass
17 | Has the Terrain.HydroEnforced.hdf file been correctly assigned to the geometry? |  | Pass
18 | Does the model account for any significant flow-regulating dams? |  | Unsure - See Reviewer Comments | there seems couple significant reservoirs; please confirm the flow-regulation for these dams | Other, See Orignator Comments | No information on flow regulation on these dams. | SK | OK
19 | Were 2D connections appropriately set-up to model the regulated outflow from the dams? |  | Not Applicable for This
20 | Are the sources for the dam operations documented? |  | Unsure - See Reviewer Comments | confirm after verifying above comment | Other, See Orignator Comments | No information on flow regulation on these dams. | SK | OK
Other
21 | Are comparison points/lines (i.e., internal 2-D connections) captured and compared against applicable benchmarks? (gage, high water mark, effective BFE, etc.) |  | Unsure - See Reviewer Comments | confirm at USGS 08143500 | Other, See Orignator Comments | will confirm during calibration steps along with other refernce data. | SK | OK
22 | If applicable, is the transfer line between this model and a downstream model well away from any boundary condition effects? |  | Fail | please utilize SA/2D Area Connection as discussed in team call on 5/4 |  | Need to add SA/2D connection | SK | verified; OK
23 | Are perimieter boundary conditions applied where flow is leaving the 2D area? |  | Pass
24 | Are boundary coniditions applied such the flow does not build up at the boundary of the 2D mesh? |  | Pass
25 | Are there any other comments related to the model geometry? |  | Pass
Total QC citations for this review |  |  | 7
Percent Passing |  |  | 72%
Other Comments

## Unsteady Flow Data
Hydrology
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Pecan Bayou - 0705_A6 |  |  |  |  | Sravan Krovidi |  | 2022-05-27
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
1 | Are the precipitation depths reasonable, and sufficiently documented? Was a reasonable temporal storm distribution used? |  | Pass
2 | Have the flow files for the Pluvial events been assigned correctly ? |  | Pass
3 | Are the flow files based on proper naming convention for the event, precip source ? |  | Pass
4 | Has the SA/2D flow area been assigned the correct DSS precipitation file from the hydrology folder? Has the appropriate event in the DSS file been selected? |  | Not Applicable for This
5 | Does the model include all required and scoped events / frequencies? |  | Fail | need to add other recurrence intervals; only 1% and 0.2% included for now | Other, See Orignator Comments | Will run other recurrence intervals during calibration | SK | OK
6 | Does model plan and precip have same AEP event. For example, 10% AEP plan use 10% AEP rainfall. |  | Pass
7 | Was the appropriate areal reduction factor used for the 2D mesh? |  | Unsure - See Reviewer Comments | aerial reduction not applied? - please confirm | Other, See Orignator Comments | No aerial reduction applied | SK | OK
8 | Are the incoming hydrographs being applied properly? (location, shapes, timing, etc.). Confirm that any incoming hydrographs have the same time and magnitude of peak flow by opening up the upstream RAS models |  | Not Applicable for This | fluvial not applied yet at time of this review
9 | For hydrographs transferred from one RAS model to a downstream RAS model, are the incoming and outgoing hydrographs being applied at a coincident location? |  | Fail | add SA/2D Area Conn per project ITR |  | Need to add SA/2D connection | SK | verified; OK
10 | If using a direct flow transfer from an upstream model, does the time interval for the inflowing hydrograph match the time interval of the extracted hydrograph from the upstream model? |  | Unsure - See Reviewer Comments | see above comment
11 | Do all boundary conditions have a hydrograph or elevation/slope data assigned? |  | Pass
12 | Is the downstream boundary condition consistent with ground slope or know downstream WSEL? |  | Unsure - See Reviewer Comments | one normal depth value used for all perimeter
13 | Are there any other comments related to the unsteady flow data? |  | Pass
Joint Probability Checks (Receiving Watersheds Only)
14 | Is the joint probability approach being applied to this watershed? If no, no additional checks are needed. |  | Not Applicable for This
15 | Is this model for a headwater watershed? If so, no additional JP checks are needed. |  | Not Applicable for This
16 | Are the Inflow Drainage Area and the Total Drainage Area upstream of each confluence correct? Are all areas computed in square miles? |  | Not Applicable for This | [5 empty] | Screenshot 1 | Screenshot 2
17 | According to the Total Drainage Area (Atot) and the Drainage Area Ratio (RA), has the correct Watershed Category been assigned to each inflow watershed? (e.g., SS, SL, LS, LL - Refer to Screenshot 1) |  | Not Applicable for This | [6 empty] | FEMA - 2D Watershed Modeling in HEC-RAS Recommended Practices - Appendix B JP Combinations
18 | For each event in the model, has the correct representative JP event been identified for each inflow watershed? |  | Unsure - See Reviewer Comments | verify after adding all recurrence intervals | Other, See Orignator Comments | Utilizing Direct flow Method. | SK | OK
19 | Have the inflow hydrographs from all inflow watersheds been included in the model? Are the hydrographs for the correct representative JP events? (refer to Screenshot 2 ) |  | Fail | need to add inflow from 0703_A4; also add via SA/2D Area Conn from upstream watersheds |  | Need to add SA/2D connection, and inflow | SK | verified; OK
20 | Has each inflow watershed been assigned its own JP flow and plan file? |  | Pass
21 | Has the JP flow file in RAS for each inflow watershed been created with the proper naming convention? (e.g., NRCS_1.0_PCT_0202_A6_JP) |  | Pass
22 | At each confluence, has each fluvial JP inflow hydrograph been shifted so that the peak of the JP inflow hydrograph is aligned with the peak of the pluvial hydrograph? As part of this check, temporarily disable other inflows so they do not interfere. |  | Not Applicable for This
23 | Has the upstream watershed(s) offset .DSS file been copied to the hydrology folder for the watershed being modeled? |  | Unsure - See Reviewer Comments | see above comment |  |  | SK | OK
24 | Has a model/plan matrix been included with the model? |  | Not Applicable for This
25 | Are there any other comments related to the Joint Probability hydrology? |  | Not Applicable for This
Total QC citations for this review |  |  | 3
Percent Passing |  |  | 88%
Other Comments

## Model Execution and Results
Hydraulics
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Pecan Bayou - 0705_A6 |  |  |  |  | Sravan Krovidi |  | 2022-05-27
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
Model Execution
1 | Is the Diffusion Wave Equation being used? |  | Pass
2 | Is the timestep appropriate for the mesh size and calculated velocities? |  | Pass
3 | Are the Computation Options and Tolerances set to the default values? If no, is it documented and justified? |  | Pass
4 | Are the advanced time step control tab settings selected properly ? Are Variable time step parameters reasonable / Meet project needs ? |  | Pass
5 | Are both the "hydrograph output interval" and "mapping output interval" set at a reasonable interval to capture peak flows within the model? |  | Pass
6 | Are there any other comments related to the HEC-RAS Unsteady Plan settings? |  | Pass
Model Results
7 | Does the model run with no cell errors? |  | Pass
8 | Does the model have acceptable volume conservation (less than 3%) |  | Pass
9 | Is the Courant number generally less than 2 but no greater than 5? |  | Pass
10 | Was the model simulation long enough to pass the entire hydrograph(s) through the model? |  | Pass
11 | Is any flow trapped at the 2D boundary? |  | Pass
12 | Are all water-surface elevation convergence warning messages acceptable per computation tolerances? |  | Pass
13 | Are contributing areas contained within the 2D mesh or accounted for with inflow hydrographs? |  | Unsure - See Reviewer Comments | review after adding inflow hydrograph from u/s watershed |  | Review | SK | verified; OK
14 | Are hydrographs at the internal and external boundary conditions smooth? |  | Unsure - See Reviewer Comments | see above comment |  |  | SK
15 | Check to make sure the computed maximum depth, WSEL, and velocity values are not from numerical surge (i.e. Beginning of model). |  | Pass
16 | Are the water surface and depth grids reasonable with no artificial dips or spikes? |  | Pass
17 | Is there any ponding behind road embankments? If so, is it reasonable or should the model be modified to allow flow through the embankment? |  | Unsure - See Reviewer Comments | flow not routing thru spillway for couple ponds and railroad; please review and see if any hydroenforcement is needed | Other, See Orignator Comments | Based on Discussion in H&H meeting, hydroenforcement will not be applied for spillways at this time. Will adjust if updated. | SK | OK
18 | Do the velocity grids appear reasonable with no unusually high velocity areas? |  | Fail | some high velocities observed (>20fps); please verify after addressing mannings n comment | Agree, Changes Made | High velocities reduced after Mannings N adjusted | SK | OK
19 | Have instances of model instabilities at the beginning of the simulation due to initial wetting of a dry grid been addressed? Should a initial condition (wet start) be used? |  | Pass
20 | Are there other comments related to the model results? |  | Pass
Total QC citations for this review |  |  | 1
Percent Passing |  |  | 95%
Other Comments

## Model Validation
Calibration and Validation
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Pecan Bayou - 0705_A6 |  |  |  |  | Sravan Krovidi |  | 2022-05-27
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
Validation is Performed for the 100-yr Only
1 | Is the method and parameters adjusted for model validation documented? | Documented in Pecan Bayou Model Overview and Results Sheet | Pass
2 | Are the modifications to the Curve Number's and/or Manning's n reasonable? | Adjusted CN table values for Developed regions. Developed, Low Intensity values were increased by 5% of original values. Developed, Open Space values were increased by 10% of original values. Developed, High Intensity and Developed, Medium Intensity values were not adjusted. Mannings N value was changed from 0.03 to 0.045. | Pass
3 | Have representative points in the watershed been used to check pluvial flows to confirm they are within the 1% regression bounds? | 13 Points throughout the watershed were measured including gages and FIS points. | Pass
4 | Do the peak discharges compare favorably to gages, effective studies, INFRM flows, or other approved benchmarks? If not, have attempts been made to calibrate? | Flow is within the gage analysis values. 3 of 5 points are within calculated regression values for streams. FIS values are larger then reported FIS flow in the urban areas. | Pass
5 | Are there other comments related to model validation? |  | Pass
Joint Probability Checks
6 | Was the JP rainfall adjusted for calibration? If so, is it within the acceptable limits outlined in Appendix B of FEMA's best practices document?
Total QC citations for this review |  |  | 0
Percent Passing |  |  | 100%
Other Comments

## Model Clean-up
Model Clean-up
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Pecan Bayou - 0705_A6 |  |  |  |  | Sravan Krovidi |  | 2022-05-27
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
For Submission to Water Board
1 | HEC-RAS Project files: Have all temporary and interim project files been deleted from the model? (*.p##, *.g##, *.u##) |  | Pass
2 | HEC-RAS Output files: Have all unused output files been deleted from the project directory? (*.O##,*.hyd##, *.c##,*.b##, *.bco##, *.g##.hdf, *.p##.hdf, *.p##.blf, *.IC.O##, *.x##) |  | Pass
3 | HEC-RAS DSS Output file: Have any unused model outputs associated with plans no longer in use been deleted from the HEC-DSS Output file? |  | Pass
4 | HEC-RAS DSS Output file: Do hydrographs for all 7 recurrence interval events (10%, 4%, 2%, 1%, 0.2%, and 1% (+/-)) show up under the "Plot Stage and Flow Hydrographs" option within HEC-RAS? |  | Pass
5 | Have all old versions of geometries and plans been removed from the tree list within RAS Mapper? |  | Pass
6 | Have all non-essential shapefiles been removed from RAS Mapper? |  | Pass
7 | Is there a projection defined within RAS Mapper and is it correct? |  | Pass
8 | Are the terrain and land cover files correctly associated with the geometry and results layers? |  | Pass
9 | Have all folders and/or files that are not necessary for viewing results been deleted from the project folder (i.e. shapefiles, Excel documents, etc.)? |  | Pass
10 | Have all old and non-relevant comments within each unsteady flow plan been removed? |  | Pass
11 | Can the "computation log file" and "runtime messages" be seen for each plan? |  | Pass
Total QC citations for this review |  |  | 0
Percent Passing |  |  | 100%
Other Comments

## Drop Down List
Pass
Fail
Unsure - See Reviewer Comments
Not Applicable for This
Agree, Changes Made
Disagree, No Changes Made
Other, See Orignator Comments