## Instructions
Engineering Files QC Checklists
1 | Please insert Study Name on Sign Off tab. This will automatically populate the remainder of the spreadsheets. Please insert the Feme Case No in front of the document name, and save the file with that name on your network.
2 | Please enter name (and initials) on Sign Off tab. If additional lines are required, copy the last line and insert below. As you complete the spreadsheets, you will need only to insert your initials.
3 | Please enter the name of the basin, stream reach, or coastal beach that you are reviewing in the appropriate space at the top of the sheet. The first of each set of forms requires names and dates to be added at the top of each column.
4 | Technical Review refers to the final review of work. This will be accomplished by an independent team of subject matter experts. Work should be considered as complete and ready to submit when submitted to this team. Be certain to add initials to the form.
5 | QA Verification refers to the determination that the work is ready to deliver. It is accomplished by a representative of the QA Manager. This review is cursory and involves review of records and spot checks of errors that appear to be systemic. The purpose of this review is to first ensure that all errors have been corrected, files are ready to be submitted and all records are ready for archival. Secondly, the review will focus on whether errors are systemic (requiring adjustment to procedure, or perhaps further training) or random (requiring review of schedules, budgets, etc.) Be certain to add initials to the form.
6 | Should there be a requirement to review data a second (or more) time, simply copy the appropriate columns and insert them to the right of the original review columns.
7 | A separate worksheet may be required for each basin, stream reach or model, and coastal beach. In this case copy the worksheet and insert into the workbook in the proper sequential order. Please label the tab with the basin name, stream reach or model number(s), or beach to make use of the workbook easier.
8 | Please indicate status of each item by responding P (Pass), F (Fail), NA (Not applicable).
9 | When your review is complete and you are satisfied with the quality of the work, please sign a hard copy of the sign off sheet. Please be certain to retain the signed sheet with other project documents and be sure the next reviewer knows where to locate it. QA Verification reviewer, please scan the sign off sheet and add to the document files for the project.

## Sign off-QC Stamp
ATKINS QUALITY REVIEW CHECKLIST SIGN OFF FORM
Study / Stream Name | San Saba HUC-8
Deliverable
MIP Case #:
PM: | Seth Ahrens
QC REVIEW ACTIVITY
Ready for QC | *Originator / Date : | Hydraulics Terrain: Iwan Thomas 11/9/21 Hydro-Conditioning: Jordan Taylor 12/20/21
QC Review | QC Review / Date: | Hydraulics Terrain: Selena Forman 11/10/21 Hydro-Conditioning: Iwan Thomas 1/20/22
Changes Made | *Originator/ Date : | Hydraulics Terrain: no changes requested Hydro-Conditioning: Jordan Taylow 1/21/22
QC Verification | *QC Reviewer: | Hydraulics Terrain: Selena Forman 11/10/21 Hydro-Conditioning: Iwan Thomas 1/21/22
Date:
PQM Approval | *QA: | Vikram Shrivastava
| Date: | 2022-05-27

## Terrain Processing
Terrain Processing
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
San Saba HUC-8 |  |  |  |  | Selena Forman for Hydraulics Terrain Processing Iwan Thomas for Hydroconditioning |  | 2022-01-20
Comments for QC Reviewer from PM and/or TM
Originators: Hydraulics Terrain: Iwan Thomas, Hydro-Conditioning: Jordan Taylor
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
Hydraulics Terrain Processing
1 | Is the correct unit system being used (i.e. SI vs. U.S. Customary)? Options -> "Unit System (US Customary/SI)…" |  | Pass |  |  |  | SF
2 | Are the source data documented? |  | Pass |  |  |  | SF
3 | Are the process tiles projection, units, and datum documented? |  | Pass |  |  |  | SF
4 | Are the processed tiles in an appropriate projection? |  | Pass |  |  |  | SF
5 | Are the processed tiles in the correction vertical units? Confirm at locations where each data source is used. |  | Pass |  |  |  | SF
6 | Are the elevations consistent with known elevation sources such as the World Topographic Base Map? |  | Pass |  |  |  | SF
7 | Are the vertical and horizontal distances in the same unit (ft/m)? |  | Pass |  |  |  | SF
8 | Do the seamless DEMs use a cell size of 5 feet? |  | Pass |  |  |  | SF
9 | Are there significant seams at locations transitions from one data source to another? If so, are they justified? |  | Pass | No significant seams |  |  | SF
10 | Are there any discontinuities or gaps observed in the contours? If so, are they justified. |  | Pass |  |  |  | SF
11 | Are there any other comments regarding the terrain? |  | Pass |  |  |  | SF
Hydroconditioning for Watershed and Streamlines
12 | Were burn lines applied appropriately to simulate the natural flow path through ponds and reservoirs? |  | Pass |  |  |  | IMT
13 | Were the burn lines applied appropriately where the top of road is part of the topography? |  | Fail | Please see QC polygon where a burn line should be added at a road. | Agree, Changes Made |  | IMT
14 | Is the stream network reasonable compared to the NHD flowlines? Are significant deviations documented and justified? |  | Pass |  |  |  | IMT
15 | Are the basin boundaries reasonable compared to the published HUC-8, HUC-10 and/or HUC-12 watershed boundaries? Are significant deviations documented and justified? |  | Pass |  |  |  | IMT
16 | Do the computed drainage areas reasonably match published values from gages, FIS reports or other studies? |  | Pass | Compares well to reported gage drainage areas |  |  | IMT
17 | Are there any other comments regarding the basins or hydrologic network? |  | Pass |  |  |  | IMT
Total QC citations for this review |  |  | 1
Percent Passing |  |  | 94.12%
Other Comments

## Drop Down List
Pass
Fail
Unsure - See Reviewer Comments
Not Applicable for This
Agree, Changes Made
Disagree, No Changes Made
Other, See Orignator Comments