## Instructions
Engineering Files QC Checklists
1 | Please insert Study Name on Sign Off tab. This will automatically populate the remainder of the spreadsheets. Please insert the Feme Case No in front of the document name, and save the file with that name on your network.
2 | Please enter name (and initials) on Sign Off tab. If additional lines are required, copy the last line and insert below. As you complete the spreadsheets, you will need only to insert your initials.
3 | Please enter the name of the basin, stream reach, or coastal beach that you are reviewing in the appropriate space at the top of the sheet. The first of each set of forms requires names and dates to be added at the top of each column.
4 | Technical Review refers to the final review of work. This will be accomplished by an independent team of subject matter experts. Work should be considered as complete and ready to submit when submitted to this team. Be certain to add initials to the form.
5 | QA Verification refers to the determination that the work is ready to deliver. It is accomplished by a representative of the QA Manager. This review is cursory and involves review of records and spot checks of errors that appear to be systemic. The purpose of this review is to first ensure that all errors have been corrected, files are ready to be submitted and all records are ready for archival. Secondly, the review will focus on whether errors are systemic (requiring adjustment to procedure, or perhaps further training) or random (requiring review of schedules, budgets, etc.) Be certain to add initials to the form.
6 | Should there be a requirement to review data a second (or more) time, simply copy the appropriate columns and insert them to the right of the original review columns.
7 | A separate worksheet may be required for each basin, stream reach or model, and coastal beach. In this case copy the worksheet and insert into the workbook in the proper sequential order. Please label the tab with the basin name, stream reach or model number(s), or beach to make use of the workbook easier.
8 | Please indicate status of each item by responding P (Pass), F (Fail), NA (Not applicable).
9 | When your review is complete and you are satisfied with the quality of the work, please sign a hard copy of the sign off sheet. Please be certain to retain the signed sheet with other project documents and be sure the next reviewer knows where to locate it. QA Verification reviewer, please scan the sign off sheet and add to the document files for the project.

## Sign off-QC Stamp
ATKINS QUALITY REVIEW CHECKLIST SIGN OFF FORM
Study / Stream Name | Brady (1001_A1)
Deliverable
MIP Case #:
PM:
QC REVIEW ACTIVITY
Ready for QC | *Originator / Date : | Jewel Guiliani
2022-07-19
QC Review | *Reviewer / Date : | Santosh Nishtala
2022-07-19
Changes Made | *Originator/ Date : | Jewel Guiliani
2022-08-10
QC Verification | *QC Reviewer: | Santosh Nishtala
| Date: | 2022-08-18
PQM Approval | *QA: | Vikram Shrivastava
| Date: | 2022-09-23

## ITR Comments
Hydraulics
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Brady_1001_A1 |  |  |  |  | Santosh Nishtala |  | 2022-07-19
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
RAS Mapper Setup
1 | Is the model geometry/results linked to Terrain, Land Cover, and Infiltration layers |  | Pass
Breaklines
2 | Are Stream Breaklines smooth? |  | Pass
3 | Have Breaklines been planarized and offshoots less than 20ft been deleted? |  | Fail | remove road breakline offshoots longer than 20'. Check for offshoots manually. | Agree, Changes Made | Offshoots have been removed | SN | Comment Closed
4 | Have breaklines for minor roads intersecting US Highways and Interstates at an angle been adjusted manually to avoid leakage? |  | Fail | Move minor road breaklines manually to be away from the major highway (interstate/us hwy) | Agree, Changes Made
5 | Have dam spillways breaklines been added to the model and re-enforced? |  | Pass
6 | Are cell faces aligned with the dam and spillway breaklines? |  | Fail | adjust cell faces to align with the dam and spillway breaklines. | Agree, Changes Made | Cell faces hae been adjusted | SN | Comment Closed
7 | Have Inflow BC condition lines been enforced as breaklines in the model? Are the breaklines aligned to cell faces? |  | Not Applicable for This | Headwater model
8 | Have 0.5 sq mi flow paths been used for stream breaklines? (for urban areas)? Have streams been checked that they are not flow accumulation on the streets? |  | Not Applicable for This | rural model
9 | Have 1 sq mi flow paths been used for stream breaklines? (for rural areas)? |  | Pass
10 | Are breaklines added/enforced such that the grid is not leaking. |  | Fail |  | Agree, Changes Made | Breaklines have been adjusted so that there is no leaking | SN | Comment Closed
Refinement Regions
11 | Have channel refinement regions been removed where the stream breaklines intersect road/railroad/dam breaklines? |  | Fail | remove channel refinement regions at intersection with dam breaklines using buffer of 100ft. check for small remnants of the channel refinement region US of the dam and remove manually if applicable. | Agree, Changes Made | channel refinement regions at intersection with dam breaklines have been removed | SN | Comment Closed
12 | Have dam refinement regions been added for dams in the NID database larger than 20 ac? |  | Fail | dam refinment regions have not been added to the manning's n polygon | Agree, Changes Made | Dam Refinement regions have been added | SN | Comment Closed
13 | Have dam refinement regions and channel refinement/manning's n regions been adjusted to avoid overlap? |  | Fail | remove channel refinement regions where dam refinement regions have been applied. | Agree, Changes Made | Channel mannings N and Refinement regions don't overlap | SN | Comment Closed
14 | Have manning's n regions been added? |  | Fail | Manning'n regions are not using channel n values. (manning's n refinement regions need to be named as "Channel") | Agree, Changes Made | Mannings N channel polygon has been classified correctly | SN | Comment Closed
Manning's n
15 | Have Manning's n values from the TWDB Guidance document been used? |  | Fail | change manning's n value for open water to 0.038 | Agree, Changes Made | Mannings N has been adjusted | SN | Comment Closed
Infiltration Layer
16 | Have CNs from the TWDB Guidance document been used? |  | Fail | CNs not consistent with TWDB guidelines | Agree, Changes Made | CNs have been updated | SN | Comment Closed
Hydraulics Structures (including dams)
17 | Check that the culvert crosses the entire width of the embankment for hydro enforced culverts. |  | Pass
18 | Are the sources for the dam operations documented? |  | Not Applicable for This
Other
19 | Has SA2D connection been added at flow transfer location in the US model and is the location appropriate? |  | Pass
20 | Are comparison points/lines (i.e., internal 2-D connections) captured and compared against applicable benchmarks? (gage, high water mark, effective BFE, etc.) |  | Unsure - See Reviewer Comments | Will be cheked at validation stage |  |  | SN | Comment Closed
21 | Are perimeter boundary conditions applied where flow is leaving the 2D area? Is the normal depth reasonable? |  | Fail | extend perimenter boundary conditions in the southern corner | Agree, Changes Made | Perimeter BC Lines have been extended | SN | Comment Closed
22 | Are boundary conditions applied such the flow does not build up at the boundary of the 2D mesh? |  | Pass
23 | Are there any other comments related to the model geometry? |  | Fail | stream breaklines extend outside the channel refinement regions | Agree, Changes Made | Fixed | SN | Comment Closed
Unsteady Flow
24 | Are the rainfall hyetographs smooth without any oscillations? |  | Pass
25 | Are there 1pct plus and minus events crossing other events in the rainfall hyetographs? |  | Not Applicable for This | will be reviewed at validation stage. 1pct plus and minus curves have not been generated yet. | Agree, Changes Made | Checked, no issues found | SN | Comment Closed
26 | Have 1000, 200, 5 and 2 yr. rainfall hyetographs been removed form the DSS file? |  | Pass
27 | Are the outflows from the US model and inflows form the DS model consistent? |  | Unsure - See Reviewer Comments | screenshare and check with modeler; do not have the DS Model. | Agree, Changes Made | Completed | SN | Comment Closed
28 | Are there any other comments related to the Unsteady Flow? |  | Not Applicable for This
Model Execution and Results
29 | Does the model run with no cell errors? |  | Pass
30 | Does the model have acceptable volume conservation (less than 3%) |  | Pass
31 | Is the Courant number generally less than 2 but no greater than 5? |  | Pass
32 | Was the model simulation long enough to pass the entire hydrograph(s) through the model? Model simulation time should be based on the DS model requirements, and should extend 24 hours from the outflow peak. |  | Pass
33 | Is any flow trapped at the 2D boundary? |  | Pass
34 | Are all water-surface elevation convergence warning messages acceptable per computation tolerances? |  | Pass
35 | Are hydrographs at the internal and external boundary conditions smooth? |  | Pass
36 | Check to make sure the computed maximum depth, WSEL, and velocity values are not from numerical surge (i.e. Beginning of model). |  | Pass
37 | Are the water surface and depth grids reasonable with no artificial dips or spikes? |  | Pass
38 | Is there any ponding behind road embankments? If so, is it reasonable or should the model be modified to allow flow through the embankment? |  | Pass
39 | Do the velocity grids appear reasonable with no unusually high velocity areas? |  | Pass
40 | Have instances of model instabilities at the beginning of the simulation due to initial wetting of a dry grid been addressed? Should a initial condition (wet start) be used? |  | Pass
41 | Is the 10 yr. floodplain contained within the 100 yr. floodplain, especially at the US of hydro enforced culverts? |  | Pass | Isolated and random areas exist where 10 yr floodplain is slightly greater than 100 year floodplain. No major areas where 10yr floodplain >100 yr floodplain.
42 | Does Mapping tie in at the overlap between the US and DS models? |  | Pass
43 | Are there other comments related to the model results? |  | Pass
Model Validation
44 | Do the peak discharges compare favorably to gages, effective studies, INFRM flows, or other approved benchmarks? If not, have attempts been made to calibrate? |  | Fail | remove the profile line called overlap | Agree, Changes Made | Removed | SN | Comment Closed
45 | Are there any other comments related to Model validation? |  | Not Applicable for This
Model Cleanup
46 | HEC-RAS DSS Output file: Have any unused model outputs associated with plans no longer in use been deleted from the HEC-DSS Output file? |  | Pass
47 | Does the dss file have data from the previous runs? Has irrelevant data from dss file been deleted? Are Boundary conditions appropriately named in the dss file? |  | Fail | there is extranesou data from the previous submittal. PLease clean the dss file to remove extraneous data. | Agree, Changes Made | Cleaned up the dss file | SN | Comment Closed
48 | HEC-RAS DSS Output file: Do hydrographs for all 7 recurrence interval events (10%, 4%, 2%, 1%, 0.2%, and 1% (+/-)) show up under the "Plot Stage and Flow Hydrographs" option within HEC-RAS? |  | Pass
49 | Have all irrelevant files from the RAS mapper and the features folder in model directory been removed? |  | Pass
50 | Are there any other comments related to Model validation? |  | Not Applicable for This
ITR Comments
51 | Have all ITR comments been addressed? Check ITR comments document and shapefile if applicable. |  | Pass
Total QC citations for this review |  |  | 13
Percent Passing |  |  | 48%
Other Comments

## Drop Down List
Pass
Fail
Unsure - See Reviewer Comments
Not Applicable for This
Agree, Changes Made
Disagree, No Changes Made
Other, See Orignator Comments