## Instructions
Engineering Files QC Checklists
1 | Please insert Study Name on Sign Off tab. This will automatically populate the remainder of the spreadsheets. Please insert the Feme Case No in front of the document name, and save the file with that name on your network.
2 | Please enter name (and initials) on Sign Off tab. If additional lines are required, copy the last line and insert below. As you complete the spreadsheets, you will need only to insert your initials.
3 | Please enter the name of the basin, stream reach, or coastal beach that you are reviewing in the appropriate space at the top of the sheet. The first of each set of forms requires names and dates to be added at the top of each column.
4 | Technical Review refers to the final review of work. This will be accomplished by an independent team of subject matter experts. Work should be considered as complete and ready to submit when submitted to this team. Be certain to add initials to the form.
5 | QA Verification refers to the determination that the work is ready to deliver. It is accomplished by a representative of the QA Manager. This review is cursory and involves review of records and spot checks of errors that appear to be systemic. The purpose of this review is to first ensure that all errors have been corrected, files are ready to be submitted and all records are ready for archival. Secondly, the review will focus on whether errors are systemic (requiring adjustment to procedure, or perhaps further training) or random (requiring review of schedules, budgets, etc.) Be certain to add initials to the form.
6 | Should there be a requirement to review data a second (or more) time, simply copy the appropriate columns and insert them to the right of the original review columns.
7 | A separate worksheet may be required for each basin, stream reach or model, and coastal beach. In this case copy the worksheet and insert into the workbook in the proper sequential order. Please label the tab with the basin name, stream reach or model number(s), or beach to make use of the workbook easier.
8 | Please indicate status of each item by responding P (Pass), F (Fail), NA (Not applicable).
9 | When your review is complete and you are satisfied with the quality of the work, please sign a hard copy of the sign off sheet. Please be certain to retain the signed sheet with other project documents and be sure the next reviewer knows where to locate it. QA Verification reviewer, please scan the sign off sheet and add to the document files for the project.

## Sign off-QC Stamp
ATKINS QUALITY REVIEW CHECKLIST SIGN OFF FORM
Study / Stream Name | Brady (1002_A3)
Deliverable
MIP Case #:
PM:
QC REVIEW ACTIVITY
Ready for QC | *Originator / Date : | Jewel Guliani
2022-07-27
QC Review | *Reviewer / Date : | Solaleh Khezri (SK)
2022-07-29
Changes Made | *Originator/ Date : | Jewel Guliani
2022-08-01
QC Verification | *QC Reviewer: | Solaleh Khezri (SK)
| Date: | 2022-08-24
PQM Approval | *QA: | Vikram Shrivastava
| Date: | 2022-09-23

## ITR Comments
Hydraulics
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Brady-10002-A03 |  |  |  |  | Solaleh Khezri |  | 2022-07-29
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
RAS Mapper Setup
1 | Is the model geometry/results linked to Terrain, Land Cover, and Infiltration layers |  | Pass
Breaklines
2 | Are Stream Breaklines smooth? |  | Pass
3 | Have Breaklines been planarized and offshoots less than 20ft been deleted? |  | Pass
4 | Have breaklines for minor roads intersecting US Highways and Interstates at an angle been adjusted manually to avoid leakage? |  | Fail | see th QC shapefile. | Agree, Changes Made | All the changes in the QC shape file have been accepted and fixed in the model | SK | Comment Closed.
5 | Have dam spillways breaklines been added to the model and re-enforced? |  | Pass
6 | Are cell faces aligned with the dam and spillway breaklines? |  | Pass
7 | Have Inflow BC condition lines been enforced as breaklines in the model? Are the breaklines aligned to cell faces? |  | Pass
8 | Have 0.5 sq mi flow paths been used for stream breaklines? (for urban areas)? Have streams been checked that they are not flow accumulation on the streets? |  | Pass
9 | Have 1 sq mi flow paths been used for stream breaklines? (for rural areas)? |  | Pass
10 | Are breaklines added/enforced such that the grid is not leaking. |  | Pass
Refinement Regions
11 | Have channel refinement regions been removed where the stream breaklines intersect road/railroad/dam breaklines? |  | Pass
12 | Have dam refinement regions been added for dams in the NID database larger than 20 ac? |  | Pass
13 | Have dam refinement regions and channel refinement/manning's n regions been adjusted to avoid overlap? |  | Fail | Please see the QC shapefile. The dam refinement overlaps the city and channel refinement in many places, needs clean up. | Agree, Changes Made | Overlaps has been removed | SK | Comment Closed.
14 | Have manning's n overlap regions been added? |  | Pass
Manning's n
15 | Have Manning's n values from the TWDB Guidance document been used? |  | Unsure - See Reviewer Comments | channel and Open water N are different. | Other, See Orignator Comments | Open water N fixed; channel manning's N is changed based on the validation (usually use 0.04 / 0.045 / 0.05 based on validation) | SK | Comment Closed.
Infiltration Layer
16 | Have CNs from the TWDB Guidance document been used? |  | Pass
Hydraulics Structures (including dams)
17 | Check that the culvert crosses the entire width of the embankment for hydro enforced culverts. |  | Pass | 100yr WSE > 10 yr WSE
18 | Are the sources for the dam operations documented? |  | Unsure - See Reviewer Comments | Do we have the information? | Other, See Orignator Comments | We don’t have any information on the reservoir | SK | Comment Closed.
Other
19 | Has SA2D connection been added at flow transfer location in the US model and is the location appropriate? |  | Pass | Change name of SA2D connection |  | Name changed | SK | Comment Closed.
20 | Are comparison points/lines (i.e., internal 2-D connections) captured and compared against applicable benchmarks? (gage, high water mark, effective BFE, etc.) |  | Unsure - See Reviewer Comments | will be checked at validation stage
21 | Are perimeter boundary conditions applied where flow is leaving the 2D area? Is the normal depth reasonable? |  | Fail | the 100 yr hydrograph is unstable at some location along the boundary. Please see the QC shapefile. | Agree, Changes Made | QC shp file comments addressed | SK | Comment Closed.
22 | Are boundary conditions applied such that the flow does not build up at the boundary of the 2D mesh? |  | Pass
23 | Are there any other comments related to the model geometry? |  | Pass
Unsteady Flow
24 | Are the rainfall hyetographs smooth without any oscillations? |  | Pass
25 | Are there 1pct plus and minus events crossing other events in the rainfall hyetographs? |  | Pass
26 | Have 1000, 200, 5 and 2 yr. rainfall hyetographs been removed form the DSS file? |  | Fail |  | Disagree, No Changes Made | The mentioned rainfall events have already been removed from the dss file "Brady_1002_A3_Rainfall_NRCS.dss" | SK | Comment Closed.
27 | Are the outflows from the US model and inflows from the DS model consistent? |  | Pass
28 | Are there any other comments related to the Unsteady Flow? |  | Pass
Model Execution and Results
29 | Does the model run with no cell errors? |  | Pass
30 | Does the model have acceptable volume conservation (less than 3%) |  | Pass
31 | Is the Courant number generally less than 2 but no greater than 5? |  | Pass
32 | Was the model simulation long enough to pass the entire hydrograph(s) through the model? Model simulation time should be based on the DS model requirements, and should extend 24 hours from the outflow peak. |  | Fail | Check the DS model later. The run time is insufficient for the inflow hydrograph. Also the previous run has not been deleted. | Agree, Changes Made | Model runtimes have been increased to 5 days | SK | Comment Closed.
33 | Is any flow trapped at the 2D boundary? |  | Pass
34 | Are all water-surface elevation convergence warning messages acceptable per computation tolerances? |  | Pass
35 | Are hydrographs at the internal and external boundary conditions smooth? |  | Fail | There are instabilities in the hydrograph along the perimiter boundary. Please see the QC shapefile. Model run time needs to be increased to route the entire hydrograph. | Agree, Changes Made | Chanages made from QC shp file; Model runtimes have been increased to 5 days | SK | Comment Closed.
36 | Check to make sure the computed maximum depth, WSEL, and velocity values are not from numerical surge (i.e. Beginning of model). |  | Pass
37 | Are the water surface and depth grids reasonable with no artificial dips or spikes? |  | Pass
38 | Is there any ponding behind road embankments? If so, is it reasonable or should the model be modified to allow flow through the embankment? |  | Pass
39 | Do the velocity grids appear reasonable with no unusually high velocity areas? |  | Pass
40 | Have instances of model instabilities at the beginning of the simulation due to initial wetting of a dry grid been addressed? Should a initial condition (wet start) be used? |  | Pass
41 | Is the 10 yr. floodplain contained within the 100 yr. floodplain, especially at the US of hydro enforced culverts? |  | Pass
42 | Does Mapping tie in at the overlap between the US and DS models? |  | Unsure - See Reviewer Comments | recheck after running the DS model with appropriate inflows file from this model. | Agree, Changes Made | Model does tie-in within 0.5 ft of WSEL | SK | Comment Closed.
| Are there other comments related to the model results? |  | Unsure - See Reviewer Comments | for the 100 yr run there is a message "Computing 2D Flow Area '1002_A3' tables: Property tables do not exist." Seems that the model have been changes after the 100 run. | Agree, Changes Made | Final runs don't have this issue | SK | Comment Closed.
Model Validation
44 | Do the peak discharges compare favorably to gages, effective studies, INFRM flows, or other approved benchmarks? If not, have attempts been made to calibrate? |  | Pass
45 | Are there any other comments related to Model validation? |  | Pass
Model Cleanup
46 | HEC-RAS DSS Output file: Have any unused model outputs associated with plans no longer in use been deleted from the HEC-DSS Output file? |  | Pass
47 | Does the dss file have data from the previous runs? Has irrelevant data from dss file been deleted? Are Boundary conditions appropriately named in the dss file? |  | Pass
48 | HEC-RAS DSS Output file: Do hydrographs for all 7 recurrence interval events (10%, 4%, 2%, 1%, 0.2%, and 1% (+/-)) show up under the "Plot Stage and Flow Hydrographs" option within HEC-RAS? |  | Pass
49 | Have all irrelevant files from the RAS mapper and the features folder in model directory been removed? |  | Pass
50 | Are there any other comments related to Model validation? |  | Pass
ITR Comments
51 | Have all ITR comments been addressed? Check ITR comments document and shapefile if applicable. |  | Pass
Total QC citations for this review |  |  | 6
Percent Passing |  |  | 76%
Other Comments

## Drop Down List
Pass
Fail
Unsure - See Reviewer Comments
Not Applicable for This
Agree, Changes Made
Disagree, No Changes Made
Other, See Orignator Comments