## Drop Down List
General
Note: This spreadsheet contains four review tabs. Reviewer should fill out all tabs corresponding to the type of study as follows:
Detailed Analysis: Hydraulics Checklist
Approximate Analysis: Approx Hydraulics Checklist
If Unsteady Analysis is used, also fill out: RAS 1D Unsteady Checklist
If 2D Analysis is used, also fill out: RAS 2D Checklist
Hydraulics Checklist
Row 4: Add Job Name, Reviewer, and Date
Row 6: Project Manager should add any information in here that the reviewer should be aware of
Rows 9 - 102: The QC reviewer should review each factual statement and determine that it either is true or false. If "true", then the drop down in column D should be used to select "Pass". If not true or if the reviewer is unsure, then the reviewer should select "Fail" or "Unsure - See Reviewer Comments" respectively. NOTE: the pass/fail column should not be changed after the initial review. Anything that fails the initial review will show how the issue was resolved in subsequent columns. The reviewer may enter any comments desired in column E which may be used to further clarify as needed and/or to explain why they selected either "Fail" or "Unsure - See Reviewer Comments". In column F, the producer (originator) should indicate how each QC comment identified as a failure was resolved. If "Disagree, no changes made" or "Other; See Originator Comments" is selected, then the originator must provide a reason in column G and the reviewers initials must be entered into column H if they agree with the resolution. The same applies if "Unsure - See Reviewer Comments" was the reviewer's citation. If the reviewer does not agree with the resolution or the explanation provided by the originator, then the issue must be escalated as shown on the Escalation Protocol tab of this workbook. No failures or "Unsure" citations are considered resolved without the initials of the QC reviewer in column H. Row 106: This is reserved for any additional QC comments that may be needed.
Approximate Hydraulics Checklist
Row 4: Add Job Name, Reviewer, and Date
Row 6: Project Manager should add any information in here that the reviewer should be aware of
Rows 9 - 52: The QC reviewer should review each factual statement and determine that it either is true or false. If "true", then the drop down in column D should be used to select "Pass". If not true, then the reviewer should select "Fail". The reviewer may enter any comments desired in column E which may be used to further clarify as needed and/or to explain why they selected either "Fail" or "Unsure - See Reviewer Comments". In column F, the producer (originator) should indicate how each QC comment identified as a failure was resolved. If "Disagree, no changes made" or "Other - See Originator Comments" is selected, then the originator must provide a reason in column G and the reviewers initials must be entered into column H if they agree with the resolution. The same applies if "Unsure - See Reviewer Comments" was the reviewer's citation. If the reviewer does not agree with the resolution or the explanation provided by the originator, then the issue must be escalated as shown on the Escalation Protocol tab of this workbook. No failures or "Unsure" citations are considered resolved without the initials of the QC reviewer in column H. For projects where a backcheck is scoped to review the corrections, column I should be used to indicate that the issue was satisfactorily corrected. Row 56: This is reserved for any additional QC comments that may be needed.
RAS 1D Unsteady Checklist
Row 4: Add Job Name/Stream Name, Reviewer, and Date
Row 6: Project Manager should add any information in here that the reviewer should be aware of
Rows 9 - 62: The QC reviewer should review each factual statement and determine that it either is true or false. If "true", then the drop down in column D should be used to select "Pass". If not true, then the reviewer should select "Fail". The reviewer may enter any comments desired in column E which may be used to further clarify as needed and/or to explain why they selected either "Fail" or "Unsure - See Reviewer Comments". In column F, the producer (originator) should indicate how each QC comment identified as a failure was resolved. If "Disagree, no changes made" or "Other; See Originator Comments" is selected, then the originator must provide a reason in column G and the reviewers initials must be entered into column H if they agree with the resolution. The same applies if "Unsure - See Reviewer Comments" was the reviewer's citation. If the reviewer does not agree with the resolution or the explanation provided by the originator, then the issue must be escalated as shown on the Escalation Protocol tab of this workbook. No "Fail" or "Unsure - See Reviewer Comments" citations are considered resolved without the initials of the QC reviewer in column H. For projects where a backcheck is scoped to review the corrections, column I should be used to indicate that the issue was satisfactorily corrected. Row 66: This is reserved for any additional QC comments that may be needed.
RAS 2D Checklist
Row 4: Add Job Name/Stream Name, Reviewer, and Date
Row 6: Project Manager should add any information in here that the reviewer should be aware of
Rows 9 - 62: The QC reviewer should review each factual statement and determine that it either is true or false. If "true", then the drop down in column D should be used to select "Pass". If not true, then the reviewer should select "Fail". The reviewer may enter any comments desired in column E which may be used to further clarify as needed and/or to explain why they selected either "Fail" or "Unsure - See Reviewer Comments". In column F, the producer (originator) should indicate how each QC comment identified as a failure was resolved. If "Disagree, no changes made" or "Other; See Originator Comments" is selected, then the originator must provide a reason in column G and the reviewers initials must be entered into column H if they agree with the resolution. The same applies if "Unsure - See Reviewer Comments" was the reviewer's citation. If the reviewer does not agree with the resolution or the explanation provided by the originator, then the issue must be escalated as shown on the Escalation Protocol tab of this workbook. No "Fail" or "Unsure - See Reviewer Comments" citations are considered resolved without the initials of the QC reviewer in column H. For projects where a backcheck is scoped to review the corrections, column I should be used to indicate that the issue was satisfactorily corrected. Row 66: This is reserved for any additional QC comments that may be needed.
Sign Off
Rows 3 - 5: The Project Manager should fill these out Rows 7 & 8: These are to be filled out by the Project Manager to certify that, to the best of his/her ability, the project meets all requirements and is ready for independent QC review. Rows 10 & 11: These are to be filled out by the QC reviewer indicating that he/she has completed the review. Rows 13 & 14: These are to be filled out by the Originator indicating that all changes requested by QC were resolved satisfactorily and any that could not be resolved were resolved per the STARR II Escalation Protocol. Rows 16 & 17: These are to be filled out by the QC reviewer indicating that all changes made are acceptable. Rows 19 & 20: These are to be filled out by the Project Manager indicating that the job is now acceptable to move on to the next phase.
Escalation Protocol
If the originator and the QC reviewer do not agree on a resolution, the process shown on the Escalation Protocol tab must be followed.
Pass
Fail
Unsure - See Reviewer Comments
Not Applicable for This
Agree, Changes Made
Disagree, No Changes Made
Other, See Orignator Comments

## Sign off-QC Stamp
ATKINS QUALITY REVIEW CHECKLIST SIGN OFF FORM
Study / Stream Name | Brady_1001_A2
Deliverable
MIP Case #:
PM:
QC REVIEW ACTIVITY
Ready for QC | *Originator / Date : | Jordan Taylor
2022-04-11
QC Review |  | Santosh Nishtala (SN)
2022-04-12
Changes Made | *Originator/ Date : | Jordan Taylor
2022-04-21
QC Verification | *QC Reviewer: | Santosh Nishtala (SN)
| Date: | 2022-04-27
PQM Approval | *QA: | Vikram Shrivastava
| Date: | 2022-04-29

## Model Geometry
Hydraulics
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Brady_1001_A2 |  |  |  |  | Santosh Nishtala |  | 2022-04-12
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
RAS Mapper Setup
1 | Is the model projection correct? |  | Pass
2 | Does the terrain and model projections match |  | Pass
3 | Is the model geometry linked to Terrain, Land Cover, and Infiltration layers |  | Pass
4 | Do the model results show Terrain, Landcover and Infiltration layers linked |  | Pass
2D Mesh
1 | Does the digital terrain model input for the 2D model cover the entire 2D study area? |  | Pass
2 | Is the 2D mesh reasonably sized to limit cell count and obtain reasonable velocities? (Generally 200 ft and refined where needed) |  | Pass
3 | Is the model domain delineated properly to capture all contributing flows through rain-on-grid or external hydrograph? |  | Fail | Outflow boundary condition should be added along the edge of the model boundary to account for any flows ponding along the periphery. This is especially relevant when the ponded area connects to a stream/inundated area inside the model boundary. | Agree, Changes Made | Boundary condition lines were added where there was excessive ponding around perimeter. | SN | Comment Closed
4 | Are there any 2D mesh errors? |  | Pass
Breaklines
5 | Are breaklines sufficiently detailed to capture features (thalweg, roads, banks, berms, etc.)? |  | Unsure | The standard 100 ft with 2 repeats may not be applicable to all streams and roadways. The repeats and spacing could be varied by stream order and roadway classification if a higher resolution is deemed appropriate for this project. If this is the level of service typically provided for BLE projects, please ignore this comment.. |  |  | SN | Closed comment. Modeling is consistent with Process document.
6 | Are breaklines consistent with the terrain data? |  | Pass
7 | Have sufficient offset breaklines been added to assure flow is not being restricted upstream? |  | Fail | -Have the stream centrelines used as breaklines been obtained from a database, or from delineation? The delineated streamlines do not necessarly follow the stream centreline. Data from database should be used if available. -Breaklines along the spillway for dam spillways should also be included in the models. -Breaklines should be included for railroads. | Other, See Orignator Comments | Streamlines were derived from the best LiDAR available and it is not possible to reshape all streams. Varied cell size in streams is not possible for this project. Breaklines were added along spillways of major dams. | SN | Closed comment
8 | Are breaklines added such that the grid is not leaking. |  | Pass | Did not find any leaks.
Manning's n
9 | Is the source of the roughness coefficients or criteria for selecting default roughness coefficients documented? |  | Fail | Reference should be added for the Manning's n values source. The roads are classified as medium, high or low intensity developed or open space. Roads should have their own classification and not be clubbed with the development. The high manning's n values for development may be justified by the buildings, but since the roads do not have any buildings, the manning's n values for roads should be lower. | Disagree, No Changes Made | We use NLCD and channel polygon as a refinement to that. Its not possible to create separate land use for roads for BLE studies | SN | Closed Comment.
10 | Are channel Manning's n values reasonable? Has 50pct plan been ran to delineated the channel region Polygon override for manning's n Values? |  | Pass | The 50 pct plan was not used to delineate channel region. The channel manning's n was based on buffering the Channel. The buffer could be varied by stream order.
11 | Is the Manning's n dataset associated with the geometry file? |  | Pass
Infiltration Layer
12 | Are Curve Numbers (CN) values reasonable, and sufficiently documented? |  | Fail | The curve numbers for Shrub Scrub which covers significant part of the Watershed appears to be underestimated. Curve numbers may need to be re-visited/increased for this Land Cover based on the model results/calibration. | Disagree, No Changes Made | Comparison to regression flows show calibration is not required | SN | Comment Closed
13 | Are the Curve Numbers reasonable? |  | Fail |  | Other, See Orignator Comments | No comment from QC reviewer, no changes made | SN | Comment Closed
14 | Has the Infiltration Layer been correctly assigned to the geometry |  | Pass
Hydraulics Structures (including dams)
15 | Has a copy of the Terrain layer (Terrain.HydroEnforced) been created ? |  | Pass
16 | Have hydro forcing burn lines been applied at all crossing using the Terrain Channel Modification Tool? Are the bottom width, and max extent widths of each line appropriately estimated to match the current structure size? Changing the side slopes can cause some issues with stability if it is too steep or vertical. |  | Fail | Additional culverts at roadway crossing can be added to the model. Some locations marked in points shapefile. Please check all roadway crossings for culverts and add to the model, unless a threshold has been set to culverts that will not be included in the model. | Agree, Changes Made | Added additional hydroenforcement lines based on QC shapefile. If there is no bridge or culvert visible in aerial imagery a line will not be added. | SN | Closed Comment
17 | Has the Terrain.HydroEnforced.hdf file been correctly assigned to the geometry? |  | Pass
18 | Does the model account for any significant flow-regulating dams? |  | Pass | Flow regulating dams exist in the study area and are accounted for in the model.
19 | Were 2D connections appropriately set-up to model the regulated outflow from the dams? |  | N/A
20 | Are the sources for the dam operations documented? |  | N/A
Other
21 | Are comparison points/lines (i.e., internal 2-D connections) captured and compared against applicable benchmarks? (gage, high water mark, effective BFE, etc.) |  | N/A
22 | If applicable, is the transfer line between this model and a downstream model well away from any boundary condition effects? |  | Pass
23 | Are perimieter boundary conditions applied where flow is leaving the 2D area? |  | Fail | Additional boundary conditions along the periphery of the model boundary are required. | Agree, Changes Made | Boundary condition lines added around perimeter where there was excessive ponding. | SN | Comment Closed
24 | Are boundary coniditions applied such the flow does not build up at the boundary of the 2D mesh? |  | Fail | Boundary condition Outfall_to_1002_A3 needs to be extended. | Agree, Changes Made | Extended boundary condition to include all of 100yr outflow | SN | Comment Closed
25 | Are there any other comments related to the model geometry? |  | Fail | Should the Principal outlets for the dams be included in the model by moditifying the terrain ? | Disagree, No Changes Made | No principal outlet data available | SN | Comment Closed
Total QC citations for this review |  |  | 9
Percent Passing |  |  | 64%
Other Comments

## Unsteady Flow Data
Hydrology
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Brady_1001_A2 |  |  |  |  | Santosh Nishtala |  | 2022-04-12
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
1 | Are the precipitation depths reasonable, and sufficiently documented? Was a reasonable temporal storm distribution used? |  | Pass
2 | Have the flow files for the Pluvial events been assigned correctly ? |  | Pass
3 | Are the flow files based on proper naming convention for the event, precip source ? |  | Pass
4 | Has the SA/2D flow area been assigned the correct DSS precipitation file from the hydrology folder? Has the appropriate event in the DSS file been selected? |  | Pass
5 | Does the model include all required and scoped events / frequencies? |  | Pass | Model includes 100 and 500 yr events, at this stage
6 | Does model plan and precip have same AEP event. For example, 10% AEP plan use 10% AEP rainfall. |  | Pass
7 | Was the appropriate areal reduction factor used for the 2D mesh? |  | N/A
8 | Are the incoming hydrographs being applied properly? (location, shapes, timing, etc.). Confirm that any incoming hydrographs have the same time and magnitude of peak flow by opening up the upstream RAS models |  | Pass
9 | For hydrographs transferred from one RAS model to a downstream RAS model, are the incoming and outgoing hydrographs being applied at a coincident location? |  | Fail | Boundary conditions from 1001_A1are not at coincident locations | Disagree, No Changes Made | In the scope of the project the bc lines do not need to be the exact same. They are in the same streamline and similar locations. | SN | Closed Comment
10 | If using a direct flow transfer from an upstream model, does the time interval for the inflowing hydrograph match the time interval of the extracted hydrograph from the upstream model? |  | Pass
11 | Do all boundary conditions have a hydrograph or elevation/slope data assigned? |  | Pass
12 | Is the downstream boundary condition consistent with ground slope or know downstream WSEL? |  | Pass | Boundary condition is not consistent with ground slope. Was a 0.001 used for slope to be conservative? | Other, See Orignator Comments | Remeasured slope and it is consistent. | SN | Closed Comment
13 | Are there any other comments related to the unsteady flow data? |  | Pass
Joint Probability Checks (Receiving Watersheds Only)
14 | Is the joint probability approach being applied to this watershed? If no, no additional checks are needed. |  | N/A
15 | Is this model for a headwater watershed? If so, no additional JP checks are needed. |  | N/A
16 | Are the Inflow Drainage Area and the Total Drainage Area upstream of each confluence correct? Are all areas computed in square miles? |  | N/A | [5 empty] | Screenshot 1 | Screenshot 2
17 | According to the Total Drainage Area (Atot) and the Drainage Area Ratio (RA), has the correct Watershed Category been assigned to each inflow watershed? (e.g., SS, SL, LS, LL - Refer to Screenshot 1) |  | N/A | [6 empty] | FEMA - 2D Watershed Modeling in HEC-RAS Recommended Practices - Appendix B JP Combinations
18 | For each event in the model, has the correct representative JP event been identified for each inflow watershed? |  | N/A
19 | Have the inflow hydrographs from all inflow watersheds been included in the model? Are the hydrographs for the correct representative JP events? (refer to Screenshot 2 ) |  | N/A
20 | Has each inflow watershed been assigned its own JP flow and plan file? |  | N/A
21 | Has the JP flow file in RAS for each inflow watershed been created with the proper naming convention? (e.g., NRCS_1.0_PCT_0202_A6_JP) |  | N/A
22 | At each confluence, has each fluvial JP inflow hydrograph been shifted so that the peak of the JP inflow hydrograph is aligned with the peak of the pluvial hydrograph? As part of this check, temporarily disable other inflows so they do not interfere. |  | N/A
23 | Has the upstream watershed(s) offset .DSS file been copied to the hydrology folder for the watershed being modeled? |  | N/A
24 | Has a model/plan matrix been included with the model? |  | N/A
25 | Are there any other comments related to the Joint Probability hydrology? |  | N/A
Total QC citations for this review |  |  | 1
Percent Passing |  |  | 96%
Other Comments

## Model Execution and Results
Hydraulics
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Brady_1001_A2 |  |  |  |  | Santosh Nishtala |  | 2022-04-12
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
Model Execution
1 | Is the Diffusion Wave Equation being used? |  | Pass
2 | Is the timestep appropriate for the mesh size and calculated velocities? |  | Pass
3 | Are the Computation Options and Tolerances set to the default values? If no, is it documented and justified? |  | Pass | set to default values
4 | Are the advanced time step control tab settings selected properly ? Are Variable time step parameters reasonable / Meet project needs ? |  | Fail | values used in the model not consistent with the values defined in the process document. The parameters are not consistent between different Brady models. | Disagree, No Changes Made | Values are consistent with process document. | SN | Closed Comment
5 | Are both the "hydrograph output interval" and "mapping output interval" set at a reasonable interval to capture peak flows within the model? |  | Pass
6 | Are there any other comments related to the HEC-RAS Unsteady Plan settings? |  | N/A
Model Results
7 | Does the model run with no cell errors? |  | Pass
8 | Does the model have acceptable volume conservation (less than 3%) |  | Pass | percent error = 0.015%
9 | Is the Courant number generally less than 2 but no greater than 5? |  | Pass | Courant Number is less than 2
10 | Was the model simulation long enough to pass the entire hydrograph(s) through the model? |  | Pass
11 | Is any flow trapped at the 2D boundary? |  | Fail | Flows are trapped along the periphery of the model, and this would be an issue at locations where the trapped areas connect to the streams on the other side of the ridge. Some flow is trapped on the Outfall to 1002_A3 boundary | Agree, Changes Made | BC lines were added along perimeter in areas with excessive ponding | SN | Closed Comment
12 | Are all water-surface elevation convergence warning messages acceptable per computation tolerances? |  | Pass
13 | Are contributing areas contained within the 2D mesh or accounted for with inflow hydrographs? |  | Pass
14 | Are hydrographs at the internal and external boundary conditions smooth? |  | Pass
15 | Check to make sure the computed maximum depth, WSEL, and velocity values are not from numerical surge (i.e. Beginning of model). |  | Pass
16 | Are the water surface and depth grids reasonable with no artificial dips or spikes? |  | Pass
17 | Is there any ponding behind road embankments? If so, is it reasonable or should the model be modified to allow flow through the embankment? |  | Fail | Additional Culverts/Bridges should be added to the model. Some bridges/culverts have been identified in the comments shapefile | Agree, Changes Made | Added hydroenforcement lines based on QC shapefile. | SN | Closed Comment
18 | Do the velocity grids appear reasonable with no unusually high velocity areas? |  | Pass
19 | Have instances of model instabilities at the beginning of the simulation due to initial wetting of a dry grid been addressed? Should a initial condition (wet start) be used? |  | Pass
20 | Are there other comments related to the model results? |  | N/A
Total QC citations for this review |  |  | 3
Percent Passing |  |  | 85%
Other Comments

## Model Validation
Calibration and Validation
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Brady_1001_A2 |  |  |  |  | Santosh Nishtala |  | 2022-04-27
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
Validation is Performed for the 100-yr Only
1 | Is the method and parameters adjusted for model validation documented? |  | Not Applicable for This
2 | Are the modifications to the Curve Number's and/or Manning's n reasonable? |  | Not Applicable for This
3 | Have representative points in the watershed been used to check pluvial flows to confirm they are within the 1% regression bounds? |  | Pass
4 | Do the peak discharges compare favorably to gages, effective studies, INFRM flows, or other approved benchmarks? If not, have attempts been made to calibrate? |  | Pass | Peak Discharges checked against +/-1% regression flows
5 | Are there other comments related to model validation? |  | Pass
Joint Probability Checks
6 | Was the JP rainfall adjusted for calibration? If so, is it within the acceptable limits outlined in Appendix B of FEMA's best practices document? |  | Not Applicable for This
Total QC citations for this review |  |  | 0
Percent Passing |  |  | 100%
Other Comments

## Model Clean-up
Model Clean-up
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Brady_1001_A2 |  |  |  |  | Santosh Nishtala |  | 2022-04-29
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
For Submission to Water Board
1 | HEC-RAS Project files: Have all temporary and interim project files been deleted from the model? (*.p##, *.g##, *.u##) |  | Pass
2 | HEC-RAS Output files: Have all unused output files been deleted from the project directory? (*.O##,*.hyd##, *.c##,*.b##, *.bco##, *.g##.hdf, *.p##.hdf, *.p##.blf, *.IC.O##, *.x##) |  | Pass
3 | HEC-RAS DSS Output file: Have any unused model outputs associated with plans no longer in use been deleted from the HEC-DSS Output file? |  | Pass
4 | HEC-RAS DSS Output file: Do hydrographs for all 7 recurrence interval events (10%, 4%, 2%, 1%, 0.2%, and 1% (+/-)) show up under the "Plot Stage and Flow Hydrographs" option within HEC-RAS? |  | Pass
5 | Have all old versions of geometries and plans been removed from the tree list within RAS Mapper? |  | Pass
6 | Have all non-essential shapefiles been removed from RAS Mapper? |  | Pass
7 | Is there a projection defined within RAS Mapper and is it correct? |  | Pass
8 | Are the terrain and land cover files correctly associated with the geometry and results layers? |  | Pass
9 | Have all folders and/or files that are not necessary for viewing results been deleted from the project folder (i.e. shapefiles, Excel documents, etc.)? |  | Pass
10 | Have all old and non-relevant comments within each unsteady flow plan been removed? |  | Pass
11 | Can the "computation log file" and "runtime messages" be seen for each plan? |  | Pass
Total QC citations for this review |  |  | 0
Percent Passing |  |  | 100%
Other Comments

## List 2
Pass
Fail
N/A
Unsure