## Region 8 H&H QC (hidden)
2-D BLE QC Review Checklist | Date: |  | QC Checkpoint 1 is a project-level QC that should be performed for the entire project footprint prior to executing runs in individual work areas.
Originator: | Wood
QC Checkpoint 1 Review By: |  |  | QC Checkpoint 2 should be completed after the 1% run is calibrated and finalized but prior to the full run of all recurrence intervals.
QC Checkpoint 1 Review Complete Date:
QC Checkpoint 2 Review By: |  |  | QC Checkpoint 3 is the final QC and should be performed after floodplain mapping is complete.
QC Checkpoint 2 Review Complete Date:
QC Checkpoint 3 Review By: |  |  | *If the cells are shaded, it is not necessary to complete that individual check at that checkpoint.
QC Checkpoint 3 Review Complete Date:
QC Check and Description | FEMA Citation | QC Checkpoint 1 |  |  | QC Checkpoint 2 |  |  | QC Checkpoint 3
| Reference | P/F/NA | Comment | Modeler Disposition | P/F/NA | Comment | Modeler Disposition | P/F/NA | Comment | Modeler Disposition
General
Is the product scalable? (i.e., can the model be upgraded to meet regulatory requirements?) | Base Level Engineering Analyses and Mapping 1.0
Is a 2-Dimensional model appropriate for this study? | Guidance for Flood Risk Analysis and Mapping Hydraulics: Two-Dimensional Analysis 2016, Section 1.2.1
Is the correct unit system being used (i.e. SI vs. U.S. Customary)? Options -> "Unit System (US Customary/SI)…"
Terrain
Does the digital terrain cover the entire 2D study area? | SID 50 Two-Dimensional Analysis: 3.1 Topographic Information
Is the model hydrology based on a DEM with an appropriate resolution? (HUC 10 or smaller should use 10-meter or better. Larger than HUC 10 should use 30-meter or better.) | Automated Engineering 2.1.1
Does the model use terrain data at least as current as the current effective study and meet FEMA topo standards? | Hydraulics: Two-Dimensional Analysis 3.1
Is the input topography reasonably dense? (Cell size should be 10-foot or less.) | Hydraulics: Two-Dimensional Analysis 3.1
Have topographic abnormalities been corrected? (No. drops or rises due to underlying data errors.) | Hydraulics: Two-Dimensional Analysis 3.1
Incoming Hydrographs (HMS and/or gage based)
Are the basin delineations reasonable? | SID 61, 90, 93
Are curve numbers reasonable, and sufficiently documented? | SID 57, 59, 61
Are the precipitation depths reasonable, and sufficiently documented? -Confirm that peak rainfall values match HMS output | SID 61, 90, 93
Is the time of concentration determination reasonable for all HMS sub basin elements? | SID 61, 90, 93
Was a reasonable temporal storm distribution used? | SID 61, 90, 93
Was the appropriate areal reduction factor used for any contributing drainage area inflow modeled using rainfall-runoff? | SID 61, 90, 93
If PeakFQ is used, was the correct confidence interval used? (Should be 0.84 instead of default 0.95) | SID 61, 84, 90, 93
Is gage-based hydrology reasonable? Does the gage-analysis follow identified best practices for this project? (If USGS report is available for the gages in this area, the same methodology should be applied to this project, or reasons for deviation should be documented.) | SID 61, 90, 93
Does the Period of Record (POR) for all gage analyses represent current conditions (i.e. post construction of large reservoirs/dams, post construction of major diversion flows, etc.)? | SID 57, 61, 90
Does the shape and time-to-peak of the inflowing hydrograph closely resemble past documented large storm events? | SID 59, 61, 90, 93
If using a direct flow transfer from an upstream model, does the time interval for the inflowing hydrograph match the time interval of the extracted hydrograph from the upstream model? | Two-Dimensional Analysis: 3.5 Hydrologic Inputs
Post Base Flood Reasonability Checks: Does the peak discharge compare favorably to gages, effective studies, regional regression studies, or other approved benchmark? If not, have attempts been made to calibrate? (This applies to both the study area and incoming hydrograph models.) | SID 59 Guidance for Flood Risk Analysis and Mapping General Hydrologic Considerations 7.0
Hydrology
Does the model include all frequencies? (10%, 4%, 2%, 1% and 0.2%) | SID 84
Does the model include the 1%-plus and 1%-minus flood events? | SID 84
Was the appropriate areal reduction factor used for the 2D mesh? | Hydrology: Rainfall-Runoff Analysis 2.1
Are curve numbers reasonable, and sufficiently documented? | SID 57, 59, 81
Are the incoming hydrographs being applied properly? (location, shapes, timing, etc.) - Confirm that any incoming hydrographs have the same time and magnitude of peak flow by opening up the upstream RAS models | SID 61, 90, 93
For hydrographs transferred from one RAS model to a downstream RAS model, are the incoming and outgoing hydrographs being applied a coincident location? | Two-Dimensional Analysis: 3.1 Topographic Information Two-Dimensional Analysis: 3.5 Hydrologic Inputs
If applicable, does the peak discharge compare favorably to gages or effective studies? If not, have attempts been made to calibrate? (This applies to both the study area and incoming hydrograph models.) | SID 59 Guidance for Flood Risk Analysis and Mapping General Hydrologic Considerations 7.0 Two-Dimensional Analysis: 4.0 Calibration of Hydraulic Models
Does the model account for any significant flow-regulating dams? | Automated Engineering 2.1.2
Confirm that precip values are based on DSS file and not hardcoded (or that any hardcoding of precip values are explained in the plan notes).
For all RAS unsteady flow files that use hardcoded precip values, does the timestep match the original derived excess precipitation hyetographs?
For all RAS unsteady flow files that use DSS hydrology, the hardcoded table is empty (and vice versa)
For all RAS unsteady flow files that use DSS hydrology, is the DSS file placed within the RAS model folder?
For all RAS unsteady flow files that use DSS hydrology, confirm that the user defined timestep and start date match the DSS file.
Hydraulics
Does the software meet FEMA's requirements for Nationally and Locally accepted models | https://www.fema.gov/hydraulic-numerical-models-meeting-minimum-requirement-national-flood-insurance-program
Is the 2D mesh reasonably sized to limit cell count and obtain reasonable velocities? | SID 61, 90, 93
Is the timestep appropriate for the mesh size and calculated velocities? | SID 61, 90, 93
Is the model domain delineated properly to capture all contributing flows through rain-on-grid or external hydrograph? | Engineering Judgement
Is the timestep appropriate for the mesh size and calculated velocities (are the associated Courant numbers reasonable)? | Best Practice for Flood Risk Analysis and Mapping 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 2.7.1.2
Is the source of the roughness coefficients or criteria for selecting default roughness coefficients documented in the report? | Automated Engineering 2.2.2.5 Two-Dimensional Analysis 3.4 Energy Loss Coefficients
Do the roughness coefficients correctly represent existing or proposed conditions? | Guidance for Flood Risk Analysis and Mapping Hydraulics: Two-Dimensional Analysis 3.4
Are significant hydraulic structures and embankments accounted for? (i.e., placing breaklines, 2D-structures, terrain processing, etc.) | Automated Engineering 2.2.2.9
Does the model account for any significant flow-regulating dams?
Are comparison points/lines (i.e., internal 2-D connections) captured and compared against applicable benchmarks? (gage, high water mark, effective BFE, etc.) | General Hydraulics Considerations 4.5 Two-Dimensional Analysis 4.0 Calibration of Hydraulic Modes
Are the boundary conditions established, documented, and reasonable? | SID 61, 90, 93 Two-Dimensional Analysis: 3.5.2 Boundary Conditions
Peak outflows have been compared to HEC-HMS's peak outflows (lag time within the HEC-HMS model needs to be updated based on timing of the modeled HEC-RAS flood wave) | SID 61, 90, 93 Two-Dimensional Analysis 4.0 Calibration of Hydraulic Modes
If applicable, is the transfer line between this model and a downstream model well away from any boundary condition effects? | SID 61, 90, 93
Are the initial conditions and final conditions reasonable? | Hydraulics: Two-Dimensional Analysis 3.5.1; General Hydraulic Considerations 9.5
Is the mass balance/volume conservation reasonable? A percent error less than or equal to 1% would be ideal however, values of 2-3% can be acceptable (i.e. rain on grid). Percent error values greater than 3% indicate that there are major problems with the model | TUFLOW User's Manual, Table 14-1
Are all water-surface elevation convergence warning messages acceptable per computation tolerances?
Has the Courant Number been calculated per the 2D equation used? Does the Courant Number justify the 2D cell size and computation time step? | Best Practices 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 2.7.1.2
Was the model simulation long enough to pass the entire hydrograph(s) through the model? Are the hydrographs reasonable when compared to the other return periods? The shapes should be similar, and hydrographs from different events should not intersect unless there is an engineering reason. Peak flows from a lower return period event should not be higher than a higher return period event. | SID 61, 90, 93
Check to make sure the computed maximum depth, WSEL, and velocity values are not from numerical surge (i.e. Beginning of model). | Engineering Judgement
Where applicable, have USGS gage rating curve(s) been used to verify model results? | Best Practices 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 2.7
Has a profile through the enhancement reach been cut in RAS Mapper to review WSEL profiles? Have instances of significant crossing profiles or adverse slopes been investigated for modeling errors? | Guidance for Flood Risk Analysis and Mapping General Hydraulic Considerations. Section 9.8
Are both the "hydrograph output interval" and "mapping output interval" set at a reasonable interval to capture peak flows within the model? Hydrograph Output Interval does not significantly increase the DSS file size for a purely 2D model (DSS entries will be created for 2D connections and boundary conditions, but there are not as many of those as there would be cross sections in a 1D model), so this can be relatively high resolution. For large models, the Mapping Output Interval will have a very large effect on the .hdf's file size and will not affect the "WSE (Max)" raster value. While it may be helpful to have this value set fairly low during model development, dialing this back for submittal (or at least for return periods other then the 1%) can save significant amounts of disk space. | Engineering Judgement
Have instances of model instabilities at the beginning of the simulation due to initial wetting of a dry grid been addressed? Should a initial condition (wet start) be used? | Engineering Judgement
Have instances of significant crossing profiles or adverse slopes been investigated for modeling errors? | Automated Engineering 2.2.2.12; General Hydraulic Considerations 9.3
Have sufficient offset breaklines been added to assure flow is not being restricted upstream? | SID 61, 90, 93
Is the correct equation set being used (Full Momentum vs. Diffusion Wave)?
Has the appropriate flow regime been selected (i.e. subcritical flow vs. mixed flow regime)?
Does mapping compare to effective mapping?
Mapping Outputs
Do the boundaries look reasonable? | Automated Engineering 2.3
Are WSELs in correct order according to return period? i.e. 0.2% > 1% > 2% > 4% > 10% -If there are inflow hydrographs, check at least one cell in each main channel as well as at least one location with flooding that is driven purely by precipitation -Use automated tool to check 500+ points within the fluvial and pluvial controlled flooding areas to confirm that WSELs increase for higher return period events. | SID 78
Model Clean-up / File Management
HEC-RAS Project files: Have all temporary and interim project files been deleted from the model? (*.p##, *.g##, *.u##)
HEC-RAS Output files: Have all unused output files been deleted from the project directory? (*.O##,*.hyd##, *.c##,*.b##, *.bco##, *.g##.hdf, *.p##.hdf, *.p##.blf, *.IC.O##, *.x##)
HEC-RAS DSS Output file: Have any unused model outputs associated with plans no longer in use been deleted from the HEC-DSS Output file?
HEC-RAS DSS Output file: Do hydrographs for all 7 recurrence interval events (10%, 4%, 2%, 1%, 0.2%, and 1% (+/-)) show up under the "Plot Stage and Flow Hydrographs" option within HEC-RAS?
Have all old versions of geometries and plans been removed from the tree list within RAS Mapper?
Have all non-essential shapefiles been removed from RAS Mapper?
Is there a projection defined within RAS Mapper and is it correct?
Are the terrain and land cover files correctly associated to the geometry and results layers?
Have all folders and/or files that are not necessary for viewing results been deleted from the project folder (i.e. shapefiles, Excel documents, etc.)?
Have all old and non-relevant comments within each unsteady flow plan been removed?
Can the "computation log file" and "runtime messages" be seen for each plan?
Additional Comments
Engineering analyses are documented and easily reproducible and include study methods, reasoning for method selection, input data and parameters, sources of data results, and justifications for major changes in computed flood hazard parameters. | SID 61, 186
Model, plans, flows, geometry, etc. names are correct - 1PAC, 1PACPlus, etc. | SID 61, 90, 93
2D Mesh Refinement
Have sufficient breaklines been delineated and added to the 2D mesh within the enhancement area to define topographic restraints such as roads, railroads, dams, levees, and natural high ground areas? | Best Practices 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 2.2.1
Has an appropriate cell spacing on either side of the breaklines been chosen to mimic topographic restraint? | Best Practices 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 2.2.1
Is the 2D cell size within the enhanced area of adequate size to describe the water surface slope and potential changes in water surface slope (i.e. is enough detail being captured by a reduced cell size)? | Best Practices 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 2.2.1
Is the computational timestep selected appropriate according to the enhanced 2D mesh? | Best Practices 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 2.7.1.2
Are offset breaklines utilized in accordance with the project guidance to allow flow to pass high ground/embankments where information on detailed hydraulic structures doesn't exist outside of the detailed enhancement reach? | SD LSAE Guidance
Structures within 2D Domain
Does the vertical datum of the structures/surveys match the vertical datum of the terrain? | Engineering Judgement |  |  |  | N/A
Do structures added as internal connections inside the 2D domain reflect the field survey data, as-built drawings, or desktop analysis? |  |  |  |  | N/A
Have internal connections been enforced as breaklines into the 2D mesh |  |  |  |  | N/A
Have reasonable values been entered into the internal connection's Htab Parameters to define the limits of the connection & structure | HEC-RAS 5.0 User's Manual [6-149 & 8-22] |  |  |  | N/A
Do the 2D cells just upstream and downstream of the structure have adequate volume at any given time step and have been properly aligned to the structure? | Best Practices 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 2.51 |  |  |  | N/A
Internal Connection: Has an appropriate overflow computation method been selected (2D equation or weir equation) If the weir equation has been selected is the weir coefficient of discharge reasonable | HEC-RAS 5.0 2D Modeling User's Manual [3-67] |  |  |  | N/A
Does the top of road elevation and rail data match the field survey |  |  |  |  | N/A
Culverts: Do the culvert invert elevations match the field survey |  |  |  |  | N/A
Culverts: Does the culvert length match the field survey |  |  |  |  | N/A
Culverts: Do the culvert dimensions and shape match the field survey |  |  |  |  | N/A
Culverts: Have the appropriate FHWA Chart & Scale #'s been selected per the field survey photographs | HEC-RAS 5.0 Reference Manual, [6-30] |  |  |  | N/A
Culverts: Has an appropriate entrance loss coefficient been selected per the field survey | HEC-RAS 5.0 Reference Manual, Chpt. [6-28, Tables 6-3, 6-4, & 6-5 ] |  |  |  | N/A
Culverts: If the surveyed culvert invert elevation is below the DEM elevation, has appropriate depth to block the culvert portion below ground been described? | Best Practices 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 2.5.1 |  |  |  | N/A
Bridges modeled as culverts: Do the number of culvert barrels mimic the number of openings between piers? | Best Practices 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 2.5.1 |  |  |  | N/A
Bridges modeled as culverts: Does the distance between the culverts represent the surveyed pier width? | Best Practices 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 2.5.1 |  |  |  | N/A
Bridges modeled as culverts: Does the FHWA chart & scale numbers adequately describe bridge? | Best Practices 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 2.5.1 |  |  |  | N/A
Bridges modeled as culverts: Does the entrance loss coefficient adequately describe the upstream face of the bridge | Best Practices 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 2.5.1 |  |  |  | N/A
Bridges modeled as culverts: Do the Manning's n for the bottom and top of the culvert barrel accurately describe the bridge low chord and the water's surface? | Best Practices 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 2.5.1 |  |  |  | N/A
Bridges modeled as culverts: If the surveyed culvert invert elevation is below the DEM elevation has appropriate depth to block the culvert portion below ground been described? | Best Practices 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 2.5.1 |  |  |  | N/A
Bridges modeled as gates: Do the gate dimensions accurately describe the bridge dimensions | Best Practices 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 2.5.1 |  |  |  | N/A
Bridges modeled as gates: Do the gate dimensions accurately describe the bridge dimensions | Best Practices 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 2.5.1 |  |  |  | N/A
Bridges modeled as gates: Has an appropriate boundary condition been set up to operate the opening/closing of the gate? The gate should be modeled as being fully open during the course of the simulation | Best Practices 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 2.5.1 |  |  |  | N/A
Have bridge results for selected reaches(modeled as culverts or gates) been verified through 1D modeling methods? | Compass FEMA Region VIII TO Technical Proposal |  |  |  | N/A
Are the entrance and exit locations of flow for all 2D internal structures reasonable and properly span terrain features? | Engineering Judgement |  |  |  | N/A
Non-Conveyance Areas
If non-conveyance areas have been modeled, has sufficient documentation been provided describing the reasoning, location, and technique? | Hydraulics: 2D Analysis Guidance Section 3.3
Energy Loss Coefficients (Manning's N)
Has a roughness coefficient been assigned to each cell | Hydraulics: 2D Analysis Guidance Section 3.4
Are roughness coefficients properly documented | Hydraulics: 2D Analysis Guidance Section 3.4
Have roughness coefficients been validated through calibration (where calibration data are available)? | Hydraulics: 2D Analysis Guidance Section 3.4
Floodway Determination
Has the model geometry associated with the base flood been QC'd and approved for floodway determination |  |  |  |  | N/A
Has the Depth x Velocity product also know as a Flood Severity raster been created and categorized | Guidance Flood Depth and Analysis Grids Section 8.0 |  |  |  | N/A
Has the floodway been defined using the Depth x Velocity product from 1% annual chance event (base flood) | Best Practices 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 3.3 |  |  |  | N/A
Has a raised/walled terrain file been generated that represents the "encroached" floodplain? | Best Practices 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 3.5.2 |  |  |  | N/A
Is the base flood geometry associated with the raised/walled terrain file? |  |  |  |  | N/A
Does the floodway surcharge meet local floodway criterion (i.e. 1.0 FT) at every 2D cell within the defined floodway | Best Practices 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 3.4 |  |  |  | N/A

## Model Review
2D BLE QC Review Checklist
Project Name: | TWDB MAST#2 |  | Watershed Name: | Cibolo HUC-8 #12100304
Modeled By: | Andrew Howe |  | Model Review By: | Paul Giany
Initial Model Review Date: | 2021-01-04 |  | Final Model Review Date:
QC Checkpoint and Description | FEMA Citation |  | Model Review
| Reference | P/F/NA | Comment | Response | Backcheck
Terrain
Does the digital terrain cover the entire 2D study area? | SID 50 Two-Dimensional Analysis: 3.1 Topographic Information | P
Is the model hydrology based on a DEM with an appropriate resolution? (HUC 10 or smaller should use 10-meter or better. Larger than HUC 10 should use 30-meter or better.) | Automated Engineering 2.1.1 | P
Does the model use terrain data at least as current as the current effective study and meet FEMA topo standards? | Hydraulics: Two-Dimensional Analysis 3.1 | P
Is the input topography reasonably dense? (Cell size should be 10-foot or less.) | Hydraulics: Two-Dimensional Analysis 3.1 | P
Have topographic abnormalities been corrected? (No. drops or rises due to underlying data errors.) | Hydraulics: Two-Dimensional Analysis 3.1 | P
Hydraulics
Does the model include all frequencies? (10%, 4%, 2%, 1% and 0.2%; 1%-plus and 1%-minus) | SID 84 | F | Only contains the 100-yr storm event. | HEC-HMS model updated to include all necessary storm events including the 10, 25, 50, 100-, 100, 100+, 500yr. Plans created to reflect each. Not run during model validation, only evaluating the 100yr storm event. Plans will be run in future (if necessary). | √
Is the model domain delineated properly to capture all contributing flows through rain-on-grid or external hydrograph? | Engineering Judgement | P
For all RAS unsteady flow files that use hardcoded precip values, does the timestep match the original derived excess precipitation hyetographs? |  | P
For all RAS unsteady flow files that use DSS hydrology, the hardcoded table is empty (and vice versa) |  | P
For all RAS unsteady flow files that use DSS hydrology, is the DSS file placed within the RAS model folder? |  | F | References within the hydrologic model folder. | Placed DSS reference files in the following folder within the HEC-RAS files … W:\Citrix\33000s\33606\008\HEC-RAS_vXX\Working\Cibolo\RAS_Model\Hydrology | √
For all RAS unsteady flow files that use DSS hydrology, confirm that the user defined timestep and start date match the DSS file. |  | P | DSS reference needs to be updated. | DSS references updated in Unsteady Flow Data description and Precipitation Boundary Condition. | √
Is the 2D mesh reasonably sized to limit cell count and obtain reasonable velocities? | SID 61, 90, 93 | P
Is the timestep appropriate for the mesh size and calculated velocities? | SID 61, 90, 93 Best Practice for Flood Risk Analysis and Mapping 2D Modeling: Zone AE Upgrades and Floodways v2.0 Section 2.7.1.2 | F | The 1 minute time step is closer to meeting the courant condition, however, there are still areas that have a courant number above 2. Please see screenshot #1 in the supporting data tab. | BLE guidance has suggested that Courant condition can approach 5, but beginning reduction of computational timestep to 20s to observe changes/reduction of Courant number throughout model. Will compare to "supporting data" images. If necessary, additional cell edits will be made. All final models will have the 20s computational interval, due to size of model, low time step will result in excessive model runtime. | √
Is the model domain delineated properly to capture all contributing flows through rain-on-grid or external hydrograph? | Engineering Judgement | P
Do the roughness coefficients correctly represent existing conditions? Are roughness coefficients properly documented? | Guidance for Flood Risk Analysis and Mapping Hydraulics: Two-Dimensional Analysis 3.4 | F | Main channel roughness zones are very narrow compared to the normal water surface seen in the aerial imagery. Consider widening the channel roughness zones and update the manning layer accordingly. Please see screenshot #2 in the supporting data tab. | Created a new Mannings-N layer (ManningsN_Widened2D). Created new centerline buffer with three regions (main stem, main tribs, connecting tribs with subsequent buffers of 45', 20', and 10' to "mimic" approx. channel widths). This Mannings-N layer has been validated as the go-by for Cibolo, used in final modeling. | √
Are significant hydraulic structures and embankments accounted for? (i.e., placing breaklines, 2D-structures, terrain processing, etc.) Significant may include roads, railroads, dams, levees, and natural high ground areas. | Automated Engineering 2.2.2.9 | P
Does the model account for any significant flow-regulating dams? |  | P
Are the boundary conditions established, documented, and reasonable? | SID 61, 90, 93 Two-Dimensional Analysis: 3.5.2 Boundary Conditions | P
Are the initial conditions and final conditions reasonable? | Hydraulics: Two-Dimensional Analysis 3.5.1; General Hydraulic Considerations 9.5 | P
Is the mass balance/volume conservation reasonable? A percent error less than or equal to 1% would be ideal however, values of 2-3% can be acceptable (i.e. rain on grid). Percent error values greater than 3% indicate that there are major problems with the model | TUFLOW User's Manual, Table 14-1 | P | Volume balance for each computation step: 3 min: 0.752% 2 min: 0.265% 1 min: 0.0347% 20-sec: 0.003% | Will update with additional runs for backcheck (i.e. lower computational timesteps-20s) | √
Was the model simulation long enough to pass the entire hydrograph(s) through the model? | SID 61, 90, 93 | P
Are the hydrographs reasonable when compared to the other return periods? The shapes should be similar, and hydrographs from different events should not intersect unless there is an engineering reason. Peak flows from a lower return period event should not be higher than a higher return period event. | SID 61, 90, 93 | P
Are both the "hydrograph output interval" and "mapping output interval" set at a reasonable interval to capture peak flows within the model? | Engineering Judgement | P
Have sufficient offset breaklines been added to assure flow is not being restricted upstream? | SID 61, 90, 93 | P
Check to make sure the computed maximum depth, WSEL, and velocity values are not from numerical surge (i.e. Beginning of model). | Engineering Judgement | P
Have instances of model instabilities at the beginning of the simulation due to initial wetting of a dry grid been addressed? Should a initial condition (wet start) be used? | Engineering Judgement | P
If non-conveyance areas have been modeled, has sufficient documentation been provided describing the reasoning, location, and technique? | Hydraulics: 2D Analysis Guidance Section 3.3 | P
Are all water-surface elevation convergence warning messages acceptable per computation tolerances? |  | P
Results Validation
If applicable, does the peak discharge compare favorably to gages or effective studies? If not, have attempts been made to calibrate? (This applies to both the study area and incoming hydrograph models.) | SID 59 Guidance for Flood Risk Analysis and Mapping General Hydrologic Considerations 7.0 Two-Dimensional Analysis: 4.0 Calibration of Hydraulic Models | N/A | The discharges in the model are significantly higher in the upper portion of the basin compared to the gage data. This could be attributed to the short time span the gages have been put in place (since 2014). | USGS gages were determined not to be the most relaible dataset for comparison, especially in Cibolo North. It was determined that comparisons to available FIS data was most appropriate moving forward, model validated/compared to this data. New Mannings-N layer, geometry edits (cells, v-notches, breaklines, etc.) led to approval of final model conditions (100 year with Cibolo_Geometry_RB2DN). | √
Are comparison points/lines (i.e., internal 2-D connections) captured and compared against applicable benchmarks? (gage, high water mark, effective BFE, etc.) Are the results justified? | General Hydraulics Considerations 4.5 Two-Dimensional Analysis 4.0 Calibration of Hydraulic Modes | N/A
Does mapping compare to effective mapping? |  | N/A | Suggest rendering using sloping method. | Sloping method will be used as default for exports. | √
Additional Comments
Engineering analyses are documented and easily reproducible and include study methods, reasoning for method selection, input data and parameters, sources of data results, and justifications for major changes in computed flood hazard parameters. | SID 61, 186 | P

## Supporting Data
1
2