## Instructions
Engineering Files QC Checklists
1 | Please insert Study Name on Sign Off tab. This will automatically populate the remainder of the spreadsheets. Please insert the Feme Case No in front of the document name, and save the file with that name on your network.
2 | Please enter name (and initials) on Sign Off tab. If additional lines are required, copy the last line and insert below. As you complete the spreadsheets, you will need only to insert your initials.
3 | Please enter the name of the basin, stream reach, or coastal beach that you are reviewing in the appropriate space at the top of the sheet. The first of each set of forms requires names and dates to be added at the top of each column.
4 | Technical Review refers to the final review of work. This will be accomplished by an independent team of subject matter experts. Work should be considered as complete and ready to submit when submitted to this team. Be certain to add initials to the form.
5 | QA Verification refers to the determination that the work is ready to deliver. It is accomplished by a representative of the QA Manager. This review is cursory and involves review of records and spot checks of errors that appear to be systemic. The purpose of this review is to first ensure that all errors have been corrected, files are ready to be submitted and all records are ready for archival. Secondly, the review will focus on whether errors are systemic (requiring adjustment to procedure, or perhaps further training) or random (requiring review of schedules, budgets, etc.) Be certain to add initials to the form.
6 | Should there be a requirement to review data a second (or more) time, simply copy the appropriate columns and insert them to the right of the original review columns.
7 | A separate worksheet may be required for each basin, stream reach or model, and coastal beach. In this case copy the worksheet and insert into the workbook in the proper sequential order. Please label the tab with the basin name, stream reach or model number(s), or beach to make use of the workbook easier.
8 | Please indicate status of each item by responding P (Pass), F (Fail), NA (Not applicable).
9 | When your review is complete and you are satisfied with the quality of the work, please sign a hard copy of the sign off sheet. Please be certain to retain the signed sheet with other project documents and be sure the next reviewer knows where to locate it. QA Verification reviewer, please scan the sign off sheet and add to the document files for the project.

## Sign off-QC Stamp
ATKINS QUALITY REVIEW CHECKLIST SIGN OFF FORM
Study / Stream Name | TWDB_TO_6/Lower_Pecos_Upper
Deliverable
MIP Case #:
PM:
QC REVIEW ACTIVITY
Ready for QC | *Originator / Date : | Abhimanyu Jha
2024-03-28
QC Review | Reviewer : | Manikanteswar Ramineni
| Date: | 2024-04-04
Changes Made | *Originator/ Date : | Abhimanyu Jha
2024-05-05
QC Verification | *QC Reviewer: | Shrinivas Kaulgud /Mohamad Rouhnia
| Date: | 2024-05-15
PQM Approval | *QA: | Sirish Madichetti
| Date: | 2024-06-01

## HEC-HMS
Hydrology
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
TWDB_TO_6/Lower_Pecos_Upper |  |  |  |  | Mohamad Rouhnia |  | 2024-05-15
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
1 | Is correct projection used for HMS model and subbasins loaded in the HMS. |  | Pass
2 | Does the HMS subbasins match model domain extent |  | Pass
3 | Are NOAA 14 grids for all duration and AEPs loaded in the HMS |  | Pass
4 | Is precipitation type is set to Frequency Storm |  | Pass
5 | Are precipitation depths shown in frequency storm increasing with duration and with AEP |  | Pass
6 | Have precipitation plots created |  | Pass
7 | Spot few subbasins precipitation depths against NOAA 14 website to identify any errors in model setup |  | Pass | [5 empty] | 1% plus and 1% minus with 5% reduction
8 | Is 1% plus and 1% minus values for each duration calculated correctly |  | Fail | Apply 5% reduction to 1% rainfall and recalculate 1% plus and 1% minus values | Agree, Changes Made | Chnages Made | svk | done
9 | Is either incremental or cumulative precipitation hyetographs for any event including 1% plus and 1% minus crossing |  | Fail | 1% minus cross 4% during non peak hours for some subbasins. Please document in report | Agree, Changes Made | Updated results do not have crossing profiles | svk | done
10 | Model, plans, elements named properly per guidance |  | Pass
11
12
13
Total QC citations for this review |  |  | 2
Percent Passing |  |  | 92%
Other Comments

## Model Geometry
Hydraulics
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
TWDB_TO_6/Lower_Pecos_Upper |  |  |  |  | Manikanteswar Ramineni/Shrinivas Kaulgud /Mohamad Rouhnia |  | 2024-05-15
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
RAS Mapper Setup
1 | Is the model projection correct? |  | Pass
2 | Does the terrain and model projections match |  | Unsure - See Reviewer Comments | Terrain projection missing Authority and WKID | Agree, Changes Made | The original terrain tif projection is correct. HEC-RAS changed the authority to custom. | SVK
3 | Is the model geometry linked to Terrain, Land Cover, Infiltration and imperviousness layers |  | Pass
4 | Do the model results show Terrain, Landcover, Infiltration layers, and Imperviousness linked |  | Fail | For 1PCT and 10 PCT are not linked to Hydroconditioned terrain. | Other, See Originator Comments | It was our understanding that the geometry file should be linked to hydro conditioned terrain and results need to be associated to original terrain. Please confirm | SVK | Very important: To run model use hydro conditioned terrain to extract grids for mapping use original terrain. Done
2D Mesh
5 | Does the digital terrain model input for the 2D model cover the entire 2D study area? |  | Pass
6 | Is the 2D mesh reasonably sized to limit cell count and obtain reasonable velocities? (Generally 100 -300' and max velocities less than 15-20 fps ) |  | Pass
7 | Is the model domain delineated properly to capture all contributing flows through rain-on-grid or external hydrograph? |  | Pass
8 | Are the break lines and refinement regions enforced properly |  | Fail | Please adjust cells at intersections to make sure cells align with break line. Especially on Roads Tx-285 and TX-302. For next model onwards please be consistent with the near repeats (i.e. for both break lines and refinement regions need to be consistent) Use comments shp to add missing break lines, review for culvert crossings and add as burn lines where present | Other, See Originator Comments | All near repeats were kept as 0, as per the directions. Planarization was carried out on the break line shapefile in order to break the roads at the intersection. We'll further refine as needed. | MR | done
9 | Overlap with adjacent model is sufficient to achieve tie-in at main outflow and perimeter ponding locations |  | Pass
10 | Are there any 2D mesh errors? |  | Pass
Break lines
11 | Are break lines sufficiently detailed to capture features (thalweg, roads, banks, berms, etc.)? |  | Pass
12 | Are break lines consistent with the terrain data? |  | Pass
13 | Are break lines added such that the flow is not leaking. |  | Fail | see shapefile for example issues | Agree, Changes Made | Changes made | MR | done
14 | Do the stream lines continue to confluence and not end in the middle. (Exception roadway crossings) |  | Pass
15 | Are break lines for spillways added |  | Pass
16 | Are overlapping or very close break lines reviewed and cleaned, break line conflicts resolved and all break line planarized |  | Fail | Please adjust cells at intersections to make sure cells align with break line. Especially on Roads Tx-285 and TX-302see shapefile for example issues | Other, See Originator Comments | Please refer to Originators Comments from ID 8 | MR | done
Refinement Region
17 | Are refinement regions around major channel reaches, urban areas (>1K population), and major reservoirs (>5 ac) included |  | Pass
18 | Break line and refinement region conflicts were reviewed and resolved |  | Pass
19 | Small holes in refinement regions filled, and small isolated refinement regions deleted |  | Pass
Manning's n
20 | Is the source of the roughness coefficients or criteria for selecting default roughness coefficients documented? |  | Pass
21 | Are channel Manning's n values reasonable? Are channel classification polygons continuous and have no gaps at roadway crossings etc. |  | Fail | No classification polygons present. The | Other, See Originator Comments | We have accounted for channel in the manning's n raster. We can provide a separate channel classification polygon if needed for the next submittal. | MR | done
22 | Is the Manning's n dataset associated with the geometry file? |  | Pass
Infiltration Layer / Impervious layer
23 | Are Curve Numbers (CN) and % imperviousness values reasonable, and sufficiently documented? Do the CN and % imperviousness values match TWDB guidance |  | Pass
24 | Are the adjustments applied to original Curve Numbers reasonable? Is the minimum CN higher than 30 even after adjustments. |  | Pass
25 | Has the Infiltration Layer and impervious layer been correctly assigned to the geometry |  | Pass
SA/2D Connections and BCLines
26 | Are the SA/2D connections added near the model outflow to transfer flows with adjacent model. Are SA/2D connections well away from any boundary condition effects to no impact on flow or WSE? |  | Fail | No SA2D condition at the outflow. | Agree, Changes Made | Added Sa/2D | MR | done
27 | SA/2D lines are perpendicular to flow and contain 500-Yr or highest floodplain |  | Fail | See image. | Agree, Changes Made
28 | Are multiple Sa/2D connections required for split areas to correctly transfer flow downstream |  | Fail | Multiple required, none present. | Agree, Changes Made
29 | Are SA/2D from upstream model match with inflow BCLines in downstream model. |  | Unsure - See Reviewer Comments | no upstream model available. Make sure it matches Delaware model. | Agree, Changes Made | SA/2D from Delaware model was received and BC line of LP-U model was revised accordingly. | MR | done
30 | Are the BcLines for main outflow separated from perimeter areas. For areas with major overflow at perimeter are BCLines split |  | Pass
31 | Are Bclines added for any receiving inflows. |  | Unsure - See Reviewer Comments | Not referenced from a hydrograph, values entered manually. | Agree, Changes Made | Added Delaware inflow hydrograph | MR | done
32 | SA/2D connections are added at validation locations such as gage, high water mark, effective BFE, etc. |  | Fail | No SA2D of Reference line added at gage location. | Agree, Changes Made
33 | All SA/2D and BCLines enforced properly |  | Unsure - See Reviewer Comments | reduce the size of inflow BC lines to better capture low flows. | Other, See Originator Comments | SA/2D from Delaware model was received and BC line of LP-U model was revised accordingly. For inflow from Pecos, the BC line was sized such that the 500-yr floodplain is contained. | MR | done
34 | Are perimeter boundary conditions applied where flow is leaving the 2D area? |  | Pass
Terrain Modifications
35 | Has a copy of the Terrain layer (Terrain.HydroEnforced) been created ? |  | Pass
36 | Have hydro forcing burn lines been applied at major crossing using the Terrain Channel Modification Tool? Are the bottom width, and max extent widths of each line appropriately estimated to match the current structure size? Changing the side slopes can cause some issues with stability if it is too steep or vertical. |  | Unsure - See Reviewer Comments | See Shapefile for more examples. Please add more burn lines to make sure flow is not ponding against roads. Especially on Roads Tx-285 and TX-302 | Agree, Changes Made
37 | Has the Terrain.HydroEnforced.hdf file been correctly assigned to the geometry? |  | Unsure - See Reviewer Comments | For 1PCT and 10 PCT are not linked to Hydroconditioned terrain. | Other, See Originator Comments | It was understood that the geometry file should be linked to hydro conditioned terrain and results need to be associated to original terrain. Please confirm | MR | done
38 | Are there any areas with ponding depths more than 2.5' where culverts are present |  | Unsure - See Reviewer Comments | See shapefile. Comment "Ponding" | Agree, Changes Made
Major Hydraulics Structures (dams)
39 | Does the model account for any significant flow-regulating dams? Are there in the study that should be modeled. |  | Fail | Please use rating curve form Red bluff study and Match initial elev. to the study. | Agree, Changes Made | Rating curve has been applied to Red Bluff Dam SA/2D connection at the center of the main spillway | MR | done
40 | Were 2D connections appropriately set-up to model the regulated outflow from the dams? |  | Fail | Did we check the Max elevations with the PMF Study ?. Also see image. | Other, See Originator Comments | HDR's HMS model result has only been used for shape of the hydrograph. | MR | done
41 | Are the sources for the dam operations documented? |  | Fail | Add documentation to report from the Red Bluff PMF study. | Other, See Originator Comments | Report results not used in the analysis except for dam rating curve and in hydrograph development. | MR | done
42 | Are the rating curves calculated or obtained reasonable. Is the computed BLE WSE close to peak stages reported by InFRM or other sources |  | Fail | Add rating curve. | Agree, Changes Made | Rating curve has been applied to Red Bluff Dam SA/2D connection at the center of the main spillway | MR | done
Other
42 | Are there any other comments related to the model geometry?
43
44
45
46
Total QC citations for this review |  |  | 12
Percent Passing |  |  | 52%
Other Comments See below
| 1. Review mesh for missing break lines. Focus on floodplains for larger streams with more than 1 sq. mi areas. Sample locations added in the attached shp. See if there are any culverts present along these and add burn lines If needed. |  | Fail
| 2. Don’t apply any areal reduction factor in HEC-HMS. Combine PRECIP_INC data for all events into one DSS and multiply by 0.95 factor to obtain final precip depths for AEP events. 1% plus and 1% minus comment in HMS tab. |  | Fail | [5 empty] | Layer association
| 3. Associate LandCover layer with % impervious layer as shown in screenshot below. Currently you have manning’s. |  | Fail
| 4. LandCover and infiltration grids should not have channel classification polygons. Delete the channel classification polygons from LandCover grid and recreate infiltration layer by using updated LandCover and soils. Screenshot of how grids look below. Your Manning’s n layer is good. |  | Fail
| 5. Rename Sa/2Ds to use short name of the gage /stream/ location identifier. |  | Fail
| 6. Update the flow rates in the flow area plot spreadsheet. Add all validation locations to this spreadsheet. |  | Fail | [5 empty] | Grids Setup
| 7. Add discussion in the memo that 1955 flow rate of ~40,000 cfs for salt Screwbean could be overestimated as flow rate of ~8,000 cfs is recorded on Pecos River from the same event located just downstream of Salt Screwbean -Pecos confluence. We validated to lower bound as 1955 peak significantly skewed the 1% gage flow. |  | Fail
| 8. Include HDR report and HMS models under supplemental data folder. |  | Fail

## Unsteady Flow Data
Hydrology
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
TWDB_TO_6/Lower_Pecos_Upper |  |  |  |  | Mohamad Rouhnia |  | 2024-05-15
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
1 | Are the precipitation depths reasonable, and sufficiently documented? Explain anything other than frequency storm used for temporal distribution? |  | Pass
2 | Have the flow files for all events been assigned correctly to matching plans, to HMS or RAS output DSS, and not hard coded |  | Pass
3 | Are the flow files based on proper naming convention for the event, precip source ? |  | Pass
4 | Has the 2D flow area been assigned the correct DSS precipitation file from the hydrology folder? Has the appropriate event in the DSS file been selected? |  | Pass
5 | Does the model include all required and scoped events / frequencies? |  | Pass
6 | Does model plan and precip have same AEP event. For example, 10% AEP plan use 10% AEP rainfall. |  | Pass
7 | Was the areal reduction factor necessary? |  | Pass
8 | Is the precipitation depth across domain vary more than 10%. If so was spatially varied rainfall used? If not explain reason |  | Fail | Spatially varied rainfall required for this domain. | Agree, Changes Made | Spatialy varied rainfall is being carried out based on the memo developed on Apr 9, 2024 by ATKINS | MR | done
9 | Is initial conditions/ elevations used for any dams or other locations in the model |  | Pass
10 | Are the incoming hydrographs being applied properly? (location, shapes, timing, etc.). Confirm that any incoming hydrographs have the same time and magnitude of peak flow by opening up the upstream RAS models |  | Pass
11 | For hydrographs transferred from one RAS model to a downstream RAS model, are the incoming and outgoing hydrographs being applied at a coincident location? The flows from upstream and downstream model cannot have more than 5% difference |  | Pass
12 | Do all boundary conditions have a hydrograph or elevation/slope data assigned? |  | Pass
13 | Is the downstream boundary condition consistent with ground slope or known downstream WSEL? |  | Pass
14 | Are there any other comments related to the unsteady flow data? |  | Pass
15
Total QC citations for this review |  |  | 1
Percent Passing |  |  | 96%
Other Comments

## Model Execution and Results
Hydraulics
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
TWDB_TO_6/Lower_Pecos_Upper |  |  |  |  | Mohamad Rouhnia |  | 2024-05-15
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
Model Execution
1 | Is the Diffusion Wave Equation being used? |  | Pass
2 | Is the timestep appropriate for the mesh size and calculated velocities? |  | Pass
3 | Are the Computation Options and Tolerances set to the default values? If no, is it documented and justified? |  | Pass
4 | Are the advanced time step control tab settings selected properly ? Are Variable time step parameters reasonable / Meet project needs ? |  | Pass
5 | Are both the "hydrograph output interval" and "mapping output interval" set at a reasonable interval to capture peak flows within the model? |  | Pass
Model Results
6 | Does the model run with no cell errors? |  | Pass
7 | Does the model have acceptable volume conservation (less than 3%) |  | Pass
8 | Is the Courant number generally less than 2 but no greater than 5? |  | Pass
9 | Does the model run time longer than 12 Hrs? The model run cannot be longer than 24 Hrs. |  | Pass
9 | Was the model simulation long enough to pass the entire hydrograph(s) through the model? At least 24 Hrs after main peak, carefully look at multiple peak situations |  | Pass
10 | Is any flow trapped at the 2D boundary? |  | Pass
11 | Are all water-surface elevation convergence warning messages acceptable per computation tolerances? |  | Pass
12 | Are contributing areas contained within the 2D mesh or accounted for with inflow hydrographs? |  | Pass
13 | Are hydrographs at the internal and external boundary conditions smooth? |  | Pass
14 | Are there any crossing profiles for flow or stage hydrographs between any plans. This should also include 1% plus and 1% minus plans and not just AEP |  | Pass
15 | Check to make sure the computed maximum depth, WSEL, and velocity values are not from numerical surge (i.e. Beginning of model). |  | Pass
16 | Are the water surface and depth grids reasonable with no artificial dips or spikes? |  | Pass
17 | Is there any deep ponding areas (>3') behind road embankments? If so, is it reasonable or should the model be modified to allow flow through the embankment? |  | Pass
18 | Do the velocity grids appear reasonable with no unusually high velocity areas? |  | Pass
19 | Have instances of model instabilities at the beginning of the simulation due to initial wetting of a dry grid been addressed? Should a initial condition (wet start) be used? |  | Pass
20 | Are there other comments related to the model results? |  | Pass
Total QC citations for this review |  |  | 0
Percent Passing |  |  | 100%
Other Comments

## Model Validation
Validation
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
TWDB_TO_6/Lower_Pecos_Upper |  |  |  |  | Mohamad Rouhnia |  | 2024-05-15
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
Validation is Performed for the 100-yr Only
1 | Is the method and parameters adjusted for model validation documented? |  | Pass
2 | Are the modifications to the Curve Number's and/or Manning's n reasonable? |  | Pass
| Was areal reduction applied to achieve validation |  | Pass
3 | Have representative points in the watershed been used to check pluvial flows to confirm they are within the 1% Gage/ regression bounds? |  | Pass
4 | Do the peak discharges compare favorably to gages, effective studies, INFRM flows, or other approved benchmarks? If not, have attempts been made to validate? |  | Pass
5 | Are there other comments related to model validation? |  | Pass
Total QC citations for this review |  |  | 0
Percent Passing |  |  | 100%
Other Comments

## Model Clean-up
Model Clean-up
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
TWDB_TO_6/Lower_Pecos_Upper |  |  |  |  | Mohamad Rouhnia |  | 2024-05-15
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
For Submission to Water Board
1 | HEC-RAS Project files: Have all temporary and interim project files been deleted from the model? (*.p##, *.g##, *.u##) |  | Pass
2 | HEC-RAS Output files: Have all unused output files been deleted from the project directory? (*.O##,*.hyd##, *.c##,*.b##, *.bco##, *.g##.hdf, *.p##.hdf, *.p##.blf, *.IC.O##, *.x##) |  | Pass
3 | HEC-RAS DSS Output file: Have any unused model outputs associated with plans no longer in use been deleted from the HEC-DSS Output file? |  | Pass
4 | HEC-RAS DSS Output file: Do hydrographs for all 7 recurrence interval events (10%, 4%, 2%, 1%, 0.2%, and 1% (+/-)) show up under the "Plot Stage and Flow Hydrographs" option within HEC-RAS? |  | Pass
5 | Have all old versions of geometries and plans been removed from the tree list within RAS Mapper? |  | Pass
6 | Have all non-essential shapefiles been removed from RAS Mapper? |  | Pass
7 | Are the terrain and land cover files correctly associated with the geometry and results layers? |  | Pass
8 | Have all folders and/or files that are not necessary for viewing results been deleted from the project folder (i.e. shapefiles, Excel documents, etc.)? |  | Pass
9 | Have all old and non-relevant comments within each unsteady flow plan been removed? |  | Pass
10 | Can the "computation log file" and "runtime messages" be seen for each plan? |  | Pass
Total QC citations for this review |  |  | 0
Percent Passing |  |  | 100%
Other Comments

## Drop Down List
Pass
Fail
Unsure - See Reviewer Comments
Not Applicable for This
Agree, Changes Made
Disagree, No Changes Made
Other, See Orignator Comments