## Instructions
Engineering Files QC Checklists
1 | Please insert Study Name on Sign Off tab. This will automatically populate the remainder of the spreadsheets. Please insert the Feme Case No in front of the document name, and save the file with that name on your network.
2 | Please enter name (and initials) on Sign Off tab. If additional lines are required, copy the last line and insert below. As you complete the spreadsheets, you will need only to insert your initials.
3 | Please enter the name of the basin, stream reach, or coastal beach that you are reviewing in the appropriate space at the top of the sheet. The first of each set of forms requires names and dates to be added at the top of each column.
4 | Technical Review refers to the final review of work. This will be accomplished by an independent team of subject matter experts. Work should be considered as complete and ready to submit when submitted to this team. Be certain to add initials to the form.
5 | QA Verification refers to the determination that the work is ready to deliver. It is accomplished by a representative of the QA Manager. This review is cursory and involves review of records and spot checks of errors that appear to be systemic. The purpose of this review is to first ensure that all errors have been corrected, files are ready to be submitted and all records are ready for archival. Secondly, the review will focus on whether errors are systemic (requiring adjustment to procedure, or perhaps further training) or random (requiring review of schedules, budgets, etc.) Be certain to add initials to the form.
6 | Should there be a requirement to review data a second (or more) time, simply copy the appropriate columns and insert them to the right of the original review columns.
7 | A separate worksheet may be required for each basin, stream reach or model, and coastal beach. In this case copy the worksheet and insert into the workbook in the proper sequential order. Please label the tab with the basin name, stream reach or model number(s), or beach to make use of the workbook easier.
8 | Please indicate status of each item by responding P (Pass), F (Fail), NA (Not applicable).
9 | When your review is complete and you are satisfied with the quality of the work, please sign a hard copy of the sign off sheet. Please be certain to retain the signed sheet with other project documents and be sure the next reviewer knows where to locate it. QA Verification reviewer, please scan the sign off sheet and add to the document files for the project.

## Sign off-QC Stamp
ATKINS QUALITY REVIEW CHECKLIST SIGN OFF FORM
Study / Stream Name | Monahans
Deliverable
MIP Case #:
PM: | Chad Cormack
QC REVIEW ACTIVITY
Ready for QC | *Originator / Date : | Lennart Matzen
| Date: | 2024-04-19
QC Review | *Reviewer / Date : | Clint Kimball
| Date: | 2024-04-26
Changes Made | *Originator/ Date : | Lennart Matzen
| Date: | 2024-05-13
QC Verification | *QC Reviewer: | Clint Kimball
| Date: | 2024-05-15
PQM Approval | *QA: | Connor Bishop
| Date: | 2024-06-19

## HEC-HMS
Hydrology
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
1 | Is correct projection used for HMS model and subbasins loaded in the HMS.
2 | Does the HMS subbasins match model domain extent
3 | Are NOAA 14 grids for all duration and AEPs loaded in the HMS
4 | Is precipitation type is set to Frequency Storm
5 | Are precipitation depths shown in frequency storm increasing with duration and with AEP
6 | Have precipitation plots created
7 | Spot few subbasins precipitation depths against NOAA 14 website to identify any errors in model setup
8 | Is 1% plus and 1% minus values for each duration calculated correctly
9 | Is either incremental or cumulative precipitation hyetographs for any event including 1% plus and 1% minus crossing
10 | Model, plans, elements named properly per guidance
11
12
13
Total QC citations for this review |  |  | 0
Percent Passing |  |  | 100%
Other Comments

## Model Geometry
Hydraulics | [8 empty] | 1
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Manohans |  |  |  |  | Manikanteswar Ramineni |  | 2024-04-26
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
RAS Mapper Setup
1 | Is the model projection correct? |  | Pass
2 | Does the terrain and model projections match |  | Unsure - See Reviewer Comments | See Picture 1 on the right | Other, See Orignator Comments | Yes, projections match. | CK
3 | Is the model geometry linked to Terrain, Land Cover, Infiltration and imperviousness layers |  | Pass
4 | Do the model results show Terrain, Landcover, Infiltration layers, and Imperviousness linked |  | Unsure - See Reviewer Comments | Please use the "LandCover_Channel" as Mannings and impervious layer. | Agree, Changes Made |  | CK
2D Mesh
5 | Does the digital terrain model input for the 2D model cover the entire 2D study area? |  | Pass
6 | Is the 2D mesh reasonably sized to limit cell count and obtain reasonable velocities? (Generally 100 -300' and max velocities less than 15-20 fps ) |  | Pass
7 | Is the model domain delineated properly to capture all contributing flows through rain-on-grid or external hydrograph? |  | Pass
8 | Are the break lines and refinement regions enforced properly |  | Unsure - See Reviewer Comments | See Issues shapefile. | Agree, Changes Made | See updated Issues Shapefile for individual responses. | CK
9 | Overlap with adjacent model is sufficient to achieve tie-in at main outflow and perimeter ponding locations |  | Unsure - See Reviewer Comments | See Issues shapefile. | Agree, Changes Made | See updated Issues Shapefile for individual responses. | CK
10 | Are there any 2D mesh errors? |  | Pass
Break lines
11 | Are break lines sufficiently detailed to capture features (thalweg, roads, banks, berms, etc.)? |  | Unsure - See Reviewer Comments | See Issues shapefile. | Agree, Changes Made | See updated Issues Shapefile for individual responses. | CK
12 | Are break lines consistent with the terrain data?
13 | Are break lines added such that the flow is not leaking.
14 | Do the stream lines continue to confluence and not end in the middle. (Exception roadway crossings)
15 | Are break lines for spillways added
16 | Are overlapping or very close break lines reviewed and cleaned, break line conflicts resolved and all break line planarized
Refinement Region
17 | Are refinement regions around major channel reaches, urban areas (>1K population), and major reservoirs (>5 ac) included
18 | Break line and refinement region conflicts were reviewed and resolved |  | Unsure - See Reviewer Comments | See Issues Shapefile. | Agree, Changes Made | See updated Issues Shapefile for individual responses. | CK
19 | Small holes in refinement regions filled, and small isolated refinement regions deleted
Manning's n
20 | Is the source of the roughness coefficients or criteria for selecting default roughness coefficients documented? |  | Pass
21 | Are channel Manning's n values reasonable? Are channel classification polygons continuous and have no gaps at roadway crossings etc. |  | Pass
22 | Is the Manning's n dataset associated with the geometry file? |  | Pass
Infiltration Layer / Impervious layer
23 | Are Curve Numbers (CN) and % imperviousness values reasonable, and sufficiently documented? Do the CN and % imperviousness values match TWDB guidance |  | Pass
24 | Are the adjustments applied to original Curve Numbers reasonable? Is the minimum CN higher than 30 even after adjustments. |  | Pass
25 | Has the Infiltration Layer and impervious layer been correctly assigned to the geometry |  | Unsure - See Reviewer Comments | Please use the "LandCover_Channel" as Mannings and impervious layer. | Agree, Changes Made |  | CK
SA/2D Connections and BCLines
26 | Are the SA/2D connections added near the model outflow to transfer flows with adjacent model. Are SA/2D connections well away from any boundary condition effects to no impact on flow or WSE? |  | Unsure - See Reviewer Comments | Please make sure the Inflow BC line is at the same location as the Upstream model SA2D and make sure the BC line is not too long so it won't distribute flow to other cells in low flow events. See Issues shapefile. | Other, See Orignator Comments | BC line is at the same location, and flow is distributed appropriately. | CK
27 | SA/2D lines are perpendicular to flow and contain 500-Yr or highest floodplain |  | Unsure - See Reviewer Comments | See Issues Shapefile. | Agree, Changes Made | See updated Issues Shapefile for individual responses. | CK
28 | Are multiple Sa/2D connections required for split areas to correctly transfer flow downstream |  | Pass
29 | Are SA/2D from upstream model match with inflow BCLines in downstream model. |  | Pass
30 | Are the BcLines for main outflow separated from perimeter areas. For areas with major overflow at perimeter are BCLines split
31 | Are Bclines added for any receiving inflows. |  | Pass
32 | SA/2D connections are added at validation locations such as gage, high water mark, effective BFE, etc.
33 | All SA/2D and BCLines enforced properly |  | Pass
34 | Are perimeter boundary conditions applied where flow is leaving the 2D area? |  | Pass
Terrain Modifications
35 | Has a copy of the Terrain layer (Terrain.HydroEnforced) been created ? |  | Pass
36 | Have hydro forcing burn lines been applied at major crossing using the Terrain Channel Modification Tool? Are the bottom width, and max extent widths of each line appropriately estimated to match the current structure size? Changing the side slopes can cause some issues with stability if it is too steep or vertical. |  | Unsure - See Reviewer Comments | See Issues shapefile. | Agree, Changes Made | See updated Issues Shapefile for individual responses. | CK
37 | Has the Terrain.HydroEnforced.hdf file been correctly assigned to the geometry? |  | Pass
38 | Are there any areas with ponding depths more than 2.5' where culverts are present
Major Hydraulics Structures (dams)
39 | Does the model account for any significant flow-regulating dams? Are there in the study that should be modeled.
40 | Were 2D connections appropriately set-up to model the regulated outflow from the dams?
41 | Are the sources for the dam operations documented?
42 | Are the rating curves calculated or obtained reasonable. Is the computed BLE WSE close to peak stages reported by InFRM or other sources
Other
42 | Are there any other comments related to the model geometry?
43
44
45
46
Total QC citations for this review |  |  | 0
Percent Passing |  |  | 100%
Other Comments

## Unsteady Flow Data
Hydrology
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
1 | Are the precipitation depths reasonable, and sufficiently documented? Explain anything other than frequency storm used for temporal distribution?
2 | Have the flow files for all events been assigned correctly to matching plans, to HMS or RAS output DSS, and not hard coded
3 | Are the flow files based on proper naming convention for the event, precip source ?
4 | Has the 2D flow area been assigned the correct DSS precipitation file from the hydrology folder? Has the appropriate event in the DSS file been selected?
5 | Does the model include all required and scoped events / frequencies?
6 | Does model plan and precip have same AEP event. For example, 10% AEP plan use 10% AEP rainfall.
7 | Was the areal reduction factor necessary?
8 | Is the precipitation depth across domain vary more than 10%. If so was spatially varied rainfall used? If not explain reason
9 | Is initial conditions/ elevations used for any dams or other locations in the model
10 | Are the incoming hydrographs being applied properly? (location, shapes, timing, etc.). Confirm that any incoming hydrographs have the same time and magnitude of peak flow by opening up the upstream RAS models
11 | For hydrographs transferred from one RAS model to a downstream RAS model, are the incoming and outgoing hydrographs being applied at a coincident location? The flows from upstream and downstream model cannot have more than 5% difference
12 | Do all boundary conditions have a hydrograph or elevation/slope data assigned?
13 | Is the downstream boundary condition consistent with ground slope or known downstream WSEL?
14 | Are there any other comments related to the unsteady flow data?
15
Total QC citations for this review |  |  | 0
Percent Passing |  |  | 100%
Other Comments

## Model Execution and Results
Hydraulics
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
Model Execution
1 | Is the Diffusion Wave Equation being used? |  | Pass
2 | Is the timestep appropriate for the mesh size and calculated velocities? |  | Pass
3 | Are the Computation Options and Tolerances set to the default values? If no, is it documented and justified? |  | Pass
4 | Are the advanced time step control tab settings selected properly ? Are Variable time step parameters reasonable / Meet project needs ? |  | Pass
5 | Are both the "hydrograph output interval" and "mapping output interval" set at a reasonable interval to capture peak flows within the model? |  | Pass
Model Results
6 | Does the model run with no cell errors?
7 | Does the model have acceptable volume conservation (less than 3%)
8 | Is the Courant number generally less than 2 but no greater than 5?
9 | Does the model run time longer than 12 Hrs? The model run cannot be longer than 24 Hrs.
9 | Was the model simulation long enough to pass the entire hydrograph(s) through the model? At least 24 Hrs after main peak, carefully look at multiple peak situations
10 | Is any flow trapped at the 2D boundary?
11 | Are all water-surface elevation convergence warning messages acceptable per computation tolerances?
12 | Are contributing areas contained within the 2D mesh or accounted for with inflow hydrographs?
13 | Are hydrographs at the internal and external boundary conditions smooth?
14 | Are there any crossing profiles for flow or stage hydrographs between any plans. This should also include 1% plus and 1% minus plans and not just AEP |  | Fail | Crossing profiles for SA2D conditions and BC lines | Disagree, No Changes Made | Disagree with item to be checked. 1% plus and 1% minus plans may cross AEP events other than the 1% event since the statistical formulation of the rainfall depths is not analagous to those events. | CK | Agree
15 | Check to make sure the computed maximum depth, WSEL, and velocity values are not from numerical surge (i.e. Beginning of model).
16 | Are the water surface and depth grids reasonable with no artificial dips or spikes?
17 | Is there any deep ponding areas (>3') behind road embankments? If so, is it reasonable or should the model be modified to allow flow through the embankment?
18 | Do the velocity grids appear reasonable with no unusually high velocity areas?
19 | Have instances of model instabilities at the beginning of the simulation due to initial wetting of a dry grid been addressed? Should a initial condition (wet start) be used?
20 | Are there other comments related to the model results?
Total QC citations for this review |  |  | 1
Percent Passing |  |  | 95%
Other Comments

## Model Validation
Validation
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
Validation is Performed for the 100-yr Only
1 | Is the method and parameters adjusted for model validation documented?
2 | Are the modifications to the Curve Number's and/or Manning's n reasonable?
Was areal reduction applied to achieve validation
3 | Have representative points in the watershed been used to check pluvial flows to confirm they are within the 1% Gage/ regression bounds?
4 | Do the peak discharges compare favorably to gages, effective studies, INFRM flows, or other approved benchmarks? If not, have attempts been made to validate?
5 | Are there other comments related to model validation?
Total QC citations for this review |  |  | 0
Percent Passing |  |  | 100%
Other Comments

## Model Clean-up
Model Clean-up
Job Name / Stream Name |  |  |  |  | Reviewer |  | Date
Comments for QC Reviewer from PM and/or TM
ID | Item to be checked | Originator Notes | Pass / Fail | Reviewer Comments | Originator Response | Originator Comments | Reviewer Initials | Backcheck Response
For Submission to Water Board
1 | HEC-RAS Project files: Have all temporary and interim project files been deleted from the model? (*.p##, *.g##, *.u##)
2 | HEC-RAS Output files: Have all unused output files been deleted from the project directory? (*.O##,*.hyd##, *.c##,*.b##, *.bco##, *.g##.hdf, *.p##.hdf, *.p##.blf, *.IC.O##, *.x##)
3 | HEC-RAS DSS Output file: Have any unused model outputs associated with plans no longer in use been deleted from the HEC-DSS Output file?
4 | HEC-RAS DSS Output file: Do hydrographs for all 7 recurrence interval events (10%, 4%, 2%, 1%, 0.2%, and 1% (+/-)) show up under the "Plot Stage and Flow Hydrographs" option within HEC-RAS?
5 | Have all old versions of geometries and plans been removed from the tree list within RAS Mapper?
6 | Have all non-essential shapefiles been removed from RAS Mapper?
7 | Are the terrain and land cover files correctly associated with the geometry and results layers?
8 | Have all folders and/or files that are not necessary for viewing results been deleted from the project folder (i.e. shapefiles, Excel documents, etc.)?
9 | Have all old and non-relevant comments within each unsteady flow plan been removed?
10 | Can the "computation log file" and "runtime messages" be seen for each plan?
Total QC citations for this review |  |  | 0
Percent Passing |  |  | 100%
Other Comments

## Drop Down List
Pass
Fail
Unsure - See Reviewer Comments
Not Applicable for This
Agree, Changes Made
Disagree, No Changes Made
Other, See Orignator Comments