## Sign off-QC Stamp
ATKINS QUALITY REVIEW CHECKLIST SIGN OFF FORM
Study / Stream Name | Monument Watershed
Deliverable | M2 FRD GDB
MIP Case #: | 22-06-0048S
PM: | Chad Cormack
QC REVIEW ACTIVITY
Ready for QC | *Originator / Date : | Billy Shamburg / 20241011
QC Review | *Reviewer / Date : | Clint Kimball / 20241015
Changes Made | *Originator/ Date : | Billy Shamburg / 20241016
QC Verification | *QC Reviewer:
Date:
PQM Approval | *QA:
Date:

## Attribute Checks v1
Study |  |  | Monument Watershed
Reviewer |  |  | Clint Kimball
Review Date |  |  | 10/15/2024
Spatial Analyst |  |  | Updated these CID attributes
Response Date |  |  | 10/16/2024
Line No. | Feature Dataset | Feature Class | Field | Field Type¹ | Pass/ Fail | Reviewer Comment | Response Comment
1 | BASE_DATASET | S_POL_AR | DFIRM_ID |  | Pass
2 |  |  | VERSION_ID |  | Pass
3 |  |  | POL_AR_ID |  | Pass
4 |  |  | POL_NAME1 |  | Pass
5 |  |  | POL_NAME2 |  | Pass
6 |  |  | POL_NAME3 |  | Pass
7 |  |  | CO_FIPS |  | Pass
8 |  |  | ST_FIPS |  | Pass
9 |  |  | COMM_NO |  | Fail | Andrews County is 0006, Winkler County is 1250, Loving County is 1235 | Updated these COMM_NO attributes
10 |  |  | CID |  | Fail | Andrews County is 480006, Winkler County is 481250 | Updated these CID attributes
11 |  |  | ANI_TF |  | Pass
12 |  |  | ANI_FIRM |  | Pass
13 |  |  | COM_NFO_ID |  | Pass
14 |  |  | SOURCE_CIT |  | Pass
15 |  | S_HUC_AR | HUC_CODE |  | Pass
16 |  |  | HUC_NAME |  | Pass
17 |  |  | DIGITS |  | Pass
18 |  |  | CASE_NO |  | Pass
19 |  |  | VERSION_ID |  | Pass
20 |  |  | SOURCE_CIT |  | Pass
21 | EBFE_DATASET | SUBBASINS | EST_ID |  |  | Empty
22 |  |  | VERSION_ID |  |  | Empty
23 |  |  | E_SUBAS_ID |  |  | Empty
24 |  |  | E_SUBAS_NM |  |  | Empty
25 |  |  | HUC8_CODE |  |  | Empty
26 |  |  | WTR_NM | Hidden |  | Empty
27 |  |  | BASIN_DESC | Hidden |  | Empty
28 |  |  | EST_AREA |  |  | Empty
29 |  |  | AREA_UNIT |  |  | Empty
30 |  |  | NODE_ID | Hidden |  | Empty
31 |  |  | BASIN_TYP | Hidden |  | Empty
32 |  |  | SOURCE_CIT |  |  | Empty
33 |  |  | US_1 | New |  | Empty
34 |  |  | US_2 | New |  | Empty
35 |  |  | US_3 | New |  | Empty
36 |  |  | US_4 | New |  | Empty
37 |  |  | DS_1 | New |  | Empty
38 |  |  | PRECIP_IN | New |  | Empty
39 |  |  | MAINCHSLP | New |  | Empty
40 |  |  | E_Q_10PCT | New |  | Empty
41 |  |  | E_Q_04PCT | New |  | Empty
42 |  |  | E_Q_02PCT | New |  | Empty
43 |  |  | E_Q_01PCT | New |  | Empty
44 |  |  | E_Q_01PLUS | New |  | Empty
45 |  |  | E_Q_01MIN | New |  | Empty
46 |  |  | E_Q_0_2PCT | New |  | Empty
47 |  | XS_1D | EST_ID |  |  | Empty
48 |  |  | VERSION_ID |  |  | Empty
49 |  |  | XS_LN_ID |  |  | Empty
50 |  |  | WTR_NM |  |  | Empty
51 |  |  | STREAM_STN |  |  | Empty
52 |  |  | START_ID |  |  | Empty
53 |  |  | XS_LTR | Hidden |  | Empty
54 |  |  | XS_LN_TYP |  |  | Empty
55 |  |  | E_WSE_1PCT |  |  | Empty
56 |  |  | STRMBED_EL | Hidden |  | Empty
57 |  |  | LEN_UNIT | Hidden |  | Empty
58 |  |  | V_DATUM |  |  | Empty
59 |  |  | PROFXS_TXT |  |  | Empty
60 |  |  | MODEL_ID |  |  | Empty
61 |  |  | SEQ |  |  | Empty
62 |  |  | SOURCE_CIT |  |  | Empty
63 |  |  | E_WSE_10PC | New |  | Empty
64 |  |  | E_WSE_4PCT | New |  | Empty
65 |  |  | E_WSE_2PCT | New |  | Empty
66 |  |  | E_WSE_1PLU | New |  | Empty
67 |  |  | E_WSE_1MIN | New |  | Empty
68 |  |  | E_WSE_0_2P | New |  | Empty
69 |  |  | E_Q_10PCT | New |  | Empty
70 |  |  | E_Q_04PCT | New |  | Empty
71 |  |  | E_Q_02PCT | New |  | Empty
72 |  |  | E_1_02PCT | New |  | Empty
73 |  |  | E_Q_01PLUS | New |  | Empty
74 |  |  | E_Q_01MIN | New |  | Empty
75 |  |  | E_Q_0_2PCT | New |  | Empty
76 |  | BFE_2D | EST_ID |  | Pass
77 |  |  | VERSION_ID |  | Pass
78 |  |  | EBFE_LN_ID |  | Pass
79 |  |  | BLELEV1PCT |  | Pass
80 |  |  | LEN_UNIT |  | Pass
81 |  |  | V_DATUM |  | Pass
82 |  |  | SOURCE_CIT |  | Pass
83 |  |  | BFE_LN_TYP | New | Pass
84 |  | WTR_LN | EST_ID |  | Pass
85 |  |  | VERSION_ID |  | Pass
86 |  |  | WTR_LN_ID |  | Pass
87 |  |  | WTR_NM |  | Pass
88 |  |  | SHOWN_FIRM | Hidden | Pass
89 |  |  | SHOWN_INDX | Hidden | Pass
90 |  |  | SOURCE_CIT |  | Pass
91 |  | WTR_AR | EST_ID |  | Pass
92 |  |  | VERSION_ID |  | Pass
93 |  |  | WTR_AR_ID |  | Pass
94 |  |  | WTR_NM |  | Pass
95 |  |  | SHOWN_FIRM | Hidden | Pass
96 |  |  | SHOWN_INDX | Hidden | Pass
97 |  |  | SOURCE_CIT |  | Pass
98 |  | DTL_STUD_LN | DTL_LN_ID |  | Pass
99 |  |  | VERSION_ID |  | Pass
100 |  |  | LOMR_ID | Hidden | Pass
101 |  |  | EFF_DATE |  | Pass
102 |  |  | CASE_NO | Hidden | Pass
103 |  |  | SCALE | Hidden | Pass
104 |  |  | SOURCE_CIT |  | Pass
105 |  |  | STATUS | Hidden | Pass
106 |  |  | FIRM_PAN | New | Pass
107 |  |  | TYPE | New | Pass
108 |  |  | CD_YN | New | Pass
109 |  |  | CD_POC | New | Pass
110 |  |  | CD_ADD1 | New | Pass
111 |  |  | CD_ADD2 | New | Pass
112 |  |  | CD_CTY | New | Pass
113 |  |  | CD_STATE | New | Pass
114 |  |  | CD_ZIP | New | Pass
115 |  |  | CD_PHONE | New | Pass
116 |  |  | CD_EMAIL | New | Pass
117 |  | DTL_STUD_AR | DTL_AR_ID |  | Pass
118 |  |  | VERSION_ID |  | Pass
119 |  |  | LOMR_ID | Hidden | Pass
120 |  |  | EFF_DATE |  | Pass
121 |  |  | CASE_NO | Hidden | Pass
122 |  |  | SCALE | Hidden | Pass
123 |  |  | SOURCE_CIT |  | Pass
124 |  |  | STATUS | Hidden | Pass
125 |  |  | FIRM_PAN | New | Pass
126 |  |  | TYPE | New | Pass
127 |  |  | CD_YN | New | Pass
128 |  |  | CD_POC | New | Pass
129 |  |  | CD_ADD1 | New | Pass
130 |  |  | CD_ADD2 | New | Pass
131 |  |  | CD_CTY | New | Pass
132 |  |  | CD_STATE | New | Pass
133 |  |  | CD_ZIP | New | Pass
134 |  |  | CD_PHONE | New | Pass
135 |  |  | CD_EMAIL | New | Pass
136 |  | FLD_HAZ_AR | EST_ID |  | Pass
137 |  |  | VERSION_ID |  | Pass
138 |  |  | EST_AR_ID |  | Pass
139 |  |  | STUDY_TYP | Hidden | Pass
140 |  |  | FLD_ZONE | Hidden | Pass
141 |  |  | ZONE_SUBTY |  | Pass
142 |  |  | SFHA_TF | Hidden | Pass
143 |  |  | STATIC_BFE | Hidden | Pass
144 |  |  | V_DATUM |  | Pass
145 |  |  | DEPTH | Hidden | Pass
146 |  |  | LEN_UNIT |  | Pass
147 |  |  | VELOCITY | Hidden | Pass
148 |  |  | VEL_UNIT | Hidden | Pass
149 |  |  | AR_REVERT | Hidden | Pass
150 |  |  | AR_SUBTRV | Hidden | Pass
151 |  |  | BFE_REVERT | Hidden | Pass
152 |  |  | DEP_REVERT | Hidden | Pass
153 |  |  | DUAL_ZONE | Hidden | Pass
154 |  |  | SOURCE_CIT |  | Pass
155 |  |  | EST_RISK | New | Pass
156 |  | TENPCT_FP | EST_ID |  | Pass
157 |  |  | VERSION_ID |  | Pass
158 |  |  | EST_AR_ID |  | Pass
159 |  |  | STUDY_TYP | Hidden | Pass
160 |  |  | FLD_ZONE | Hidden | Pass
161 |  |  | ZONE_SUBTY |  | Pass
162 |  |  | SFHA_TF | Hidden | Pass
163 |  |  | STATIC_BFE | Hidden | Pass
164 |  |  | V_DATUM |  | Pass
165 |  |  | DEPTH | Hidden | Pass
166 |  |  | LEN_UNIT |  | Pass
167 |  |  | VELOCITY | Hidden | Pass
168 |  |  | VEL_UNIT | Hidden | Pass
169 |  |  | AR_REVERT | Hidden | Pass
170 |  |  | AR_SUBTRV | Hidden | Pass
171 |  |  | BFE_REVERT | Hidden | Pass
172 |  |  | DEP_REVERT | Hidden | Pass
173 |  |  | DUAL_ZONE | Hidden | Pass
174 |  |  | SOURCE_CIT |  | Pass
175 |  |  | EST_RISK | New | Pass
176 | MIT-HAZ_DATASETS | S_FRAS_PT | AOMI_ID |  |  | Empty
177 |  |  | CID |  |  | Empty
178 |  |  | POL_NAME1 |  |  | Empty
179 |  |  | AOMI_CLASS |  |  | Empty
180 |  |  | AOMI_TYP |  |  | Empty
181 |  |  | AOMI_CAT |  |  | Empty
182 |  |  | AOMI_SRCE |  |  | Empty
183 |  |  | AOMI_INFO |  |  | Empty
184 |  |  | NOTES |  |  | Empty
185 |  |  | HUC8_CODE |  |  | Empty
186 |  |  | CASE_NO |  |  | Empty
187 |  |  | VERSION_ID |  |  | Empty
188 |  |  | SOURCE_CIT |  |  | Empty
189 |  | S_AOMI_AR | AOMI_ID |  | Pass
190 |  |  | CID |  | Fail | Update missing values per comments in BASE_DATASET above | Updated these CID attributes
191 |  |  | POL_NAME1 |  | Pass
192 |  |  | AOMI_CLASS |  | Pass
193 |  |  | AOMI_TYP |  | Pass
194 |  |  | AOMI_INFO |  | Pass
195 |  |  | HUC8_CODE |  | Pass
196 |  |  | CASE_NO |  | Pass
197 |  |  | VERSION_ID |  | Pass
198 |  |  | SOURCE_CIT |  | Pass
199 |  | S_FRAC_AR | CEN_BLK_ID |  | Pass
200 |  |  | ARV_BG_TOT |  | Pass
201 |  |  | ARV_CN_TOT |  | Pass
202 |  |  | HAZARD_TYP | Hidden | Pass
203 |  |  | SCENAR_ID | Hidden | Pass
204 |  |  | TOT_LOSS10 | Hidden | Pass
205 |  |  | BL_TOT10 | Hidden | Pass
206 |  |  | CL_TOT10 | Hidden | Pass
207 |  |  | TOT_LOSS04 | Hidden | Pass
208 |  |  | BL_TOT04 | Hidden | Pass
209 |  |  | CL_TOT04 | Hidden | Pass
210 |  |  | TOT_LOSS02 | Hidden | Pass
211 |  |  | BL_TOT02 | Hidden | Pass
212 |  |  | CL_TOT02 | Hidden | Pass
213 |  |  | TOT_LOSS01 |  | Pass
214 |  |  | BL_TOT01 |  | Pass
215 |  |  | CL_TOT01 |  | Pass
216 |  |  | TOT_LSS0_2 | Hidden | Pass
217 |  |  | BL_TOT0_2 | Hidden | Pass
218 |  |  | CL_TOT0_2 | Hidden | Pass
219 |  |  | TOT_LSSAAL | Hidden | Pass
220 |  |  | BL_TOTAAL | Hidden | Pass
221 |  |  | CL_TOTAAL | Hidden | Pass
222 |  |  | HUC8_CODE |  | Pass
223 |  |  | CASE_NO |  | Pass
224 |  |  | VERSION_ID |  | Pass
225 |  |  | SOURCE_CIT |  | Pass
226 | CNMS_ DATASET | S_STUDIES_LN |  |  |  | Empty
227 |  | S_UNMAPPED_LN |  |  |  | Empty
228 | GRIDS | BLE_WSE01PCT |  |  | Pass
229 |  | BLE_WSE0_2PCT |  |  | Pass
230 |  | BLE_DEP01PCT |  |  | Pass
231 |  | BLE_DEP0_2PCT |  |  | Pass
232 | L_SOURCE_CIT | SOURCE_CIT |  |  | Pass
233 |  | DFIRM_ID |  |  | Pass
234 |  | CITATION |  |  | Pass
235 |  | PUBLISHER |  |  | Pass
236 |  | TITLE |  |  | Pass
237 |  | AUTHOR |  |  | Pass
238 |  | PUB_PLACE |  |  | Pass
239 |  | PUB_DATE |  |  | Pass
240 |  | WEBLINK |  |  | Pass
241 |  | SRC_SCALE |  |  | Pass
242 |  | MEDIA |  |  | Pass
243 |  | CASE_NO |  |  | Pass
244 |  | VERSION_ID |  |  | Pass
¹ | "Hidden" fields are those not visible to the public in the Region 6 viewer at https://webapps.usgs.gov/infrm/estbfe/.
"New" fields are created for the BLE database and are not described in the Technical References. Refer to the Base Level Engineering, Region 6 Submittal Guidance instead.
Remove extra fields before submitting

## Spatial Checks v1
Study |  | Monument Watershed
Reviewer |  | Clint Kimball
Review Date |  | 10/15/2024
Spatial Analyst |  | Billy Shamburg
Response Date |  | 10/16/2024
Line No. | Feature Dataset | Feature Class | Pass/ Fail | Topology Checks² | Reviewer Comment | Response Comment
1 | BASE_DATASET | S_POL_AR | Pass
2 |  | S_HUC_AR | Pass
3 | EBFE_DATASET | SUBBASINS | N/A
4 |  | XS_1D | N/A
5 |  | BFE_2D | Pass
6 |  | WTR_LN | Pass
7 |  | WTR_AR | Pass
8 |  | DTL_STUD_LN | Pass
9 |  | DTL_STUD_AR | Pass
10 |  | FLD_HAZ_AR | Pass
11 |  | TENPCT_FP | Pass
12 | MIT-HAZ_DATASET | S_AOMI_PT | N/A |  |  |  | `
13 |  | S_AOMI_AR | Pass
14 |  | S_FRAC_AR | Pass
15 | CNMS_DATASET | S_STUDIES_LN | N/A
16 |  | S_UNMAPPED_LN | N/A
17 | GRIDS | BLE_WSE_01PCT | Pass
18 |  | BLE_WSE_0_2PCT | Pass
19 |  | BLE_DEP_01PCT | Pass
20 |  | BLE_DEP_0_2PCT | Pass
² | The following topology rules are listed in Base Level Engineering, Region 6 Submittal Guidance,Version 6, July 2021, page 30.

## Internal QC Checks
Study | Monument Watershed
Spatial Analyst
Completion Date
| QC Test | Pass/ Fail | Test Description | Results Note
1 | Zero Value Cells | P | ensure final BLE rasters do not have cells with zero values
2 | Results spikes | P | checks for abnormal DEP/WSE spikes often found along 2D model cell faces | found 1 anomoly and corrected
3 | Raster Extents | P | to ensure final BLE rasters (DEP & WSE) have values for cells in the same location. Geoprocess 'Is_Null' for each grid; add results for each event (WSE+DEP) and ensure all cell values are either "0" or "2"…no "1" values.
4 | Raster Value Outliers | P | To ensure DEP1pct values only exist where there's DEP02pct values. Divide DEP02pct 'Is_Null' grid by DEP1pct and all cells should equal zero "0"
5 | HUC Sections Edges | P | Ensure Monument grids and feature classes have seamless edge with Monahans
6
7
8
9
10
11
12
13
14